## Table 1
| Week Start | Weekly Performance to Date
| 45733 | ALL Aircraft (AC) |  |  |  | Shop Complete (AC) |  |  |  | Shop Complete (MM) |  |  | Major Milestone (MM) |  |  |  | Mon 3/17 | Tue 3/18 | Wed 3/19 | Thu 3/20 | Fri 3/21 | Sat 3/22 | Sun 3/23
|  | Actuals (BL) | Chk / Maint / Bltn | NCOs Closed | NCOs Created | Conformity | Non-Conformity | HF NCO | BARGE | Conformity | Non-Conformity | HF NCO | Balance to Go | Actuals | NCOs Closed | NCOs Created | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals
| Total | 144 | 32 | 145 | 130 |  | 43 | 91 |  |  | 35 | 75 | 9980 | 124 | 143 | 126 | 24 | 26 | 28 | 30 | 16
|  | ALL Aircraft 1 | [7 empty] | AC1 - Structures Complete
| Aircraft 1 | 55 | 16 | 83 | 66 |  | 16 | 53 | Total |  | 13 | 45 | 4198 | 37 | 83 | 64 | 7 | 8 | 8 | 10 | 4
Aircraft 1 | BARGE1 | 5 |  | 13 | 11 |  | 1 | 10 | BARGE1 |  | 1 | 8 | 798 | 5 | 13 | 11 | Mon 3/17: 2; Wed 3/19: 2; Thu 3/20: 1
Aircraft 1 | BARGE2 | 6 |  | 11 | 9 |  | 2 | 9 | BARGE2 |  | 2 | 8 | 804 | 5 | 11 | 9 | Tue 3/18: 1; Wed 3/19: 2; Thu 3/20: 2
Aircraft 1 | BARGE3 | 13 |  | 5 | 3 |  | 5 | 15 | BARGE3 |  | 5 | 14 | 1440 | 13 | 5 | 3 | 3 | 3 | 2 | 2 | 3
Aircraft 1 | BARGE4 | 4 |  | 1 | 6 |  | 1 | 2 | BARGE4 |  | 1 | 2 | 137 | 4 | 1 | 5 | Mon 3/17: 1; Tue 3/18: 2; Wed 3/19: 1
Aircraft 1 | BARGE5 | 7 |  | 37 | 23 |  | 2 | 10 | BARGE5 |  | 2 | 9 | 526 | 7 | 37 | 22 | Mon 3/17: 1; Tue 3/18: 2; Thu 3/20: 3; Fri 3/21: 1
Aircraft 1 | BARGE6 | 3 |  | 16 | 14 |  | 2 | 4 | BARGE6 |  | 2 | 4 | 473 | 3 | 16 | 14 | Wed 3/19: 1; Thu 3/20: 2
Aircraft 1 | MISC | 17 |  |  |  |  | 3 | 3 | MISC |  |  |  | 20
|  | ALL Aircraft 2 | [7 empty] | AC2 - Structures Complete
| Aircraft 2 | 89 | 16 | 62 | 64 |  | 27 | 38 | Total |  | 22 | 30 | 5782 | 87 | 60 | 62 | 17 | 18 | 20 | 20 | 12
Aircraft 2 | BARGE1 | 18 |  | 19 | 17 |  | 4 | 6 | BARGE1 |  | 4 | 5 | 1161 | 18 | 18 | 17 | 1 | 2 | 6 | 3 | 6
Aircraft 2 | BARGE2 | 11 |  | 10 | 10 |  | 7 | 5 | BARGE2 |  | 5 | 3 | 898 | 11 | 9 | 10 | 2 | 3 | 2 | 3 | 1
Aircraft 2 | BARGE3 | 21 |  | 11 | 6 |  | 4 | 5 | BARGE3 |  | 4 | 5 | 1956 | 21 | 11 | 5 | 6 | 5 | 2 | 5 | 3
Aircraft 2 | BARGE4 | 12 |  | 3 | 9 |  | 5 | 3 | BARGE4 |  | 5 | 3 | 423 | 12 | 3 | 9 | Tue 3/18: 3; Wed 3/19: 3; Thu 3/20: 4; Fri 3/21: 2
Aircraft 2 | BARGE5 | 20 |  | 9 | 11 |  | 4 | 15 | BARGE5 |  | 4 | 11 | 813 | 18 | 9 | 10 | Mon 3/17: 6; Tue 3/18: 3; Wed 3/19: 5; Thu 3/20: 4
Aircraft 2 | BARGE6 | 7 |  | 10 | 11 |  |  | 3 | BARGE6 |  |  | 3 | 506 | 7 | 10 | 11 | Mon 3/17: 2; Tue 3/18: 2; Wed 3/19: 2; Thu 3/20: 1
Aircraft 2 | MISC | [5 empty] | 3 | 1 | MISC |  |  |  | 25