## Table 1
| Week Start | Weekly Performance to Date
| 45747 | ALL Aircraft (AC) |  |  |  | Shop Complete (AC) |  |  |  | Shop Complete (MM) |  |  | Major Milestone (MM) |  |  |  | Mon 3/31 | Tue 4/1 | Wed 4/2 | Thu 4/3 | Fri 4/4 | Sat 4/5 | Sun 4/6
|  | Actuals (BL) | Chk / Maint / Bltn | NCOs Closed | NCOs Created | Conformity | Non-Conformity | HF NCO | BARGE | Conformity | Non-Conformity | HF NCO | Balance to Go | Actuals | NCOs Closed | NCOs Created | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals
| Total | 157 | 35 | 132 | 151 | 1 | 36 | 77 |  |  | 29 | 61 | 9663 | 122 | 128 | 147 | 21 | 25 | 37 | 20 | 19
|  | ALL Aircraft 1 | [7 empty] | AC1 - Structures Complete
| Aircraft 1 | 82 | 17 | 58 | 53 |  | 16 | 41 | Total |  | 13 | 33 | 4084 | 47 | 57 | 51 | 5 | 10 | 18 | 8 | 6
Aircraft 1 | BARGE1 | 6 |  | 9 | 9 |  |  | 9 | BARGE1 |  |  | 7 | 774 | 6 | 9 | 9 | Mon 3/31: 2; Tue 4/1: 1; Wed 4/2: 2; Thu 4/3: 1
Aircraft 1 | BARGE2 | 7 |  | 12 | 9 |  | 3 | 5 | BARGE2 |  | 3 | 4 | 787 | 7 | 12 | 9 | 1 | 1 | 3 | 1 | 1
Aircraft 1 | BARGE3 | 17 |  | 9 | 4 |  | 5 | 12 | BARGE3 |  | 5 | 11 | 1402 | 17 | 9 | 4 | 1 | 6 | 5 | 4 | 1
Aircraft 1 | BARGE4 | 3 |  | 4 | 5 |  | 1 | 1 | BARGE4 |  | 1 | 1 | 130 | 3 | 4 | 3 | bar: Tue 4/1 to Wed 4/2; Fri 4/4
Aircraft 1 | BARGE5 | 44 |  | 12 | 10 |  | 5 | 10 | BARGE5 |  | 2 | 6 | 526 | 9 | 11 | 10 | Tue 4/1: 1; Wed 4/2: 3; Thu 4/3: 2; Fri 4/4: 3
Aircraft 1 | BARGE6 | 5 |  | 12 | 16 |  | 2 | 4 | BARGE6 |  | 2 | 4 | 463 | 5 | 12 | 16 | Mon 3/31: 1; Wed 4/2: 4
Aircraft 1 | MISC | [7 empty] | MISC |  |  |  | 2
|  | ALL Aircraft 2 | [7 empty] | AC2 - Structures Complete
| Aircraft 2 | 75 | 18 | 74 | 98 | 1 | 20 | 36 | Total |  | 16 | 28 | 5579 | 75 | 71 | 96 | 16 | 15 | 19 | 12 | 13
Aircraft 2 | BARGE1 | 14 |  | 8 | 14 |  | 2 | 7 | BARGE1 |  | 2 | 5 | 1110 | 14 | 8 | 14 | 1 | 2 | 5 | 4 | 2
Aircraft 2 | BARGE2 | 9 |  | 18 | 23 | 1 | 1 | 7 | BARGE2 |  |  | 5 | 870 | 9 | 18 | 23 | Tue 4/1: 3; Wed 4/2: 1; Thu 4/3: 2; Fri 4/4: 3
Aircraft 2 | BARGE3 | 24 |  | 11 | 11 |  | 5 | 5 | BARGE3 |  | 5 | 5 | 1909 | 24 | 11 | 11 | 5 | 5 | 7 | 3 | 4
Aircraft 2 | BARGE4 | 9 |  | 7 | 7 |  | 2 | 2 | BARGE4 |  | 2 | 2 | 388 | 9 | 7 | 7 | Mon 3/31: 4; Tue 4/1: 1; Wed 4/2: 3; Thu 4/3: 1
Aircraft 2 | BARGE5 | 11 |  | 16 | 33 |  | 5 | 12 | BARGE5 |  | 2 | 8 | 807 | 11 | 13 | 32 | 3 | 2 | 2 | 1 | 3
Aircraft 2 | BARGE6 | 8 |  | 14 | 9 |  | 5 | 3 | BARGE6 |  | 5 | 3 | 494 | 8 | 14 | 9 | 3 | 2 | 1 | 1 | 1
Aircraft 2 | MISC |  |  |  | 1 |  |  |  | MISC |  |  |  | 1