## Table 1
| Week Start | Weekly Performance to Date
| 2025-04-14 | ALL Aircraft (AC) |  |  |  | Shop Complete (AC) |  |  |  | Shop Complete (MM) |  |  | Major Milestone (MM) |  |  |  | Mon 4/14 | Tue 4/15 | Wed 4/16 | Thu 4/17 | Fri 4/18 | Sat 4/19 | Sun 4/20
|  | Actuals (BL) | Chk / Maint / Bltn | NCOs Closed | NCOs Created | Conformity | Non-Conformity | HF NCO | BARGE | Conformity | Non-Conformity | HF NCO | Balance to Go | Actuals | NCOs Closed | NCOs Created | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals
| Total | 191 | 30 | 168 | 149 | 1 | 60 | 72 |  |  | 52 | 59 | 9307 | 145 | 166 | 140 | 27 | 30 | 28 | 38 | 22
|  | ALL Aircraft 1 | [7 empty] | AC1 - Structures Complete
| Aircraft 1 | 98 | 18 | 76 | 67 |  | 31 | 41 | Total |  | 27 | 34 | 3995 | 53 | 75 | 60 | 9 | 11 | 11 | 11 | 11
Aircraft 1 | BARGE1 | 6 |  | 12 | 10 |  | 8 | 9 | BARGE1 |  | 8 | 8 | 771 | 6 | 12 | 9 | Tue 4/15: 1; Wed 4/16: 1; Thu 4/17: 1; Fri 4/18: 3
Aircraft 1 | BARGE2 | 10 |  | 12 | 9 |  | 2 | 4 | BARGE2 |  | 1 | 3 | 770 | 10 | 12 | 8 | 2 | 2 | 1 | 2 | 3
Aircraft 1 | BARGE3 | 20 |  | 20 | 18 |  | 10 | 11 | BARGE3 |  | 10 | 10 | 1368 | 20 | 20 | 18 | Mon 4/14: 5; Tue 4/15: 6; Wed 4/16: 6; Thu 4/17: 3
Aircraft 1 | BARGE4 | 2 |  | 4 | 11 |  | 2 | 1 | BARGE4 |  | 2 | 1 | 128 |  | 3 | 7 | bar: Tue 4/15 to Fri 4/18
Aircraft 1 | BARGE5 | 52 |  | 13 | 7 |  | 4 | 12 | BARGE5 |  | 2 | 8 | 506 | 9 | 13 | 6 | 1 | 1 | 1 | 4 | 2
Aircraft 1 | BARGE6 | 8 |  | 15 | 12 |  | 5 | 4 | BARGE6 |  | 4 | 4 | 450 | 8 | 15 | 12 | 1 | 1 | 2 | 1 | 3
Aircraft 1 | MISC | [7 empty] | MISC |  |  |  | 2 | bar: Tue 4/15 to Fri 4/18
|  | ALL Aircraft 2 | [7 empty] | AC2 - Structures Complete
| Aircraft 2 | 93 | 12 | 92 | 82 | 1 | 29 | 31 | Total |  | 25 | 25 | 5312 | 92 | 91 | 80 | 18 | 19 | 17 | 27 | 11
Aircraft 2 | BARGE1 | 22 |  | 18 | 8 |  | 10 | 7 | BARGE1 |  | 10 | 6 | 1063 | 22 | 18 | 8 | 6 | 4 | 3 | 6 | 3
Aircraft 2 | BARGE2 | 11 |  | 16 | 23 | 1 | 2 | 5 | BARGE2 |  | 1 | 3 | 851 | 11 | 15 | 22 | 2 | 3 | 2 | 1 | 3
Aircraft 2 | BARGE3 | 30 |  | 30 | 15 |  | 11 | 4 | BARGE3 |  | 11 | 4 | 1857 | 30 | 30 | 15 | 6 | 5 | 5 | 10 | 4
Aircraft 2 | BARGE4 | 10 |  | 3 | 10 |  |  | 2 | BARGE4 |  |  | 2 | 291 | 10 | 3 | 9 | 2 | 4 | 2 | 1 | 1
Aircraft 2 | BARGE5 | 7 |  | 18 | 17 |  | 5 | 10 | BARGE5 |  | 2 | 7 | 782 | 6 | 18 | 17 | Tue 4/15: 1; Wed 4/16: 2; Thu 4/17: 3
Aircraft 2 | BARGE6 | 13 |  | 7 | 9 |  | 1 | 3 | BARGE6 |  | 1 | 3 | 467 | 13 | 7 | 9 | Mon 4/14: 2; Tue 4/15: 2; Wed 4/16: 3; Thu 4/17: 6
Aircraft 2 | MISC | [7 empty] | MISC |  |  |  | 1 | bar: Tue 4/15 to Fri 4/18

## Table 1 (2)
| Week Start | Weekly Performance to Date
| 2025-04-14 | ALL Aircraft (AC) |  |  |  | Shop Complete (AC) |  |  |  | Shop Complete (MM) |  |  | Major Milestone (MM) |  |  |  | Mon 4/14 | Tue 4/15 | Wed 4/16 | Thu 4/17 | Fri 4/18 | Sat 4/19 | Sun 4/20
|  | Actuals (BL) | Chk / Maint / Bltn | NCOs Closed | NCOs Created | Conformity | Non-Conformity | HF NCO | BARGE | Conformity | Non-Conformity | HF NCO | Balance to Go | Actuals | NCOs Closed | NCOs Created | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals
| Total | 191 | 30 | 168 | 149 | 1 | 60 | 72 |  |  | 52 | 59 | 9307 | 145 | 166 | 140 | 27 | 30 | 28 | 38 | 22
|  | ALL Aircraft 1 | [7 empty] | AC1 - Structures Complete
AC1 | Aircraft 1 | 98 | 18 | 76 | 67 |  | 31 | 41 | Total |  | 27 | 34 | 3995 | 53 | 75 | 60 | 9 | 11 | 11 | 11 | 11
| BARGE1 | 6 |  | 12 | 10 |  | 8 | 9 | BARGE1 |  | 8 | 8 | 771 | 6 | 12 | 9 | Tue 4/15: 1; Wed 4/16: 1; Thu 4/17: 1; Fri 4/18: 3
| BARGE2 | 10 |  | 12 | 9 |  | 2 | 4 | BARGE2 |  | 1 | 3 | 770 | 10 | 12 | 8 | 2 | 2 | 1 | 2 | 3
| BARGE3 | 20 |  | 20 | 18 |  | 10 | 11 | BARGE3 |  | 10 | 10 | 1368 | 20 | 20 | 18 | Mon 4/14: 5; Tue 4/15: 6; Wed 4/16: 6; Thu 4/17: 3
| BARGE4 | 2 |  | 4 | 11 |  | 2 | 1 | BARGE4 |  | 2 | 1 | 128 |  | 3 | 7 | bar: Tue 4/15 to Fri 4/18
| BARGE5 | 52 |  | 13 | 7 |  | 4 | 12 | BARGE5 |  | 2 | 8 | 506 | 9 | 13 | 6 | 1 | 1 | 1 | 4 | 2
| BARGE6 | 8 |  | 15 | 12 |  | 5 | 4 | BARGE6 |  | 4 | 4 | 450 | 8 | 15 | 12 | 1 | 1 | 2 | 1 | 3
| MISC | [7 empty] | MISC |  |  |  | 2 | bar: Tue 4/15 to Fri 4/18
|  | ALL Aircraft 2 | [7 empty] | AC2 - Structures Complete
AC2 | Aircraft 2 | 93 | 12 | 92 | 82 | 1 | 29 | 31 | Total |  | 25 | 25 | 5312 | 92 | 91 | 80 | 18 | 19 | 17 | 27 | 11
| BARGE1 | 22 |  | 18 | 8 |  | 10 | 7 | BARGE1 |  | 10 | 6 | 1063 | 22 | 18 | 8 | 6 | 4 | 3 | 6 | 3
| BARGE2 | 11 |  | 16 | 23 | 1 | 2 | 5 | BARGE2 |  | 1 | 3 | 851 | 11 | 15 | 22 | 2 | 3 | 2 | 1 | 3
| BARGE3 | 30 |  | 30 | 15 |  | 11 | 4 | BARGE3 |  | 11 | 4 | 1857 | 30 | 30 | 15 | 6 | 5 | 5 | 10 | 4
| BARGE4 | 10 |  | 3 | 10 |  |  | 2 | BARGE4 |  |  | 2 | 291 | 10 | 3 | 9 | 2 | 4 | 2 | 1 | 1
| BARGE5 | 7 |  | 18 | 17 |  | 5 | 10 | BARGE5 |  | 2 | 7 | 782 | 6 | 18 | 17 | Tue 4/15: 1; Wed 4/16: 2; Thu 4/17: 3
| BARGE6 | 13 |  | 7 | 9 |  | 1 | 3 | BARGE6 |  | 1 | 3 | 467 | 13 | 7 | 9 | Mon 4/14: 2; Tue 4/15: 2; Wed 4/16: 3; Thu 4/17: 6
| MISC | [7 empty] | MISC |  |  |  | 1 | bar: Tue 4/15 to Fri 4/18