## Sheet1 (2)
ANDONA1:W50 | PartStatus | Ncr | Comment | End Item | Job Status | WBS | ACC | Pos | Team | WorkPackageId | Work Type | Reason | Gate | Plan Start Date | Plan Complete Date | Top Order | Order Id | Plan Description | Plan Id | Disposition Text | Budget | BCWP | Actual | BCWS | CV | CPI | SPI | % Comp. | EAC | ETC | Act. Start | Act. Finish
| B | 2 |  | 2 | STARTED |  | 301 | P4H | 915 |  | DEPOT |  |  | 2022-09-02 | 2022-09-12 | [5 empty] | 8 | 4 | 16.5 | 8 | -12.5 | 0.2 | 0.5 | 50 | 20.5 | 4 | 2022-08-27 06:34
| B | 1 |  | 2 | SCHEDULED |  | 951 | GL | 915 |  | DEPOT |  | FCF | 2025-07-25 | 2025-08-01
| G | 1 |  | 2 | NOT STARTED |  | VC601 | PZH1 | 601¦TAILCONE |  | DEPOT | HF OTHER BHS | Wires Ready | 2024-08-13 | 2024-08-20 | [5 empty] | 83.4 |  |  | 83.4 |  |  |  |  | 83.4 | 83.4
| B | 1 |  | 2 | STARTED |  | 050 | 2L | 000 ¦ MAINT-HMX |  | DEPOT |  |  | 2024-06-26 | 2024-06-27 | [5 empty] | 7 | 4.9 | 2.1 | 7 | 2.8 | 2.3 | 0.7 | 70 | 4.2 | 2.1 | 2024-06-21 08:36
| G | 1 |  | 2 | SCHEDULED |  | 551 | DF | 915 |  | DEPOT |  | FCF | 2025-08-05 | 2025-08-12 | [5 empty] | 16 | [7 empty] | 16 | 16
| Y | 2 |  | 2 | SCHEDULED |  | 551 | DF | 915 |  | DEPOT |  | FCF | 2025-08-12 | 2025-08-19 | [5 empty] | 16 | [7 empty] | 16 | 16
| Y | 1 |  | 2 | SCHEDULED |  | 551 | DF | 915 |  | DEPOT |  | FCF | 2025-07-24 | 2025-07-31 | [5 empty] | 16 | [7 empty] | 16 | 16
| B | 3 |  | 2 | STARTED |  | 851 | F6 | 851¦48 SECTION |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-02-11 | 2025-03-27 | [5 empty] | 311.8 | 145.5 | 28.5 | 311.8 | 117 | 5.1 | 0.5 | 46.7 | 194.8 | 166.3 | 2020-05-26 14:33
| B | 1 |  | 2 | STARTED |  | 851 | F6 | 851¦48 SECTION |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-02-11 | 2025-03-26 | [5 empty] | 305.3 | 305.3 | 14.8 | 305.3 | 290.4 | 20.6 | 1 | 100 | 14.8 |  | 2020-05-04 09:10
2 | B | 1 |  | 2 | STARTED |  | 851 | F6 | 851¦48 SECTION |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-02-11 | 2025-03-26 | [5 empty] | 378.7 | 174.8 | 50.9 | 378.7 | 123.9 | 3.4 | 0.5 | 46.2 | 254.8 | 203.9 | 2020-06-12 07:53
| B | 1 |  | 2 | STARTED |  | 601 | F6 | 601¦TAILCONE |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-05-08 | 2025-05-28 | [5 empty] | 1247.9 | 998.3 | 421.6 |  | 576.7 | 2.4 |  | 80 | 671.2 | 249.6 | 2021-01-25 06:01
| B | 1 |  | 2 | STARTED |  | 851 | F6 | 851¦GFE |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-03-03 | 2025-05-06 | [5 empty] | 222.2 |  | 18.7 | 119.6 | -18.7 |  |  |  | 240.9 | 222.2 | 2023-05-17 15:44
| Y | 1 |  | 2 | NOT STARTED |  | 451 | 45 | 915 |  | DEPOT |  | Power On | 2024-11-19 | 2024-11-26 | [5 empty] | 16 |  |  | 16 |  |  |  |  | 16 | 16
| B | 5 |  | 2 | STARTED |  | 050 | 2 | 000¦MAINT |  | DEPOT |  |  | 2020-10-09 | 2020-10-09 | [5 empty] | 8 | 8 | 35.5 | 8 | -27.5 | 0.2 | 1 | 100 | 35.5 |  | 2021-01-09 05:47
| B | 4 |  | 2 | STARTED |  | 851 | EH | 951 ¦ STR-GAC |  | DEPOT |  |  | 2024-09-24 | 2024-09-25 | [5 empty] | 7 | 3.9 | 25.3 | 7 | -21.4 | 0.2 | 0.6 | 55.6 | 28.4 | 3.1 | 2024-07-24 04:47
| G | 1 |  | 2 | STARTED |  | 251 | F0 | 251¦FLOOR DRILL |  | DEPOT |  | Wires Ready | 2025-06-04 | 2025-06-24 | [5 empty] | 213 | 121.7 | 89 |  | 32.7 | 1.4 |  | 57.1 | 180.3 | 91.3 | 2023-02-10 05:05
| B | 2 |  | 2 | STARTED |  | 251 | F0 | 251¦FLOOR DRILL |  | DEPOT |  | Wires Ready | 2025-10-30 | 2025-11-10 | [5 empty] | 203.2 | 203.2 | 131.1 |  | 72.1 | 1.5 |  | 100 | 131.1 |  | 2023-02-21 06:04
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-03-06 | 2024-03-12 | [5 empty] | 1 | 0.4 | 0.7 | 1 | -0.3 | 0.5 | 0.4 | 37.5 | 1.3 | 0.6 | 2024-04-30 08:54
1 | B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MAINT |  | DEPOT |  |  | 2022-02-28 | 2022-02-28 | [5 empty] | 33 | 33 | 43.7 | 33 | -10.7 | 0.8 | 1 | 100 | 43.7 |  | 2022-03-03 11:42
| B | 7 |  | 2 | STARTED |  | 101 | 4E | 915 |  | DEPOT |  | Enter Gate | 2022-03-24 | 2022-03-25 | [5 empty] | 16 | 12 |  | 16 | 12 |  | 0.8 | 75 | 4 | 4 | 2022-03-25 12:53 | 2022-03-28 12:53
| R | 1 |  | 2 | NOT STARTED |  | 201 | 4P | 201¦BLANKETS |  | DEPOT | HF PARTS | Wires Ready | 2024-08-14 | 2024-08-15 | [5 empty] | 7.9 |  |  | 7.9 |  |  |  |  | 7.9 | 7.9
| R | 1 |  | 2 | SCHEDULED |  | 201 | 24 | 915 |  | DEPOT |  | Post FCF | 2026-03-30 | 2026-04-06
| G | 1 |  | 2 | SCHEDULED |  | 201 | DH | 915 |  | DEPOT |  | FCF | 2025-07-23 | 2025-07-30 | [5 empty] | 16 | [7 empty] | 16 | 16
| B | 3 |  | 2 | STARTED |  | 551 | DF | 000¦MAINT |  | DEPOT |  |  | 2023-03-15 | 2023-03-15 | [5 empty] | 16 | 14.4 | 35 | 16 | -20.6 | 0.4 | 0.9 | 90 | 36.6 | 1.6 | 2023-03-16 12:54
| B | 53 |  | 2 | STARTED |  | 050 | 28 | 000¦COLLECTOR |  | DEPOT | HF OTHER BHS |  | 2020-01-20 | 2021-06-30 | [12 empty] | 100 |  |  | 2022-12-20 14:54 | 2022-12-20 14:54
| Y | 1 |  | 2 | STARTED |  | 401 | 3A | 401¦STRUCTURES |  | DEPOT |  | Power On | 2024-11-06 | 2024-11-13 | [5 empty] | 16 |  | 1 | 16 | -1 |  |  |  | 17 | 16 | 2023-01-12 08:40
| B | 1 |  | 2 | STARTED |  | 050 | 8 | 000¦TASK END |  | DEPOT |  | Enter Gate | 2019-10-01 | 2024-04-01 | [15 empty] | 2019-10-01 09:22
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MAINT |  | DEPOT |  |  | 2020-07-14 | 2020-07-14 | [5 empty] | 24 | 16 | 47.1 | 24 | -31.1 | 0.3 | 0.7 | 66.7 | 55.1 | 8 | 2020-07-14 09:10
| B | 1 |  | 2 | NOT STARTED |  | 151 | F8 | 651¦OSWO |  | DEPOT |  | Wires Ready | 2025-04-16 | 2025-04-17 | [5 empty] | 2 | [7 empty] | 2 | 2
| Y | 1 |  | 2 | SCHEDULED |  | 351 | DB | 351¦FIRE SUPPRESSION |  | DEPOT | HF PARTS | FCF | 2025-08-04 | 2025-08-11 | [5 empty] | 16 | [7 empty] | 16 | 16
2 | B | 5 |  | 2 | STARTED |  | 251 | F6 | 251¦FLOOR MOD |  | DEPOT | HF PARTS | Wires Ready | 2025-10-02 | 2025-10-20 | [5 empty] | 4038.7 | 4038.7 | 135.1 |  | 3903.6 | 29.9 |  | 100 | 135.1 |  | 2022-10-13 09:29
| B | 1 |  | 2 | NOT STARTED |  | VC351 | PZD3 | 351¦OSWO |  | DEPOT |  | Wires Ready | 2024-03-05 | 2024-03-07 | [5 empty] | 426.1 |  |  | 426.1 |  |  |  |  | 426.1 | 426.1
| B | 3 |  | 2 | STARTED |  | 301 | 4H | 951¦STRINGER INSP |  | DEPOT | [11 empty] | 66.1 |  | -66.1 |  |  | 50 | 66.1 |  | 2022-08-23 05:56
| B | 3 |  | 2 | STARTED |  | 050 | 2 | 000¦MAINT |  | DEPOT |  |  | 2020-11-13 | 2020-11-13 | [5 empty] | 8 | 8 | 6.5 | 8 | 1.5 | 1.2 | 1 | 100 | 6.5 |  | 2020-11-13 09:22
| B | 4 |  | 2 | NOT STARTED |  | 251 | 4W | C FWD |  | DEPOT
| B | 9 |  | 2 | NOT STARTED |  | 101 | 4S | C FWD |  | DEPOT
| B | 5 |  | 2 | NOT STARTED |  | 151 | 4R | C FWD |  | DEPOT |  |  | 2023-01-11 | 2023-01-15
| B | 1 |  | 2 | NOT STARTED |  | 401 | 4U | C FWD |  | DEPOT
| B | 1 |  | 2 | NOT STARTED |  | 301 | 4V | C FWD |  | DEPOT
| B | 1 |  | 2 | STARTED |  | 401 | F6 | 401¦FLOOR DRILL |  | DEPOT |  | Wires Ready | 2025-02-10 | 2025-03-04 | [5 empty] | 130.2 | 45.6 | 26 | 130.2 | 19.6 | 1.8 | 0.3 | 35 | 110.6 | 84.6 | 2024-12-16 06:08
| B | 1 |  | 2 | STARTED |  | 351 | F6 | 351¦BRACKETS |  | DEPOT |  | Wires Ready | 2025-02-26 | 2025-03-05 | [5 empty] | 249.6 | 115.2 | 80.1 | 249.6 | 35.1 | 1.4 | 0.5 | 46.2 | 214.5 | 134.4 | 2024-02-22 05:36
| G | 1 |  | 2 | SCHEDULED |  | 551 | DF | 915 |  | DEPOT |  | FCF | 2025-07-24 | 2025-07-31 | [5 empty] | 16 | [7 empty] | 16 | 16
| B | 1 |  | 2 | STARTED |  | 601 | F6 | 601¦OSWO |  | DEPOT |  | Wires Ready | 2025-03-04 | 2025-04-22 | [5 empty] | 137 | 82.2 | 29.8 | 93.1 | 52.4 | 2.8 | 0.9 | 60 | 84.6 | 54.8 | 2024-02-26 05:01
| G | 1 |  | 2 | NOT STARTED |  | 151 | F6 | 301¦PROVISIONS |  | DEPOT |  | Wires Ready | 2025-09-18 | 2025-09-29 | [5 empty] | 55.7 | [7 empty] | 55.7 | 55.7
| B | 1 |  | 2 | NOT STARTED |  | 601 | F7 | 601¦OSWO |  | DEPOT |  |  | 2025-05-13 | 2025-05-19 | [5 empty] | 140.8 | [7 empty] | 140.8 | 140.8
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MAINT |  | DEPOT |  |  | 2022-08-05 | 2022-08-05 | [5 empty] | 6 |  | 19.9 | 6 | -19.9 |  |  |  | 25.9 | 6 | 2022-08-06 04:54
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-05-02 | 2024-05-09 | [5 empty] | 1 | 0.4 | 1.2 | 1 | -0.8 | 0.3 | 0.4 | 37.5 | 1.8 | 0.6 | 2024-05-10 12:19
| B | 1 |  | 2 | NOT STARTED |  | 601 | F8 | 601¦TAILCONE |  | DEPOT |  | Wires Ready | 2025-06-02 | 2025-06-05 | [5 empty] | 47.7 | [7 empty] | 47.7 | 47.7
| Y | 2 |  | 2 | STARTED |  | 251 | F6 | 251¦INT STRUCTURES |  | DEPOT | HF PARTS | Wires Ready | 2025-02-10 | 2025-02-18 | [5 empty] | 512.3 | 245 | 141.8 | 512.3 | 103.2 | 1.7 | 0.5 | 47.8 | 409.1 | 267.3 | 2024-06-11 13:28
| B | 1 |  | 2 | STARTED |  | 151 | F0 | 151¦PROVISIONS |  | DEPOT |  | Wires Ready | 2025-04-24 | 2025-05-13 | [5 empty] | 130.9 | 93.5 | 28.4 |  | 65.1 | 3.3 |  | 71.4 | 65.8 | 37.4 | 2023-09-25 06:54
| B | 1 |  | 2 | NOT STARTED |  | 101 | F8 | 101¦OSWO |  | DEPOT |  | Wires Ready | 2025-10-29 | 2025-10-29 | [5 empty] | 4.8 | [7 empty] | 4.8 | 4.8
| B | 4 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-04-16 | 2024-04-23 | [5 empty] | 1 | 0.6 | 6.4 | 1 | -5.8 | 0.1 | 0.6 | 62.5 | 6.8 | 0.4 | 2024-05-02 05:17
| B | 1 |  | 2 | STARTED |  | 401 | F6 | 401¦LL AFT |  | DEPOT | WORKABLE | Decrib | 2025-01-27 | 2025-02-26 | [5 empty] | 48 | 46.2 | 235.5 | 48 | -189.3 | 0.2 | 1 | 96.2 | 237.3 | 1.8 | 2020-09-28 05:19 | 2020-10-30 11:30
3 | B | 5 |  | 2 | STARTED |  | 401 | F6 | 401¦STRUCTURES |  | DEPOT | HF ME | Wires Ready | 2025-06-25 | 2025-07-10 | [5 empty] | 1152.3 | 1047.5 | 100.6 |  | 946.9 | 10.4 |  | 90.9 | 205.4 | 104.8 | 2022-07-21 07:15
| B | 1 |  | 2 | SCHEDULED |  | 201 | 16 | 201¦WINDOWS |  | DEPOT | WORKABLE | FCF | 2025-07-31 | 2025-08-07 | [5 empty] | 16 | 8 | 57.6 |  | -49.6 | 0.1 |  | 50 | 65.6 | 8 | 2021-03-08 06:11
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-02-22 | 2024-02-29 | [5 empty] | 1 | 0.8 | 1 | 1 | -0.3 | 0.8 | 0.8 | 75 | 1.3 | 0.3 | 2024-02-22 11:46
| B | 3 |  | 2 | NOT STARTED |  | 351 | F6 | 915 |  | DEPOT |  | Wires Ready | 2025-03-05 | 2025-03-11 | [5 empty] | 1657.8 |  |  | 1657.8 |  |  |  |  | 1657.8 | 1657.8
| B | 1 |  | 2 | NOT STARTED |  | VC351 | PZD4 |  |  | DEPOT |  | Power On | 2024-09-05 | 2024-09-12
| B | 1 |  | 2 | NOT STARTED |  | 851 | F6 | 851¦TAILCONE |  | DEPOT |  |  | 2025-01-29 | 2025-02-05 | [5 empty] | 136.8 | 136.8 |  | 136.8 | 136.8 |  | 1 | 100
| G | 1 |  | 2 | NOT STARTED |  | 401 | 72 | 401¦PROVISIONS |  | DEPOT |  | Power On | 2025-01-29 | 2025-02-12 | [5 empty] | 47.6 |  |  | 47.6 |  |  |  |  | 47.6 | 47.6
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-02-02 | 2024-02-05 | [5 empty] | 1 | 0.8 | 14.6 | 1 | -13.8 | 0.1 | 0.8 | 75 | 14.8 | 0.3 | 2024-02-12 12:12
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-03-04 | 2024-03-08 | [5 empty] | 1 | 0.8 | 0.4 | 1 | 0.3 | 1.9 | 0.8 | 75 | 0.7 | 0.3 | 2024-04-03 09:54
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-02-02 | 2024-02-05 | [5 empty] | 1 | 0.6 | 21.8 | 1 | -21.2 |  | 0.6 | 62.5 | 22.2 | 0.4 | 2024-02-12 12:36
| B | 1 |  | 2 | STARTED |  | 401 | XM | 401¦STRUCTURES |  | DEPOT | HF OTHER BHS | Power On | 2024-12-04 | 2024-12-11 | [5 empty] | 45 | 9 | 14.4 | 45 | -5.4 | 0.6 | 0.2 | 20 | 50.4 | 36 | 2022-03-18 07:06
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-02-02 | 2024-02-05 | [5 empty] | 1 | 0.8 | 3 | 1 | -2.3 | 0.3 | 0.8 | 75 | 3.3 | 0.3 | 2024-02-06 09:48
| B | 2 |  | 2 | NOT STARTED |  | 050 | 28 | 000¦COLLECTOR |  | DEPOT | HF OTHER BHS |  | 2020-03-02 | 2020-10-01 | [12 empty] | 100 |  |  |  | 2022-11-18 07:14
| B | 1 |  | 2 | NOT STARTED |  | 351 | F6 | 351¦OSWO |  | DEPOT |  | Wires Ready | 2025-07-28 | 2025-07-30 | [5 empty] | 91.4 | [7 empty] | 91.4 | 91.4
| Y | 1 |  | 2 | SCHEDULED |  | 551 | DF | 915 |  | DEPOT |  | FCF | 2025-07-29 | 2025-08-05 | [5 empty] | 16 | [7 empty] | 16 | 16
| B | 2 |  | 2 | STARTED |  | 351 | F6 | 351¦OSWO |  | DEPOT |  | Wires Ready | 2025-02-27 | 2025-03-06 | [5 empty] | 840.8 | 420.4 | 8.7 | 840.8 | 411.7 | 48.3 | 0.5 | 50 | 429.1 | 420.4 | 2024-04-02 08:21
| B | 1 |  | 2 | STARTED |  | 251 | F0 | 251¦INT STRUCTURES |  | DEPOT |  | Wires Ready | 2025-10-15 | 2025-10-21 | [5 empty] | 29.1 | 7.7 | 12.7 |  | -5 | 0.6 |  | 26.7 | 34 | 21.3 | 2024-12-06 05:35
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-03-18 | 2024-03-25 | [5 empty] | 1 | 0.4 | 0.4 | 1 |  | 0.9 | 0.4 | 37.5 | 1 | 0.6 | 2024-04-16 11:55
| B | 2 |  | 2 | STARTED |  | 551 | F7 | 551¦WINGS |  | DEPOT |  | Wires Ready | 2025-01-30 | 2025-02-12 | [5 empty] | 243.2 | 157.4 | 56.8 | 243.2 | 100.6 | 2.8 | 0.6 | 64.7 | 142.6 | 85.8 | 2023-04-05 07:41
| B | 6 |  | 2 | NOT STARTED |  | VC351 | PZA1 | 351¦VERIFICATION |  | DEPOT |  | Wires Ready | 2024-02-15 | 2024-02-19 | [5 empty] | 809.5 |  |  | 809.5 |  |  |  |  | 809.5 | 809.5
| B | 1 |  | 2 | STARTED |  | 050 | 2L | 000 ¦ MAINT-HMX |  | DEPOT |  |  | 2024-06-27 | 2024-06-28 | [5 empty] | 7 | 4.7 | 0.1 | 7 | 4.6 | 46.7 | 0.7 | 66.7 | 2.4 | 2.3 | 2024-06-26 09:44
| B | 4 |  | 2 | NOT STARTED |  | 050 | 28 | 000¦COLLECTOR |  | DEPOT
| B | 2 |  | 2 | STARTED |  | 050 | 7 | 551¦ENGINE MODS |  | DEPOT |  |  | 2023-10-11 | 2023-10-18 | [5 empty] | 16 | 16 | 35.5 | 16 | -19.5 | 0.5 | 1 | 100 | 35.5 |  | 2023-10-20 07:58
| B | 2 |  | 2 | NOT STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-04-29 | 2024-05-03 | [5 empty] | 1 |  |  | 1 |  |  |  |  | 1 | 1
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-02-22 | 2024-02-29 | [5 empty] | 1 | 0.6 | 1 | 1 | -0.4 | 0.6 | 0.6 | 62.5 | 1.4 | 0.4 | 2024-03-15 09:58
| B | 1 |  | 2 | STARTED |  | 601 | F8 | 601¦TAILCONE |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-06-10 | 2025-06-23 | [5 empty] | 319.4 | 228.2 | 5.6 |  | 222.6 | 40.7 |  | 71.4 | 96.9 | 91.3 | 2023-07-13 12:48
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-02-22 | 2024-02-29 | [5 empty] | 1 | 0.8 | 1.5 | 1 | -0.8 | 0.5 | 0.8 | 75 | 1.8 | 0.3 | 2024-03-15 09:44
1 | G | 1 |  | 2 | STARTED |  | 351 | AA | 351¦PROVISIONS |  | DEPOT |  | Power On | 2024-09-13 | 2024-09-20 | [5 empty] | 44.1 | 9.2 | 25.8 | 44.1 | -16.6 | 0.4 | 0.2 | 20.8 | 60.7 | 34.9 | 2022-09-08 05:57
| B | 1 |  | 2 | UNOPENED |  | 050 | 28 | 915 |  | DEPOT
1 | B | 3 |  | 2 | STARTED |  | 351 | F6 | 351¦STRUCTURES |  | DEPOT |  | Wires Ready | 2025-03-26 | 2025-04-03 | [5 empty] | 355.8 | 213.5 | 48.8 | 355.8 | 164.7 | 4.4 | 0.6 | 60 | 191.1 | 142.3 | 2023-11-13 14:55
| B | 2 |  | 2 | STARTED |  | 401 | F6 | 401¦OSWO |  | DEPOT |  | Wires Ready | 2025-02-06 | 2025-03-11 | [5 empty] | 332.9 | 258.9 | 93.8 | 332.9 | 165.1 | 2.8 | 0.8 | 77.8 | 167.8 | 74 | 2024-09-21 07:39
| B | 1 |  | 2 | NOT STARTED |  | 851 | F6 | 915 |  | DEPOT |  | Wires Ready | 2025-02-26 | 2025-03-05 | [5 empty] | 159.8 |  |  | 159.8 |  |  |  |  | 159.8 | 159.8
| B | 1 |  | 2 | SCHEDULED |  | 951 | GM | 915 |  | DEPOT |  | FCF | 2025-07-28 | 2025-08-04
| Y | 1 |  | 2 | STARTED |  | 351 | F7 | 351¦FLOORS |  | DEPOT |  | Wires Ready | 2025-04-23 | 2025-05-01 | [5 empty] | 47.2 | 20.6 | 79.3 |  | -58.7 | 0.3 |  | 43.8 | 105.8 | 26.5 | 2023-02-21 21:15
| Y | 1 |  | 2 | NOT STARTED |  | 351 | 12 | 915 |  | DEPOT |  | Hiblo | 2025-03-19 | 2025-03-26
1 | B | 1 |  | 2 | STARTED |  | 401 | F8 | 401¦STRUCTURES |  | DEPOT | WORKABLE | Wires Ready | 2025-06-18 | 2025-07-09 | [5 empty] | 615 | 361.8 | 137.1 |  | 224.7 | 2.6 |  | 58.8 | 390.3 | 253.2 | 2021-01-23 08:18
| Y | 4 |  | 2 | STARTED |  | 251 | F9 | 251¦INT STRUCTURES |  | DEPOT | HF PARTS | Wires Ready | 2025-02-05 | 2025-02-27 | [5 empty] | 237.9 | 69.4 | 42.9 | 237.9 | 26.5 | 1.6 | 0.3 | 29.2 | 211.4 | 168.5 | 2024-06-04 09:06
| B | 1 |  | 2 | STARTED |  | 601 | F7 | 601¦TAILCONE |  | DEPOT | HF PARTS | Wires Ready | 2025-08-18 | 2025-08-26 | [5 empty] | 251.8 | 132.6 | 183.2 |  | -50.6 | 0.7 |  | 52.6 | 302.5 | 119.3 | 2022-05-02 09:12
| Y | 1 |  | 2 | STARTED |  | 151 | F7 | 201¦PROVISIONS |  | DEPOT |  | Wires Ready | 2025-06-19 | 2025-06-23 | [5 empty] | 124.5 | 83 | 29.8 |  | 53.2 | 2.8 |  | 66.7 | 71.3 | 41.5 | 2022-05-13 09:44
| B | 1 |  | 2 | NOT STARTED |  | 251 | XH | 251¦OSWO |  | DEPOT |  |  | 2025-08-26 | 2025-09-02 | [5 empty] | 33 | [7 empty] | 33 | 33
| R | 1 |  | 2 | STARTED |  | 551 | 14 | 701¦FLIGHT TEST |  | DEPOT | WORKABLE | HiBlo | 2025-03-11 | 2025-03-18 | [5 empty] | 16 | 3.6 | 27.8 | 16 | -24.2 | 0.1 | 0.2 | 22.2 | 40.2 | 12.4 | 2020-10-26 05:31
| B | 1 |  | 2 | NOT STARTED |  | 601 | F8 | 601¦TAILCONE |  | DEPOT |  | Wires Ready | 2025-05-14 | 2025-05-20 | [5 empty] | 71.5 | [7 empty] | 71.5 | 71.5
| B | 3 |  | 2 | STARTED |  | 601 | F6 | 601¦TAILCONE |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-03-12 | 2025-03-19 | [5 empty] | 305.4 | 122.1 | 65.7 | 305.4 | 56.4 | 1.9 | 0.4 | 40 | 248.9 | 183.2 | 2023-11-14 08:07
| B | 1 |  | 2 | STARTED |  | VC601 | PZH1 | 601¦GFE LOWER SHELF |  | DEPOT | HF OTHER BHS | Wires Ready | 2024-07-23 | 2024-07-30 | [5 empty] | 122.3 | 43.7 | 44.6 | 122.3 | -0.9 | 1 | 0.4 | 35.7 | 123.2 | 78.6 | 2021-12-16 11:27
| B | 2 |  | 2 | STARTED |  | 151 | F8 | 651¦OSWO |  | DEPOT |  | Wires Ready | 2025-04-16 | 2025-04-16 | [5 empty] | 4.4 | 3.3 | 70.1 |  | -66.8 |  |  | 75 | 71.2 | 1.1 | 2024-05-01 07:12
| B | 2 |  | 2 | STARTED |  | 151 | F7 | 251¦INT STRUCTURES |  | DEPOT |  | Wires Ready | 2025-11-10 | 2025-11-13 | [5 empty] | 48.5 | 32.4 | 21.2 |  | 11.2 | 1.5 |  | 66.7 | 37.4 | 16.2 | 2023-08-24 05:11
| B | 6 |  | 2 | STARTED |  | 151 | F6 | 151¦STRUCTURES |  | DEPOT | WORKABLE | Wires Ready | 2025-02-10 | 2025-02-26 | [5 empty] | 783.3 | 510.9 | 83.5 | 783.3 | 427.4 | 6.1 | 0.7 | 65.2 | 356 | 272.5 | 2020-05-04 05:50
| B | 2 |  | 2 | STARTED |  | 601 | 72 | 601¦TAILCONE |  | DEPOT |  | Wires Ready | 2026-02-12 | 2026-02-17 | [5 empty] | 300.7 | 233.9 | 13 |  | 220.9 | 18 |  | 77.8 | 79.8 | 66.8 | 2021-05-13 10:17
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MAINT |  | DEPOT |  |  | 2023-03-24 | 2023-03-24 | [5 empty] | 60 | 60 | 13.5 | 60 | 46.5 | 4.4 | 1 | 100 | 13.5 |  | 2023-03-24 05:41
| B | 1 |  | 2 | STARTED |  | 151 | F9 | 251¦OSWO |  | DEPOT |  |  | 2025-11-20 | 2025-11-26 | [5 empty] | 1 | 0.5 | 8.9 |  | -8.4 | 0.1 |  | 50 | 9.4 | 0.5 | 2024-09-06 10:31
| B | 1 |  | 2 | STARTED |  | 151 | F8 | 915 |  | DEPOT |  |  | 2025-07-29 | 2025-07-31 | [7 empty] | 4.7 |  | -4.7 |  |  | 100 | 4.7 |  | 2025-01-23 10:18
| B | 1 |  | 2 | STARTED |  | 401 | F0 | 401¦STRUCTURES |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-10-02 | 2025-10-08 | [5 empty] | 650 | 650 | 81.4 |  | 568.6 | 8 |  | 100 | 81.4 |  | 2021-03-18 13:52
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-04-16 | 2024-04-23 | [5 empty] | 1 | 0.4 | 10 | 1 | -9.6 |  | 0.4 | 37.5 | 10.6 | 0.6 | 2024-04-25 05:14
| Y | 1 |  | 2 | NOT STARTED |  | 101 | F9 | 101¦WINDOWS |  | DEPOT | HF PARTS | Wires Ready | 2025-02-04 | 2025-02-12 | [5 empty] | 179.3 |  |  | 179.3 |  |  |  |  | 179.3 | 179.3
| B | 1 |  | 2 | STARTED |  | 851 | EH | 000¦SERVICE BULLETIN |  | DEPOT |  |  | 2024-09-13 | 2024-09-16 | [5 empty] | 7 | 5.4 | 17.4 | 7 | -12 | 0.3 | 0.8 | 77.8 | 19 | 1.6 | 2024-07-08 12:01
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MAINT |  | DEPOT |  |  | 2024-07-22 | 2024-07-22 | [5 empty] | 1 | 1 | 1.9 | 1 | -0.9 | 0.5 | 1 | 100 | 1.9 |  | 2024-07-22 05:47
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MAINT |  | DEPOT |  |  | 2024-06-13 | 2024-06-13 | [5 empty] | 1 | 1 | 1 | 1 |  | 1 | 1 | 100 | 1 |  | 2024-06-13 06:46 | 2024-06-13 12:59
1 | B | 2 |  | 2 | STARTED |  | VC451 | PSH | 000¦SERVICE BULLETIN |  | DEPOT |  |  | 2023-02-03 | 2024-06-10 | [5 empty] | 135 | 23.8 | 191.1 | 135 | -167.3 | 0.1 | 0.2 | 17.6 | 302.3 | 111.2 | 2024-03-19 08:11
| G | 1 |  | 2 | STARTED |  | 601 | F5 | 601¦TAILCONE |  | DEPOT | HF OTHER BHS | FCF | 2025-08-04 | 2025-08-11 | [5 empty] | 47.5 | 15.8 | 41.7 |  | -25.9 | 0.4 |  | 33.3 | 73.4 | 31.7 | 2022-10-04 06:20
| B | 1 |  | 2 | NOT STARTED |  | 151 | W2 | 915 |  | DEPOT
3 | B | 1 |  | 2 | STARTED |  | 401 | F6 | 401¦STRUCTURES |  | DEPOT | HF ENG | Wires Ready | 2025-03-17 | 2025-03-19 | [5 empty] | 45 | 45 | 8 | 45 | 37 | 5.6 | 1 | 100 | 8 |  | 2021-06-02 10:55 | 2023-11-13 09:32
| B | 6 |  | 2 | NOT STARTED |  | 951 | AD | 951¦GFE CRIBBING |  | DEPOT |  | Wires Ready | 2024-07-23 | 2024-08-01 | [5 empty] | 643.9 |  |  | 643.9 |  |  |  |  | 643.9 | 643.9
| B | 2 |  | 2 | NOT STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-04-25 | 2024-04-30 | [5 empty] | 1 |  |  | 1 |  |  |  |  | 1 | 1
| R | 1 |  | 2 | NOT STARTED |  | 050 | 2 | 551¦ENGINE MODS |  | DEPOT |  |  | 2025-10-29 | 2025-10-30 | [5 empty] | 33 | [7 empty] | 33 | 33
| B | 2 |  | 2 | NOT STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-04-25 | 2024-04-30 | [5 empty] | 1 |  |  | 1 |  |  |  |  | 1 | 1
| B | 1 |  | 2 | NOT STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-03-18 | 2024-03-25 | [5 empty] | 1 | 0.4 |  | 1 | 0.4 |  | 0.4 | 37.5 | 0.6 | 0.6
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-02-22 | 2024-02-29 | [5 empty] | 1 | 0.6 | 0.5 | 1 | 0.1 | 1.3 | 0.6 | 62.5 | 0.9 | 0.4 | 2024-03-18 06:29
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-03-18 | 2024-03-25 | [5 empty] | 1 | 0.6 | 1.7 | 1 | -1.1 | 0.4 | 0.6 | 62.5 | 2.1 | 0.4 | 2024-04-30 09:36
| B | 2 |  | 2 | NOT STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-04-26 | 2024-04-30 | [5 empty] | 1 |  |  | 1 |  |  |  |  | 1 | 1
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-02-26 | 2024-03-01 | [5 empty] | 1 | 0.8 | 1 | 1 | -0.3 | 0.8 | 0.8 | 75 | 1.3 | 0.3 | 2024-03-04 13:08
| B | 2 |  | 2 | NOT STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-04-26 | 2024-04-30 | [5 empty] | 1 |  |  | 1 |  |  |  |  | 1 | 1
| B | 1 |  | 2 | NOT STARTED |  | 301 | 71 | 301¦OSWO |  | DEPOT |  |  | 2025-11-10 | 2025-11-10 | [5 empty] | 0.9 | [7 empty] | 0.9 | 0.9
| B | 2 |  | 2 | NOT STARTED |  | 351 | F6 | 351¦OSWO |  | DEPOT |  | Wires Ready | 2025-02-25 | 2025-04-23 | [5 empty] | 82.3 |  |  | 58.2 |  |  |  |  | 82.3 | 82.3
| B | 1 |  | 2 | NOT STARTED |  | 151 | XC | 151¦OSWO |  | DEPOT |  |  | 2025-11-25 | 2025-12-08 | [5 empty] | 4.4 | [7 empty] | 4.4 | 4.4
| B | 1 |  | 2 | NOT STARTED |  | 901 | WH | 901¦BENCH WORK |  | DEPOT |  | Wires Ready | 2024-09-17 | 2024-09-19 | [5 empty] | 51.1 |  |  | 51.1 |  |  |  |  | 51.1 | 51.1
1 | Y | 1 |  | 2 | STARTED |  | 401 | F9 | 401¦FLOOR DRILL |  | DEPOT |  | Wires Ready | 2025-08-04 | 2025-08-18 | [5 empty] | 78 | 28.7 | 54.2 |  | -25.5 | 0.5 |  | 36.8 | 103.4 | 49.2 | 2024-11-05 06:10
| Y | 1 |  | 2 | STARTED |  | 401 | F9 | 401¦FLOOR DRILL |  | DEPOT |  | Wires Ready | 2025-08-04 | 2025-08-18 | [5 empty] | 78 | 34.6 | 80.5 |  | -45.9 | 0.4 |  | 44.4 | 123.8 | 43.3 | 2024-11-19 13:50
| B | 1 |  | 2 | NOT STARTED |  | 401 | F9 | 401¦OSWO |  | DEPOT |  | Wires Ready | 2025-07-08 | 2025-07-22 | [5 empty] | 146.3 | [7 empty] | 146.3 | 146.3
1 | B | 2 |  | 2 | STARTED |  | 351 | F9 | 351¦PROVISIONS |  | DEPOT |  | Wires Ready | 2025-09-17 | 2025-09-24 | [5 empty] | 313.4 | 313.4 | 150.3 |  | 163.1 | 2.1 |  | 100 | 150.3 |  | 2022-04-01 16:18
| B | 1 |  | 2 | STARTED |  | 201 | 72 | 201¦FLOORS |  | DEPOT |  | Wires Ready | 2025-06-16 | 2025-06-18 | [5 empty] | 35.1 | 35.1 | 172.4 |  | -137.3 | 0.2 |  | 100 | 172.4 |  | 2022-08-12 15:11
| B | 2 |  | 2 | STARTED |  | 201 | 72 | 201¦FLOORS |  | DEPOT |  | Wires Ready | 2025-05-14 | 2025-05-28 | [5 empty] | 28.1 | 15.1 | 95.3 |  | -80.2 | 0.2 |  | 53.8 | 108.3 | 13 | 2022-08-11 20:26
| G | 2 |  | 2 | STARTED |  | 251 | 74 | 251¦FLOOR DRILL |  | DEPOT |  | Wires Ready | 2025-07-07 | 2025-07-22 | [5 empty] | 184.1 | 99.1 | 45 |  | 54.1 | 2.2 |  | 53.8 | 129.9 | 84.9 | 2023-04-10 06:40
| B | 1 |  | 2 | UNOPENED |  | 351 | 3A | 915 |  | DEPOT |  | Hiblo | 2022-01-05 | 2022-01-07
1 | B | 1 |  | 2 | STARTED |  | 401 | XM | 401¦STRUCTURES |  | DEPOT | HF OTHER BHS | Power On | 2024-11-27 | 2024-12-04 | [5 empty] | 45 | 15 | 54.8 | 45 | -39.8 | 0.3 | 0.3 | 33.3 | 84.8 | 30 | 2021-05-13 22:46
| B | 1 |  | 2 | NOT STARTED |  | 251 | F6 | 251¦VERIFICATION |  | DEPOT |  |  | 2025-02-05 | 2025-03-10 | [5 empty] | 389.9 | 167.1 |  | 389.9 | 167.1 |  | 0.8 | 42.9 | 222.8 | 222.8
| G | 1 |  | 2 | SCHEDULED |  | 351 | DB | 351¦FIRE SUPPRESSION |  | DEPOT | HF PARTS | FCF | 2025-08-01 | 2025-08-08 | [5 empty] | 16 | [7 empty] | 16 | 16
2 | G | 1 |  | 2 | STARTED |  | 401 | XM | 401¦STRUCTURES |  | DEPOT | HF OTHER BHS | Power On | 2024-12-02 | 2024-12-09 | [5 empty] | 26.1 | 12 | 85 | 26.1 | -73 | 0.1 | 0.5 | 46.2 | 99 | 14 | 2021-06-22 09:17
| B | 10 |  | 2 | NOT STARTED |  | 201 | F7 | 201¦OSWO |  | DEPOT |  | Wires Ready | 2025-03-06 | 2025-03-20 | [5 empty] | 56.1 |  |  | 56.1 |  |  |  |  | 56.1 | 56.1
1 | B | 2 |  | 2 | STARTED |  | 251 | F6 | 251¦FLOOR MOD |  | DEPOT |  | Wires Ready | 2025-02-18 | 2025-03-25 | [5 empty] | 902.4 | 902.4 | 344 | 902.4 | 558.4 | 2.6 | 1 | 100 | 344 |  | 2022-11-01 05:40
| B | 1 |  | 2 | STARTED |  | 851 | F6 | 851¦48 SECTION |  | DEPOT | HF PARTS | Wires Ready | 2025-02-11 | 2025-02-20 | [5 empty] | 540.2 | 371.4 | 212.1 | 540.2 | 159.3 | 1.8 | 0.7 | 68.8 | 380.9 | 168.8 | 2022-12-06 15:25
| B | 1 |  | 2 | STARTED |  | 151 | F8 | 351¦OSWO |  | DEPOT |  |  | 2025-09-25 | 2025-09-30 | [5 empty] | 14.7 | 8.8 | 11.6 |  | -2.8 | 0.8 |  | 60 | 17.5 | 5.9 | 2025-02-03 11:20
1 | B | 1 |  | 2 | STARTED |  | 351 | F6 | 351¦OSWO |  | DEPOT |  | Wires Ready | 2025-03-06 | 2025-03-26 | [5 empty] | 1 | 0.5 | 15.7 | 1 | -15.2 |  | 0.5 | 50 | 16.2 | 0.5 | 2025-03-11 05:24
| Y | 1 |  | 2 | STARTED |  | 251 | F0 | 251¦CIC APPLICATION |  | DEPOT |  | Wires Ready | 2025-09-02 | 2025-09-10 | [5 empty] | 51.1 | 14.6 | 96 |  | -81.4 | 0.2 |  | 28.6 | 132.5 | 36.5 | 2025-01-16 21:19
| B | 7 |  | 2 | STARTED |  | VC601 | PZH4 | 601¦TAILCONE |  | DEPOT | HF OTHER BHS | Wires Ready | 2024-01-22 | 2024-01-25 | [5 empty] | 269.1 | 134.6 | 109 | 269.1 | 25.6 | 1.2 | 0.5 | 50 | 243.6 | 134.6 | 2021-10-28 16:49
| B | 16 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-02-02 | 2024-02-05 | [5 empty] | 1 | 0.8 | 8.9 | 1 | -8.2 | 0.1 | 0.8 | 75 | 9.2 | 0.3 | 2024-02-09 10:30
| Y | 1 |  | 2 | STARTED |  | 301 | F0 | 301¦STRUCTURES |  | DEPOT |  | Wires Ready | 2025-09-08 | 2025-09-18 | [5 empty] | 65.9 | 22 | 24.6 |  | -2.6 | 0.9 |  | 33.3 | 68.5 | 43.9 | 2025-01-17 12:22
| Y | 1 |  | 2 | STARTED |  | 301 | F0 | 301¦STRUCTURES |  | DEPOT |  | Wires Ready | 2025-09-10 | 2025-09-23 | [5 empty] | 65.9 | 22 | 19.5 |  | 2.5 | 1.1 |  | 33.3 | 63.4 | 43.9 | 2025-01-17 13:07
| Y | 1 |  | 2 | STARTED |  | 201 | F7 | 201¦FLAME SPRAY |  | DEPOT |  | Wires Ready | 2025-04-23 | 2025-05-01 | [5 empty] | 306.6 | 168.6 | 54.1 |  | 114.5 | 3.1 |  | 55 | 192 | 137.9 | 2024-12-06 08:25
| B | 8 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-02-02 | 2024-02-05 | [5 empty] | 1 | 0.6 | 2.5 | 1 | -1.9 | 0.3 | 0.6 | 62.5 | 2.9 | 0.4 | 2024-02-07 12:13
| G | 1 |  | 2 | NOT STARTED |  | 401 | XM | 401¦STRUCTURES |  | DEPOT | HF OTHER BHS | Power On | 2024-12-03 | 2024-12-10 | [5 empty] | 26.1 |  |  | 26.1 |  |  |  |  | 26.1 | 26.1
| B | 1 |  | 2 | STARTED |  | 101 | F8 | 101¦STRUCTURES |  | DEPOT |  | Wires Ready | 2025-10-13 | 2025-10-14 | [5 empty] | 28.6 | 19 | 14.9 |  | 4.1 | 1.3 |  | 66.7 | 24.4 | 9.5 | 2023-10-23 09:43
| B | 8 |  | 2 | STARTED |  | 401 | F6 | 401¦STRUCTURES |  | DEPOT | IN WORK | Wires Ready | 2025-02-17 | 2025-04-14 | [5 empty] | 1606.2 | 803.1 | 331 | 1380.8 | 472.1 | 2.4 | 0.6 | 50 | 1134.1 | 803.1 | 2021-02-03 09:23
| B | 2 |  | 2 | NOT STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-04-25 | 2024-04-30 | [5 empty] | 1 |  |  | 1 |  |  |  |  | 1 | 1
| B | 1 |  | 2 | NOT STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-04-29 | 2024-05-03 | [5 empty] | 1 |  |  | 1 |  |  |  |  | 1 | 1
| B | 4 |  | 2 | NOT STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-04-29 | 2024-05-03 | [5 empty] | 1 |  |  | 1 |  |  |  |  | 1 | 1
| B | 2 |  | 2 | NOT STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-04-25 | 2024-04-30 | [5 empty] | 1 |  |  | 1 |  |  |  |  | 1 | 1
| B | 4 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-02-02 | 2024-02-05 | [5 empty] | 1 | 0.6 | 5.9 | 1 | -5.3 | 0.1 | 0.6 | 62.5 | 6.3 | 0.4 | 2024-02-07 09:54
| B | 16 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-02-02 | 2024-02-05 | [5 empty] | 1 | 0.6 | 6.4 | 1 | -5.8 | 0.1 | 0.6 | 62.5 | 6.8 | 0.4 | 2024-02-12 12:01
| B | 2 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-04-25 | 2024-04-30 | [5 empty] | 1 | 0.6 | 1.5 | 1 | -0.9 | 0.4 | 0.6 | 62.5 | 1.9 | 0.4 | 2024-04-30 11:51
| B | 2 |  | 2 | NOT STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-04-25 | 2024-04-30 | [5 empty] | 1 |  |  | 1 |  |  |  |  | 1 | 1
| B | 2 |  | 2 | NOT STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-04-25 | 2024-04-30 | [5 empty] | 1 |  |  | 1 |  |  |  |  | 1 | 1
| B | 2 |  | 2 | NOT STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-04-25 | 2024-04-30 | [5 empty] | 1 |  |  | 1 |  |  |  |  | 1 | 1
| B | 2 |  | 2 | NOT STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-04-29 | 2024-05-03 | [5 empty] | 1 |  |  | 1 |  |  |  |  | 1 | 1
| B | 2 |  | 2 | NOT STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-04-22 | 2024-04-26 | [5 empty] | 1 |  |  | 1 |  |  |  |  | 1 | 1
| B | 2 |  | 2 | NOT STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-04-22 | 2024-04-26 | [5 empty] | 1 |  |  | 1 |  |  |  |  | 1 | 1
| B | 2 |  | 2 | NOT STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-04-22 | 2024-04-26 | [5 empty] | 1 |  |  | 1 |  |  |  |  | 1 | 1
| B | 18 |  | 2 | NOT STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-04-25 | 2024-04-30 | [5 empty] | 1 |  |  | 1 |  |  |  |  | 1 | 1
| Y | 5 |  | 2 | SCHEDULED |  | 551 | DF | 915 |  | DEPOT |  | FCF | 2025-08-01 | 2025-08-08 | [5 empty] | 16 | [7 empty] | 16 | 16
| B | 9 |  | 2 | NOT STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-02-27 | 2024-03-05 | [5 empty] | 1 |  |  | 1 |  |  |  |  | 1 | 1
| B | 1 |  | 2 | NOT STARTED |  | 651 | F7 | 651¦GFE FLIGHT DECK |  | DEPOT |  | Wires Ready | 2025-04-07 | 2025-04-08 | [5 empty] | 1.1 | [7 empty] | 1.1 | 1.1
| B | 4 |  | 2 | NOT STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-04-25 | 2024-04-30 | [5 empty] | 1 |  |  | 1 |  |  |  |  | 1 | 1
| B | 1 |  | 2 | NOT STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-04-22 | 2024-04-26 | [5 empty] | 1 |  |  | 1 |  |  |  |  | 1 | 1
| B | 1 |  | 2 | NOT STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-04-22 | 2024-04-26 | [5 empty] | 1 |  |  | 1 |  |  |  |  | 1 | 1
| B | 2 |  | 2 | STARTED |  | 251 | F6 | 251¦FLOOR MOD |  | DEPOT | HF PARTS | Wires Ready | 2025-02-12 | 2025-02-26 | [5 empty] | 590 | 590 | 164.4 | 590 | 425.6 | 3.6 | 1 | 100 | 164.4 |  | 2021-09-25 05:29
| B | 5 |  | 2 | STARTED |  | 401 | F7 | 401¦STRUCTURES |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-03-10 | 2025-04-28 | [5 empty] | 1329.1 | 474.7 | 105.5 | 744.3 | 369.2 | 4.5 | 0.6 | 35.7 | 959.9 | 854.4 | 2021-04-27 06:14
| B | 3 |  | 2 | STARTED |  | 851 | EH | 000¦SERVICE BULLETIN |  | DEPOT |  |  | 2024-09-06 | 2024-09-09 | [5 empty] | 7 | 5.3 | 6 | 7 | -0.8 | 0.9 | 0.8 | 75 | 7.8 | 1.8 | 2024-07-08 13:09
| B | 4 |  | 2 | NOT STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-04-29 | 2024-05-03 | [5 empty] | 1 |  |  | 1 |  |  |  |  | 1 | 1
1 | B | 1 |  | 2 | STARTED |  | 351 | F8 | 351¦BRACKETS |  | DEPOT |  | Wires Ready | 2025-05-06 | 2025-05-12 | [5 empty] | 255.7 | 118 | 59.7 |  | 58.3 | 2 |  | 46.2 | 197.4 | 137.7 | 2024-02-06 06:11
| G | 1 |  | 2 | SCHEDULED |  | 101 | DZ | 101¦FLOORS |  | DEPOT |  | FCF | 2025-07-23 | 2025-07-30 | [5 empty] | 26.1 | 2 | 2 |  |  | 1 |  | 7.7 | 26 | 24 | 2023-01-09 19:21
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-02-22 | 2024-02-29 | [5 empty] | 1 | 0.6 | 11 | 1 | -10.4 | 0.1 | 0.6 | 62.5 | 11.4 | 0.4 | 2024-04-05 07:19
| B | 1 |  | 2 | STARTED |  | 251 | F8 | 251¦FLOOR MOD |  | DEPOT | HF PARTS | Wires Ready | 2025-08-20 | 2025-09-04 | [5 empty] | 118.2 | 118.2 | 193.2 |  | -75 | 0.6 |  | 100 | 193.2 |  | 2021-09-23 11:41 | 2021-11-04 18:01
| R | 1 |  | 2 | STARTED |  | 551 | DF | 551¦ENGINE MODS |  | DEPOT |  | FCF | 2024-02-01 | 2024-02-23 | [5 empty] | 16 | 14.5 | 6.4 | 16 | 8.1 | 2.3 | 0.9 | 90.9 | 7.9 | 1.5 | 2024-07-01 08:35
| B | 1 |  | 2 | STARTED |  | 401 | F9 | 401¦STRUCTURES |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-07-28 | 2025-08-11 | [5 empty] | 353.4 | 353.4 | 100.2 |  | 253.2 | 3.5 |  | 100 | 100.2 |  | 2022-05-19 06:56 | 2022-06-07 10:13
| G | 1 |  | 2 | STARTED |  | 801 | F1 | 801¦PROVISIONS |  | DEPOT | HF PARTS | Wires Ready | 2024-02-12 | 2024-02-20 | [5 empty] | 346.7 | 247.7 | 271.1 | 346.7 | -23.4 | 0.9 | 0.7 | 71.4 | 370.2 | 99.1 | 2023-02-17 05:27
| Y | 1 |  | 2 | NOT STARTED |  | 050 | 6 | 915 |  | DEPOT |  | Wires Ready | [7 empty] | 51.1 | [7 empty] | 51.1 | 51.1
| B | 1 |  | 2 | NOT STARTED |  | 251 | 12 | 915 |  | DEPOT |  | Hiblo | 2025-03-04 | 2025-03-11 | [5 empty] | 16 |  |  | 16 |  |  |  |  | 16 | 16
1 | B | 2 |  | 2 | NOT STARTED |  | 251 | F6 | 251¦VERIFICATION |  | DEPOT |  |  | 2025-02-04 | 2025-03-11 | [5 empty] | 313.3 | 134.3 |  | 313.3 | 134.3 |  | 0.6 | 42.9 | 179 | 179
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-02-16 | 2024-02-21 | [5 empty] | 1 | 0.6 | 780.6 | 1 | -780 |  | 0.6 | 62.5 | 781 | 0.4 | 2024-09-09 07:52
1 | B | 2 |  | 2 | STARTED |  | 601 | F7 | 601¦TAILCONE |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-04-28 | 2025-04-30 | [5 empty] | 734.7 | 388.9 | 245 |  | 143.9 | 1.6 |  | 52.9 | 590.7 | 345.7 | 2021-10-07 20:19
| B | 1 |  | 2 | STARTED |  | VC601 | PZH6 | 601¦TAILCONE |  | DEPOT | HF OTHER BHS | Wires Ready | 2024-07-09 | 2024-07-16 | [5 empty] | 226.4 | 64.7 | 18.2 | 226.4 | 46.5 | 3.6 | 0.3 | 28.6 | 179.9 | 161.7 | 2022-11-26 11:09
| B | 2 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-02-16 | 2024-02-21 | [5 empty] | 1 | 0.6 | 8 | 1 | -7.4 | 0.1 | 0.6 | 62.5 | 8.4 | 0.4 | 2024-09-23 05:39
1 | B | 6 |  | 2 | STARTED |  | 601 | F6 | 601¦TAILCONE |  | DEPOT |  |  | 2025-10-07 | 2025-10-09 | [5 empty] | 85.6 | 57.1 | 131.8 |  | -74.7 | 0.4 |  | 66.7 | 160.3 | 28.5 | 2024-10-15 06:34
| B | 1 |  | 2 | STARTED |  | 501 | F6 | 501¦HSTAB/VFIN |  | DEPOT | HF PARTS | Wires Ready | 2025-03-10 | 2025-03-25 | [5 empty] | 56.4 | 37.6 | 62.6 | 56.4 | -25 | 0.6 | 0.7 | 66.7 | 81.4 | 18.8 | 2021-03-12 07:07
| B | 1 |  | 2 | STARTED |  | 251 | F6 | 251¦PROVISIONS |  | DEPOT |  | Wires Ready | 2025-02-13 | 2025-03-27 | [5 empty] | 329.7 | 247.3 | 107 | 329.7 | 140.3 | 2.3 | 0.8 | 75 | 189.4 | 82.4 | 2022-10-13 19:07
| B | 1 |  | 2 | STARTED |  | 351 | XK | 351¦STRUCTURES |  | DEPOT |  |  | 2025-08-07 | 2025-08-13 | [5 empty] | 22 | 13.6 | 130.4 |  | -116.8 | 0.1 |  | 61.9 | 138.8 | 8.4 | 2025-01-31 06:20
| Y | 1 |  | 2 | NOT STARTED |  | 351 | P7 | 951 ¦ STR-DS |  | DEPOT |  | Wires Ready | 2024-02-26 | 2024-03-07 | [5 empty] | 0.9 |  |  | 0.9 |  |  |  |  | 0.9 | 0.9
| B | 1 |  | 2 | STARTED |  | 601 | F8 | 601¦TAILCONE |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-10-27 | 2025-10-30 | [5 empty] | 57.3 | 35.2 | 24.8 |  | 10.4 | 1.4 |  | 61.5 | 46.8 | 22 | 2022-01-31 19:50
| G | 1 |  | 2 | SCHEDULED |  | 601 | 9F | 601¦TAILCONE |  | DEPOT | HF PARTS | FCF | 2025-08-13 | 2025-08-20 | [5 empty] | 26.4 | [7 empty] | 26.4 | 26.4
| B | 1 |  | 2 | STARTED |  | 501 | F6 | 501¦HSTAB/VFIN |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-05-07 | 2025-05-21 | [5 empty] | 83.2 | 79.6 | 70.5 |  | 9.1 | 1.1 |  | 95.7 | 74.1 | 3.6 | 2025-02-05 21:31
| B | 2 |  | 2 | STARTED |  | 251 | F9 | 251¦PROVISIONS |  | DEPOT |  | Wires Ready | 2025-07-17 | 2025-07-31 | [5 empty] | 95.8 | 70.3 | 52.1 |  | 18.2 | 1.3 |  | 73.3 | 77.7 | 25.6 | 2024-05-22 05:22
| B | 1 |  | 2 | STARTED |  | 401 | 4G | 401¦AFT BG |  | DEPOT | HF PARTS | GFE Decrib | 2020-09-21 | 2020-09-21 | [5 empty] | 12 | 12 | 45.6 | 12 | -33.6 | 0.3 | 1 | 100 | 45.6 |  | 2021-02-25 19:00 | 2021-07-26 14:18
| B | 5 |  | 2 | STARTED |  | 601 | F7 | 601¦TAILCONE |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-06-10 | 2025-06-24 | [5 empty] | 553.5 | 369 | 35.6 |  | 333.4 | 10.4 |  | 66.7 | 220.1 | 184.5 | 2023-03-06 05:28
| G | 4 |  | 2 | STARTED |  | 601 | F6 | 601¦TAILCONE |  | DEPOT | HF PARTS | Wires Ready | 2026-01-15 | 2026-01-22 | [5 empty] | 790.5 | 425.6 | 93.8 |  | 331.8 | 4.5 |  | 53.8 | 458.6 | 364.8 | 2021-09-23 06:27
| B | 4 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-09-25 | 2024-10-25 | [5 empty] | 1 | 0.6 | 97.3 | 1 | -96.7 |  | 0.6 | 62.5 | 97.7 | 0.4 | 2024-10-24 13:33
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-09-25 | 2024-10-25 | [5 empty] | 1 | 1 | 2.3 | 1 | -1.3 | 0.4 | 1 | 100 | 2.3 |  | 2024-10-23 06:41
| B | 3 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-09-25 | 2024-10-25 | [5 empty] | 1 | 1 | 5.7 | 1 | -4.7 | 0.2 | 1 | 100 | 5.7 |  | 2024-10-23 05:50
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-09-25 | 2024-10-25 | [5 empty] | 1 | 1 | 30 | 1 | -29 |  | 1 | 100 | 30 |  | 2024-10-22 09:10
| B | 2 |  | 2 | NOT STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-03-26 | 2024-03-29 | [5 empty] | 1 | 0.8 |  | 1 | 0.8 |  | 0.8 | 75 | 0.3 | 0.3
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-09-25 | 2024-10-25 | [5 empty] | 1 | 0.6 | 140.2 | 1 | -139.6 |  | 0.6 | 62.5 | 140.6 | 0.4 | 2024-10-29 08:21
| Y | 1 |  | 2 | NOT STARTED |  | 451 | F7 | 451¦WHEEL WELL |  | DEPOT |  | Wires Ready | 2025-03-19 | 2025-04-16 | [5 empty] | 157.4 | 21.7 |  | 103.1 | 21.7 |  | 0.2 | 13.8 | 135.7 | 135.7
| B | 1 |  | 2 | STARTED |  | 251 | 4W | 251¦PROVISIONS |  | DEPOT |  |  | 2023-09-19 | 2023-09-22 | [5 empty] | 22.2 | 22.2 | 16.3 | 22.2 | 5.9 | 1.4 | 1 | 100 | 16.3 |  | 2023-09-21 06:46 | 2023-09-25 13:30
| B | 6 |  | 2 | NOT STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-08-14 | 2024-08-14 | [5 empty] | 1 |  |  | 1 |  |  |  |  | 1 | 1
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-02-22 | 2024-02-29 | [5 empty] | 1 | 0.6 | 2.8 | 1 | -2.2 | 0.2 | 0.6 | 62.5 | 3.2 | 0.4 | 2024-02-22 12:07
1 | B | 1 |  | 2 | STARTED |  | 401 | F0 | 401¦STRUCTURES |  | DEPOT |  |  | 2025-06-04 | 2025-06-11 | [5 empty] | 56.4 | 26 | 22 |  | 4 | 1.2 |  | 46.2 | 52.4 | 30.4 | 2025-03-24 14:31
| B | 1 |  | 2 | NOT STARTED |  | 151 | XC | 251¦OSWO |  | DEPOT |  |  | 2025-06-19 | 2025-06-26 | [5 empty] | 33 | [7 empty] | 33 | 33
| B | 1 |  | 2 | STARTED |  | 651 | F7 | 651¦FLIGHT DECK |  | DEPOT |  | Wires Ready | 2025-03-24 | 2025-03-27 | [5 empty] | 22 | 13.6 | 216 | 22 | -202.4 | 0.1 | 0.6 | 61.9 | 224.4 | 8.4 | 2024-01-29 17:45
| G | 2 |  | 2 | STARTED |  | 351 | F1 | 351¦STRUCTURES |  | DEPOT | HF PARTS | Wires Ready | 2024-02-05 | 2024-02-06 | [5 empty] | 290.3 |  | 114.1 | 290.3 | -114.1 |  |  |  | 404.4 | 290.3 | 2022-09-14 13:04
1 | B | 1 |  | 2 | STARTED |  | 101 | F6 | 101¦FLOORS |  | DEPOT | HF PARTS | Wires Ready | 2025-02-27 | 2025-03-10 | [5 empty] | 3484.9 | 3484.9 | 583.1 | 3484.9 | 2901.8 | 6 | 1 | 100 | 583.1 |  | 2022-09-08 15:42
| G | 1 |  | 2 | STARTED |  | 601 | F6 | 601¦TAILCONE |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-03-12 | 2025-05-12 | [5 empty] | 245.6 | 122.8 | 10.4 | 103 | 112.4 | 11.8 | 1.2 | 50 | 133.2 | 122.8 | 2023-08-09 09:37
| B | 2 |  | 2 | STARTED |  | 251 | F0 | 251¦INT STRUCTURES |  | DEPOT |  | Wires Ready | 2025-09-24 | 2025-09-30 | [5 empty] | 36.4 | 21.3 | 18.1 |  | 3.2 | 1.2 |  | 58.6 | 33.2 | 15.1 | 2025-02-04 06:54
| B | 1 |  | 2 | STARTED |  | 351 | F7 | 351¦PROVISIONS |  | DEPOT |  |  | 2025-04-07 | 2025-04-14 | [5 empty] | 144 | 144 | 147.7 |  | -3.7 | 1 |  | 100 | 147.7 |  | 2024-07-29 22:25
| B | 4 |  | 2 | NOT STARTED |  | 301 | F6 | 951 ¦ STR-GAC |  | DEPOT |  | Wires Ready | 2025-03-19 | 2025-04-21 | [5 empty] | 2105.2 |  |  | 1176.4 |  |  |  |  | 2105.2 | 2105.2
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  |  | 2025-01-10 | [5 empty] | 1 |  | 1507.5 | 1 | -1507.5 |  |  |  | 1508.5 | 1 | 2024-01-22 10:41
| B | 1 |  | 2 | STARTED |  | 251 | 72 | 251¦OSWO |  | DEPOT |  |  | 2025-11-06 | 2025-11-17 | [5 empty] | 4.4 | 4.4 | 7.9 |  | -3.5 | 0.6 |  | 100 | 7.9 |  | 2025-03-03 16:58 | 2025-03-06 20:33
| Y | 1 |  | 2 | STARTED |  | 251 | F0 | 251¦CIC APPLICATION |  | DEPOT |  | Wires Ready | 2025-09-02 | 2025-09-11 | [5 empty] | 51.1 | 12.2 | 22.5 |  | -10.3 | 0.5 |  | 23.8 | 61.4 | 38.9 | 2025-01-16 18:38
| B | 2 |  | 2 | STARTED |  | 100 | 3 | B AFT |  | DEPOT | WORKABLE | HiBlo | 2020-02-28 | 2020-03-02 | [5 empty] | 32 | 32 | 59 | 32 | -27 | 0.5 | 1 | 100 | 59 |  | 2020-06-15 09:21 | 2020-10-19 12:48
| G | 1 |  | 2 | STARTED |  | 151 | 4R | 151¦STRUCTURES |  | DEPOT |  | Power On | 2024-10-22 | 2024-10-29 | [5 empty] | 39.6 |  | 6.4 | 39.6 | -6.4 |  |  |  | 46 | 39.6 | 2023-02-17 06:26
| G | 1 |  | 2 | STARTED |  | 351 | F7 | 351¦STRUCTURES |  | DEPOT |  | Wires Ready | 2025-04-14 | 2025-04-23 | [5 empty] | 68.3 |  | 5 |  | -5 |  |  |  | 73.3 | 68.3 | 2022-08-16 08:08
1 | B | 1 |  | 2 | STARTED |  | VC451 | PSH | 000¦SERVICE BULLETIN |  | DEPOT |  |  | 2022-12-13 | 2024-05-29 | [5 empty] | 75 | 75 | 138.5 | 75 | -63.5 | 0.5 | 1 | 100 | 138.5 |  | 2024-02-16 08:59
| B | 1 |  | 2 | NOT STARTED |  | 50 | 1 | 401¦OSWO |  | DEPOT |  | Power On | 2025-01-06 | 2025-01-13 | [5 empty] | 5.3 |  |  | 5.3 |  |  |  |  | 5.3 | 5.3
| B | 1 |  | 2 | STARTED |  | 251 | F0 | 251¦PROVISIONS |  | DEPOT |  |  | 2025-10-07 | 2025-10-15 | [5 empty] | 13.9 | 6.9 | 15.5 |  | -8.6 | 0.4 |  | 50 | 22.4 | 6.9 | 2024-12-14 08:16
| Y | 1 |  | 2 | STARTED |  | 401 | F6 | 401¦STRUCTURES |  | DEPOT |  | Wires Ready | 2025-02-05 | 2025-02-12 | [5 empty] | 156.7 | 29.4 | 7.4 | 156.7 | 22 | 4 | 0.2 | 18.8 | 134.7 | 127.3 | 2024-01-29 12:16
| G | 1 |  | 2 | NOT STARTED |  | 551 | DF | 915 |  | DEPOT |  | Power On | 2024-11-20 | 2024-11-27 | [5 empty] | 16 |  |  | 16 |  |  |  |  | 16 | 16
| B | 1 |  | 2 | STARTED |  | 601 | F6 | 601¦TAILCONE |  | DEPOT | HF PARTS | Wires Ready | 2025-02-11 | 2025-02-25 | [5 empty] | 1005.2 | 591.3 | 64.2 | 1005.2 | 527.1 | 9.2 | 0.6 | 58.8 | 478.1 | 413.9 | 2022-05-24 12:40
| B | 1 |  | 2 | STARTED |  | 401 | F8 | 401¦STRUCTURES |  | DEPOT |  | Wires Ready | 2025-06-25 | 2025-07-10 | [5 empty] | 109.1 | 50.3 | 35 |  | 15.3 | 1.4 |  | 46.2 | 93.7 | 58.7 | 2022-10-06 17:47
| B | 1 |  | 2 | STARTED |  | 401 | 12 | 100NCP |  | DEPOT | IN WORK | HiBlo | 2025-03-12 | 2025-03-19 | [5 empty] | 16 | 16 | 25.4 | 16 | -9.4 | 0.6 | 1 | 100 | 25.4 |  | 2020-04-24 06:14 | 2020-05-04 09:31
| B | 1 |  | 2 | SCHEDULED |  | 951 | H2 | 915 |  | DEPOT |  |  | 2025-07-31 | 2025-08-07
| B | 1 |  | 2 | SCHEDULED |  | 951 | H2 | 915 |  | DEPOT |  |  | 2025-07-24 | 2025-07-31
| B | 1 |  | 2 | SCHEDULED |  | 951 | H2 | 915 |  | DEPOT |  |  | 2025-08-12 | 2025-08-19
| B | 1 |  | 2 | SCHEDULED |  | 951 | H2 | 915 |  | DEPOT |  |  | 2025-08-14 | 2025-08-21
| B | 1 |  | 2 | SCHEDULED |  | 951 | H2 | 915 |  | DEPOT |  |  | 2025-08-01 | 2025-08-08
| B | 1 |  | 2 | SCHEDULED |  | 951 | H2 | 915 |  | DEPOT |  |  | 2025-08-08 | 2025-08-15
| B | 1 |  | 2 | SCHEDULED |  | 951 | H2 | 915 |  | DEPOT |  |  | 2025-07-22 | 2025-07-29
| B | 1 |  | 2 | SCHEDULED |  | 951 | H2 | 915 |  | DEPOT |  |  | 2025-08-15 | 2025-08-22
| B | 1 |  | 2 | SCHEDULED |  | 951 | H2 | 915 |  | DEPOT |  |  | 2025-08-06 | 2025-08-13
| B | 1 |  | 2 | SCHEDULED |  | 951 | H2 | 915 |  | DEPOT |  |  | 2025-08-14 | 2025-08-21
| Y | 2 |  | 2 | NOT STARTED |  | VC801 | PZD2 |  |  | DEPOT | HF OTHER BHS | Power On | 2025-01-06 | 2025-01-13 | [5 empty] | 16 |  |  | 16 |  |  |  |  | 16 | 16
1 | B | 1 |  | 2 | STARTED |  | 151 | F6 | 151¦PROVISIONS |  | DEPOT | WORKABLE | Wires Ready | 2025-07-10 | 2025-07-23 | [5 empty] | 866.8 | 775.5 | 510.6 |  | 264.9 | 1.5 |  | 89.5 | 601.8 | 91.2 | 2020-08-19 07:43
| B | 3 |  | 2 | STARTED |  | 451 | F6 | 451¦WHEEL WELL |  | DEPOT |  | Wires Ready | 2025-02-04 | 2025-02-13 | [5 empty] | 669.3 | 245.4 | 328.1 | 669.3 | -82.7 | 0.7 | 0.4 | 36.7 | 752 | 423.9 | 2022-05-27 11:43
| B | 1 |  | 2 | NOT STARTED |  | 201 | F9 | 201¦OSWO |  | DEPOT |  |  | 2025-08-06 | 2025-08-07
| Y | 1 |  | 2 | STARTED |  | 451 | F6 | 451¦WHEEL WELL |  | DEPOT |  | Wires Ready | 2025-02-04 | 2025-03-11 | [5 empty] | 568.5 | 119.7 | 153.5 | 568.5 | -33.8 | 0.8 | 0.2 | 21.1 | 602.3 | 448.8 | 2022-06-01 11:47
1 | B | 1 |  | 2 | STARTED |  | 451 | F6 | 451¦WHEEL WELL |  | DEPOT | HF PARTS | Wires Ready | 2025-02-25 | 2025-04-14 | [5 empty] | 358.1 | 197.6 | 200.4 | 299.7 | -2.8 | 1 | 0.7 | 55.2 | 360.9 | 160.6 | 2022-05-18 09:16
| B | 1 |  | 2 | STARTED |  | VC201 | PSD | 000¦SERVICE BULLETIN |  | DEPOT |  |  | 2022-12-05 | 2025-01-15 | [5 empty] | 10 | 7.1 | 33.6 | 10 | -26.5 | 0.2 | 0.7 | 70.6 | 36.5 | 2.9 | 2022-12-06 07:29
| B | 2 |  | 2 | STARTED |  | 201 | 72 | 201¦FLOORS |  | DEPOT |  |  | 2025-07-16 | 2025-07-24 | [5 empty] | 22.7 | 15.1 | 14.7 |  | 0.4 | 1 |  | 66.7 | 22.3 | 7.6 | 2025-01-13 09:16
| B | 8 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-02-12 | 2024-02-12 | [5 empty] | 1 | 0.6 | 2 | 1 | -1.4 | 0.3 | 0.6 | 62.5 | 2.4 | 0.4 | 2024-02-13 11:20
| B | 1 |  | 2 | STARTED |  | 151 | F8 | 151¦STRUCTURES |  | DEPOT |  | Wires Ready | 2025-07-09 | 2025-07-16 | [5 empty] | 33 | 18.8 | 12.8 |  | 6 | 1.5 |  | 57.1 | 26.9 | 14.1 | 2025-03-20 14:41
1 | B | 3 |  | 2 | STARTED |  | 351 | 4F | 951 ¦ STR-DS |  | DEPOT |  |  | 2020-08-18 | 2020-08-21 | [7 empty] | 111.3 |  | -111.3 |  |  | 50 | 111.3 |  | 2022-05-28 05:44
1 | B | 2 |  | 2 | STARTED |  | 351 | F0 | 351¦OSWO |  | DEPOT |  |  | 2025-09-30 | 2025-10-01 | [5 empty] | 14.7 |  | 4.6 |  | -4.6 |  |  |  | 19.3 | 14.7 | 2025-02-11 15:33
| B | 1 |  | 2 | NOT STARTED |  | 401 | 71 | 401¦OSWO |  | DEPOT |  |  | 2025-06-13 | 2025-06-20 | [5 empty] | 33 | [7 empty] | 33 | 33
| G | 1 |  | 2 | STARTED |  | 401 | XM | 401¦STRUCTURES |  | DEPOT | HF OTHER BHS | Power On | 2025-06-11 | 2025-06-18 | [5 empty] | 26.1 | 15.2 | 9.2 |  | 6 | 1.7 |  | 58.3 | 20.1 | 10.9 | 2025-03-20 12:21
1 | B | 1 |  | 2 | STARTED |  | 351 | F7 | 351¦PROVISIONS |  | DEPOT |  | Wires Ready | 2025-09-09 | 2025-09-17 | [5 empty] | 337.3 | 233.5 | 15.5 |  | 218 | 15.1 |  | 69.2 | 119.3 | 103.8 | 2023-04-11 05:20
| B | 30 |  | 2 | NOT STARTED |  | 200 | 4 | 951 ¦ STR-DS |  | DEPOT | [16 empty] | 50
| B | 2 |  | 2 | NOT STARTED |  | 401 | F8 | 951 ¦ STR-DS |  | DEPOT |  |  | 2025-05-06 | 2025-05-27 | [5 empty] | 154.5 | [7 empty] | 154.5 | 154.5
| B | 1 |  | 2 | STARTED |  | 251 | XH | 951 ¦ STR-DS |  | DEPOT | [11 empty] | 33.4 |  | -33.4 |  |  | 50 | 33.4 |  | 2022-08-18 15:34
| B | 1 |  | 2 | NOT STARTED |  | 251 | 4J | 251¦OSWO |  | DEPOT |  |  | 2025-08-28 | 2025-09-04 | [5 empty] | 33 | [7 empty] | 33 | 33
| G | 1 |  | 2 | STARTED |  | 351 | F9 | 351¦PROVISIONS |  | DEPOT |  | Wires Ready | 2025-07-23 | 2025-07-29 | [5 empty] | 37.5 | 15 | 14.1 |  | 0.9 | 1.1 |  | 40 | 36.6 | 22.5 | 2024-01-23 14:34
| Y | 1 |  | 2 | NOT STARTED |  | 601 | F6 | 915 |  | DEPOT | HF PARTS | Wires Ready | 2025-03-12 | 2025-03-19
| B | 1 |  | 2 | STARTED |  | 351 | F6 | 351¦STRUCTURES |  | DEPOT |  | Wires Ready | 2025-05-21 | 2025-05-28 | [5 empty] | 32.1 | 17.1 | 36.6 |  | -19.5 | 0.5 |  | 53.3 | 51.6 | 15 | 2023-04-19 06:58
| B | 1 |  | 2 | STARTED |  | 601 | F6 | 601¦OSWO |  | DEPOT |  | Wires Ready | 2025-06-18 | 2025-06-24 | [5 empty] | 51.1 | [7 empty] | 51.1 | 51.1 | 2025-04-07 07:01
| B | 10 |  | 2 | NOT STARTED |  | 401 | F6 | 951 ¦ STR-DS |  | DEPOT |  |  | 2025-02-25 | 2025-05-05 | [5 empty] | 2142.3 | 856.9 |  | 1254.7 | 856.9 |  | 0.7 | 40 | 1285.3 | 1285.3
| B | 6 |  | 2 | NOT STARTED |  | 351 | F6 | 951 ¦ STR-DS |  | DEPOT |  |  | 2025-02-10 | 2025-02-19 | [5 empty] | 929.5 | 929.5 |  | 929.5 | 929.5 |  | 1 | 100
| B | 1 |  | 2 | STARTED |  | 851 | EH | 951 ¦ STR-GAC |  | DEPOT |  |  | 2024-09-10 | 2024-09-11 | [5 empty] | 7 | 7 | 9.5 | 7 | -2.5 | 0.7 | 1 | 100 | 9.5 |  | 2024-08-06 04:50
| B | 1 |  | 2 | STARTED |  | 851 | EH | 951 ¦ STR-GAC |  | DEPOT |  |  | 2024-09-19 | 2024-09-20 | [5 empty] | 7 | 5.3 | 16.9 | 7 | -11.7 | 0.3 | 0.8 | 75 | 18.6 | 1.8 | 2024-07-24 12:00
| B | 1 |  | 2 | STARTED |  | 301 | F9 | 301¦PROVISIONS |  | DEPOT |  | Wires Ready | 2025-08-27 | 2025-09-10 | [5 empty] | 73.3 | 50.4 | 104.1 |  | -53.7 | 0.5 |  | 68.8 | 127 | 22.9 | 2024-12-05 06:50
| B | 46 |  | 2 | NOT STARTED |  | 120 | 7 | 951 ¦ STR-DS |  | DEPOT
| B | 1 |  | 2 | STARTED |  | 451 | F9 | 451¦WHEEL WELL |  | DEPOT |  |  | 2025-12-08 | 2025-12-16 | [5 empty] | 17.4 | 13.1 | 19 |  | -6 | 0.7 |  | 75 | 23.4 | 4.3 | 2025-02-17 11:45
| Y | 2 |  | 2 | STARTED |  | 201 | F7 | 201¦FLAME SPRAY |  | DEPOT |  | Wires Ready | 2025-04-21 | 2025-04-29 | [5 empty] | 143.9 | 61.7 | 94.3 |  | -32.6 | 0.7 |  | 42.9 | 176.6 | 82.3 | 2024-12-06 08:19
| B | 2 |  | 2 | STARTED |  | 251 | F0 | 251¦INT STRUCTURES |  | DEPOT |  | Wires Ready | 2025-09-22 | 2025-09-29 | [5 empty] | 36.4 | 10 | 25.5 |  | -15.5 | 0.4 |  | 27.6 | 51.9 | 26.4 | 2025-02-03 05:31
1 | B | 1 |  | 2 | STARTED |  | 120 | 7 | 951 ¦ STR-DS |  | DEPOT | HF QA |  | 2020-05-12 | 2020-05-13 | [5 empty] | 32 | 32 | 109.5 | 32 | -77.5 | 0.3 | 1 | 100 | 109.5 |  | 2020-09-09 06:00 | 2021-01-27 08:11
2 | B | 29 |  | 2 | STARTED |  | 351 | F3 | 951 ¦ STR-DS |  | DEPOT | WORKABLE | Wires Ready | 2025-02-05 | 2025-03-11 | [5 empty] | 5045 | 5045 | 125 | 5045 | 4920 | 40.4 | 1 | 100 | 125 |  | 2020-10-27 05:22
1 | B | 1 |  | 2 | STARTED |  | 401 | F7 | 951 ¦ STR-DS |  | DEPOT |  |  | 2025-04-14 | 2025-05-28 | [5 empty] | 1682.5 | 1121.6 |  |  | 1121.6 |  |  | 66.7 | 560.8 | 560.8 | 2021-06-02
1 | Y | 1 |  | 2 | STARTED |  | 601 | F9 | 601¦TAILCONE |  | DEPOT |  | Wires Ready | 2026-02-17 | 2026-02-18 | [5 empty] | 800.1 | 386.2 | 318.6 |  | 67.6 | 1.2 |  | 48.3 | 732.4 | 413.8 | 2022-07-01 05:43
1 | B | 1 |  | 2 | STARTED |  | 601 | F9 | 601¦TAILCONE |  | DEPOT |  | Wires Ready | 2026-01-28 | 2026-02-03 | [5 empty] | 530 | 244.6 | 183.4 |  | 61.2 | 1.3 |  | 46.2 | 468.8 | 285.4 | 2022-07-01 05:37
| B | 1 |  | 2 | STARTED |  | 301 | XJ | 951 ¦ STR-GAC |  | DEPOT |  |  | 2020-08-18 | 2020-08-21 | [7 empty] | 32 |  | -32 |  |  | 100 | 32 |  | 2022-05-23 17:11
| B | 1 |  | 2 | NOT STARTED |  | 050 | 5 | 101¦OSWO |  | DEPOT |  |  | 2025-05-16 | 2025-05-23 | [5 empty] | 33 | [7 empty] | 33 | 33
| B | 4 |  | 2 | STARTED |  | 351 | F6 | 351¦PROVISIONS |  | DEPOT | HF PARTS | Wires Ready | 2025-02-20 | 2025-03-05 | [5 empty] | 358.4 | 244.4 | 233.4 | 358.4 | 11 | 1 | 0.7 | 68.2 | 347.5 | 114.1 | 2022-04-25 15:29
| B | 6 |  | 2 | STARTED |  | 101 | F9 | 101¦FLOORS |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-02-05 | 2025-02-25 | [5 empty] | 1155.9 | 578 | 184.8 | 1155.9 | 393.1 | 3.1 | 0.5 | 50 | 762.8 | 578 | 2021-05-01 12:14
| B | 5 |  | 2 | STARTED |  | 351 | F0 | 351¦PROVISIONS |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-10-23 | 2025-10-28 | [5 empty] | 188.1 | 178.7 | 275.9 |  | -97.2 | 0.6 |  | 95 | 285.3 | 9.4 | 2023-03-18 05:32
| B | 1 |  | 2 | STARTED |  | 501 | F0 | 501¦HSTAB/VFIN |  | DEPOT |  | Wires Ready | 2025-09-11 | 2025-09-18 | [5 empty] | 34.7 | 15.1 | 31.9 |  | -16.8 | 0.5 |  | 43.5 | 51.5 | 19.6 | 2025-01-17 14:14
1 | B | 1 |  | 2 | STARTED |  | 851 | EH | 951 ¦ STR-GAC |  | DEPOT | [11 empty] | 59 |  | -59 |  |  | 100 | 59 |  | 2022-05-23 22:19
| B | 3 |  | 2 | STARTED |  | 601 | F6 | 601¦TAILCONE |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-03-12 | 2025-04-03 | [5 empty] | 87.7 | 43.8 | 27.3 | 87.7 | 16.5 | 1.6 | 0.5 | 50 | 71.1 | 43.8 | 2023-06-30 08:19
| B | 50 |  | 2 | STARTED |  | 401 | 8 | 951 ¦ STR-DS |  | DEPOT | [11 empty] | 8.7 |  | -8.7 |  |  | 50 | 8.7 |  | 2025-03-14 13:25
2 | B | 1 |  | 2 | STARTED |  | 251 | F6 | 251¦FLOOR MOD |  | DEPOT |  | Wires Ready | 2025-09-04 | 2025-09-18 | [5 empty] | 860 | 860 | 257.6 |  | 602.5 | 3.3 |  | 100 | 257.6 |  | 2022-11-21 21:59
| B | 3 |  | 2 | STARTED |  | 601 | F7 | 601¦OSWO |  | DEPOT |  |  | 2026-01-15 | 2026-01-22 | [5 empty] | 33 | 24.8 | 8 |  | 16.8 | 3.1 |  | 75 | 16.3 | 8.3 | 2025-03-17 22:53
1 | B | 5 |  | 2 | STARTED |  | 151 | F6 | 101¦OSWO |  | DEPOT |  | Wires Ready | 2025-02-05 | 2025-02-25 | [5 empty] | 367.4 | 183.7 | 3.5 | 367.4 | 180.2 | 52.5 | 0.5 | 50 | 187.2 | 183.7 | 2023-11-30 09:27
| B | 2 |  | 2 | STARTED |  | 551 | F7 | 551¦WINGS |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-01-30 | 2025-02-19 | [5 empty] | 838.8 | 838.8 | 18 | 838.8 | 820.8 | 46.6 | 1 | 100 | 18 |  | 2022-07-19 07:02
| Y | 2 |  | 2 | STARTED |  | 451 | F9 | 451¦WHEEL WELL |  | DEPOT |  | Wires Ready | 2025-08-07 | 2025-08-25 | [5 empty] | 139.7 | 27.9 | 39.2 |  | -11.3 | 0.7 |  | 20 | 151 | 111.8 | 2022-11-15 05:29
3 | B | 1 |  | 2 | STARTED |  | 651 | F6 | 651¦FLIGHT DECK |  | DEPOT |  | Wires Ready | 2025-01-27 | 2025-01-28 | [5 empty] | 26.1 | 14.6 | 225.8 | 26.1 | -211.2 | 0.1 | 0.6 | 55.9 | 237.3 | 11.5 | 2022-07-07 11:28
| B | 1 |  | 2 | STARTED |  | 251 | F0 | 251¦INT STRUCTURES |  | DEPOT |  | Wires Ready | 2025-10-15 | 2025-10-21 | [5 empty] | 29.1 | 7.7 | 26.4 |  | -18.7 | 0.3 |  | 26.7 | 47.7 | 21.3 | 2024-12-06 06:30
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-04-30 | 2024-05-07 | [5 empty] | 1 | 0.8 | 1.7 | 1 | -0.9 | 0.4 | 0.8 | 75 | 1.9 | 0.3 | 2024-04-30 13:19
| B | 2 |  | 2 | STARTED |  | 101 | 72 | 101¦FLOORS |  | DEPOT | HF PARTS | Wires Ready | 2025-03-17 | 2025-03-25 | [5 empty] | 99.4 | 72.7 | 182.4 | 99.4 | -109.7 | 0.4 | 0.7 | 73.1 | 209.2 | 26.8 | 2022-06-24 06:33
| B | 8 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-02-02 | 2024-02-05 | [5 empty] | 1 | 0.8 | 1.5 | 1 | -0.8 | 0.5 | 0.8 | 75 | 1.8 | 0.3 | 2024-02-12 12:46
| Y | 2 |  | 2 | STARTED |  | 351 | F9 | 351¦STRUCTURES |  | DEPOT |  | Wires Ready | 2025-10-22 | 2025-10-28 | [5 empty] | 64.8 | 34.9 | 39.6 |  | -4.7 | 0.9 |  | 53.8 | 69.5 | 29.9 | 2022-12-07 06:24
1 | B | 1 |  | 2 | STARTED |  | 251 | 71 | 351¦PROVISIONS |  | DEPOT |  | Wires Ready | 2025-08-28 | 2025-09-04 | [5 empty] | 26.4 | 13.9 | 67 |  | -53.1 | 0.2 |  | 52.6 | 79.5 | 12.5 | 2025-02-04 14:48
| B | 1 |  | 2 | STARTED |  | 351 | F7 | 351¦STRUCTURES |  | DEPOT |  | Wires Ready | 2025-03-17 | 2025-05-14 | [5 empty] | 41.2 | 24.7 | 5.7 | 14.7 | 19 | 4.3 | 1.7 | 60 | 22.2 | 16.5 | 2024-12-30 05:26
| G | 1 |  | 2 | NOT STARTED |  | 601 | 9C | 601¦TAILCONE |  | DEPOT |  | Power On | 2025-04-29 | 2025-05-06 | [5 empty] | 16 | [7 empty] | 16 | 16
1 | B | 1 |  | 2 | STARTED |  | 601 | F7 | 601¦TAILCONE |  | DEPOT |  | Wires Ready | 2026-01-26 | 2026-02-02 | [5 empty] | 83.4 | 11.9 | 69.9 |  | -58 | 0.2 |  | 14.3 | 141.4 | 71.5 | 2025-02-18 00:46
| B | 2 |  | 2 | NOT STARTED |  | 401 | XM | 401¦OSWO |  | DEPOT |  |  | 2025-06-09 | 2025-06-16 | [5 empty] | 33 | [7 empty] | 33 | 33
| B | 4 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-02-02 | 2024-02-05 | [5 empty] | 1 | 0.6 | 3.9 | 1 | -3.3 | 0.2 | 0.6 | 62.5 | 4.3 | 0.4 | 2024-02-07 07:03
| B | 1 |  | 2 | STARTED |  | 401 | F6 | 401¦STRUCTURES |  | DEPOT |  | Wires Ready | 2025-03-13 | 2025-03-25 | [5 empty] | 132.2 | 61 | 256.7 | 132.2 | -195.7 | 0.2 | 0.5 | 46.2 | 327.9 | 71.2 | 2023-04-27 05:19
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 551¦ENGINE MODS |  | DEPOT |  |  | 2024-03-01 | 2024-03-01 | [5 empty] | 33 |  | 0.1 | 33 | -0.1 |  |  |  | 33.1 | 33 | 2024-03-08 14:17
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 551¦ENGINE MODS |  | DEPOT |  |  | 2024-03-12 | 2024-03-13 | [5 empty] | 33 |  | 0.1 | 33 | -0.1 |  |  |  | 33.1 | 33 | 2024-03-08 14:13
1 | B | 1 |  | 2 | STARTED |  | 151 | F8 | 151¦STRUCTURES |  | DEPOT |  | Wires Ready | 2025-07-10 | 2025-07-22 | [5 empty] | 56.4 | 32.2 | 162.2 |  | -130 | 0.2 |  | 57.1 | 186.4 | 24.2 | 2023-09-13 11:59
| B | 1 |  | 2 | STARTED |  | 501 | F6 | 501¦HSTAB/VFIN |  | DEPOT |  | Wires Ready | 2025-02-11 | 2025-02-18 | [5 empty] | 41.2 | 22 | 15.9 | 41.2 | 6.1 | 1.4 | 0.5 | 53.3 | 35.1 | 19.2 | 2024-12-23 08:36
| B | 1 |  | 2 | STARTED |  | 601 | F7 | 601¦TAILCONE |  | DEPOT |  | Wires Ready | 2025-11-26 | 2025-12-03 | [5 empty] | 75.3 | 40.1 | 17.3 |  | 22.8 | 2.3 |  | 53.3 | 52.4 | 35.1 | 2023-03-21 20:47
| B | 1 |  | 2 | STARTED |  | 601 | 72 | 915 |  | DEPOT |  |  | 2026-03-16 | 2026-03-19 | [7 empty] | 34.9 |  | -34.9 |  |  | 66.7 | 34.9 |  | 2025-03-06 09:26
| B | 1 |  | 2 | STARTED |  | 151 | F6 | 151¦OSWO |  | DEPOT |  | Wires Ready | 2025-07-02 | 2025-07-07 | [5 empty] | 68.4 | 45.6 | 16.1 |  | 29.5 | 2.8 |  | 66.7 | 38.9 | 22.8 | 2024-03-25 05:48
1 | Y | 1 |  | 2 | STARTED |  | 401 | F6 | 401¦STRUCTURES |  | DEPOT | HF PARTS | Wires Ready | 2025-02-05 | 2025-02-13 | [5 empty] | 452.5 | 198 | 187.7 | 452.5 | 10.3 | 1.1 | 0.4 | 43.8 | 442.2 | 254.5 | 2022-12-07 06:54
1 | B | 2 |  | 2 | STARTED |  | 101 | 71 | 101¦OSWO |  | DEPOT |  |  | 2025-09-24 | 2025-09-30 | [5 empty] | 503.4 |  | 13.2 |  | -13.2 |  |  |  | 516.6 | 503.4 | 2023-04-21 08:17
| B | 1 |  | 2 | STARTED |  | 901 | 5G | 901¦BLANKETS MOD |  | DEPOT |  | Wires Ready | 2024-05-21 | 2024-05-23 | [5 empty] | 16 | 16 | 27.7 | 16 | -11.7 | 0.6 | 1 | 100 | 27.7 |  | 2024-05-20 12:01
| B | 1 |  | 2 | STARTED |  | 901 | 5G | 901¦BLANKETS MOD |  | DEPOT |  | Wires Ready | 2024-05-22 | 2024-05-24 | [5 empty] | 16 | 16 | 28.8 | 16 | -12.8 | 0.6 | 1 | 100 | 28.8 |  | 2024-05-20 12:53
| B | 1 |  | 2 | STARTED |  | 901 | 5G | 901¦BLANKETS MOD |  | DEPOT |  | Wires Ready | 2024-06-04 | 2024-06-06 | [5 empty] | 16 | 10.7 | 21.8 | 16 | -11.1 | 0.5 | 0.7 | 66.7 | 27.1 | 5.3 | 2024-06-03 07:15
| B | 1 |  | 2 | STARTED |  | 901 | 5G | 901¦BLANKETS MOD |  | DEPOT |  | Wires Ready | 2024-08-05 | 2024-08-07 | [5 empty] | 16 | 12.4 | 24 | 16 | -11.6 | 0.5 | 0.8 | 77.8 | 27.6 | 3.6 | 2024-08-14 11:51
| B | 1 |  | 2 | STARTED |  | 401 | F6 | 401¦PROVISIONS |  | DEPOT |  | Wires Ready | 2025-02-03 | 2025-02-10 | [5 empty] | 308.3 | 138.7 | 67.8 | 308.3 | 70.9 | 2 | 0.5 | 45 | 237.4 | 169.6 | 2023-10-16 06:22
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-02-22 | 2024-02-29 | [5 empty] | 1 | 1 | 0.8 | 1 | 0.2 | 1.3 | 1 | 100 | 0.8 |  | 2024-03-05 09:12
| B | 8 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-02-02 | 2024-02-05 | [5 empty] | 1 | 0.6 | 6.9 | 1 | -6.3 | 0.1 | 0.6 | 62.5 | 7.3 | 0.4 | 2024-02-09 09:15
| Y | 2 |  | 2 | STARTED |  | 201 | F9 | 201¦PROVISIONS |  | DEPOT |  |  | 2025-04-21 | 2025-04-28 | [5 empty] | 26.4 | 15.9 | 33.1 |  | -17.2 | 0.5 |  | 60 | 43.7 | 10.6 | 2025-02-26 04:33
| G | 2 |  | 2 | NOT STARTED |  | 801 | XP | 801¦PROVISIONS |  | DEPOT | HF PARTS | Power On | 2024-08-14 | 2024-08-21 | [5 empty] | 16 |  |  | 16 |  |  |  |  | 16 | 16
| B | 2 |  | 2 | STARTED |  | 151 | F8 | 151¦STRUCTURES |  | DEPOT |  | Wires Ready | 2025-07-10 | 2025-07-17 | [5 empty] | 33 | 18.8 | 23.9 |  | -5.1 | 0.8 |  | 57.1 | 38 | 14.1 | 2025-03-31 05:25
| B | 3 |  | 2 | STARTED |  | 801 | F5 | 801¦PROVISIONS |  | DEPOT |  |  | 2025-06-11 | 2025-06-18 | [5 empty] | 33 | 23.3 | 35.8 |  | -12.5 | 0.7 |  | 70.6 | 45.5 | 9.7 | 2025-03-26 09:39
| Y | 1 |  | 2 | STARTED |  | 601 | F9 | 601¦TAILCONE |  | DEPOT |  | Wires Ready | 2025-09-16 | 2025-09-22 | [5 empty] | 57.9 | 31.2 | 8.4 |  | 22.8 | 3.7 |  | 53.8 | 35.1 | 26.7 | 2025-03-05 08:57
1 | B | 1 |  | 2 | STARTED |  | 351 | F0 | 351¦STRUCTURES |  | DEPOT | WORKABLE | Power On | 2025-09-09 | 2025-09-17 | [5 empty] | 36.7 | 11 | 32.1 |  | -21.1 | 0.3 |  | 30 | 57.8 | 25.7 | 2021-05-05 16:01
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-02-22 | 2024-02-29 | [5 empty] | 1 | 0.8 | 3 | 1 | -2.3 | 0.3 | 0.8 | 75 | 3.3 | 0.3 | 2024-04-16 09:18
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-05-02 | 2024-05-09 | [5 empty] | 1 | 0.4 | 0.3 | 1 | 0.1 | 1.3 | 0.4 | 37.5 | 0.9 | 0.6 | 2025-03-21 13:13
| Y | 1 |  | 2 | STARTED |  | 251 | F9 | 251¦FLAME SPRAY |  | DEPOT |  | Wires Ready | 2025-08-25 | 2025-09-03 | [5 empty] | 51.1 | 23 | 126.4 |  | -103.4 | 0.2 |  | 45 | 154.5 | 28.1 | 2024-12-10 16:24
| B | 1 |  | 2 | STARTED |  | 451 | F8 | 451¦WHEEL WELL |  | DEPOT |  | Wires Ready | 2025-05-07 | 2025-05-27 | [5 empty] | 99.3 | 33.1 | 62.1 |  | -29 | 0.5 |  | 33.3 | 128.3 | 66.2 | 2025-01-29 09:05
| B | 2 |  | 2 | STARTED |  | 551 | F7 | 551¦WINGS |  | DEPOT |  | Wires Ready | 2025-05-06 | 2025-05-12 | [5 empty] | 83.6 | 71.7 | 76.9 |  | -5.2 | 0.9 |  | 85.7 | 88.8 | 11.9 | 2023-04-05 09:08
| B | 1 |  | 2 | STARTED |  | 601 | F6 | 601¦TAILCONE |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-02-11 | 2025-02-11 | [5 empty] | 163.5 | 75.4 | 34.9 | 163.5 | 40.5 | 2.2 | 0.5 | 46.2 | 122.9 | 88 | 2023-07-18 15:37
| B | 1 |  | 2 | STARTED |  | 601 | F6 | 601¦TAILCONE |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-02-25 | 2025-02-25 | [5 empty] | 220.2 | 102.7 | 99.1 | 220.2 | 3.6 | 1 | 0.5 | 46.7 | 216.5 | 117.4 | 2023-07-18 15:30
| B | 1 |  | 2 | STARTED |  | 151 | F8 | 151¦STRUCTURES |  | DEPOT |  | Wires Ready | 2025-04-24 | 2025-05-05 | [5 empty] | 49.4 | 34 | 48 |  | -14 | 0.7 |  | 68.8 | 63.4 | 15.4 | 2025-03-25 12:12
| B | 3 |  | 2 | STARTED |  | 601 | F8 | 601¦TAILCONE |  | DEPOT | HF PARTS | Wires Ready | 2025-05-12 | 2025-05-29 | [5 empty] | 1786.4 | 1236.7 | 480.2 |  | 756.5 | 2.6 |  | 69.2 | 1029.9 | 549.7 | 2022-08-04 05:21
| G | 1 |  | 2 | STARTED |  | 151 | F6 | 101¦PROVISIONS |  | DEPOT |  |  | 2025-09-02 | 2025-09-10 | [5 empty] | 43.5 | 18.3 | 24.3 |  | -6 | 0.8 |  | 42.1 | 49.5 | 25.2 | 2024-12-18 05:53
| Y | 2 |  | 2 | STARTED |  | 601 | F9 | 601¦TAILCONE |  | DEPOT | HF PARTS | Wires Ready | 2025-09-08 | 2025-09-16 | [5 empty] | 332.6 | 183 | 274.7 |  | -91.7 | 0.7 |  | 55 | 424.4 | 149.7 | 2022-02-08 19:35
| B | 1 |  | 2 | STARTED |  | 151 | F6 | 351¦PROVISIONS |  | DEPOT |  | Wires Ready | 2025-07-24 | 2025-07-30 | [5 empty] | 49.5 | 33 | 42.3 |  | -9.3 | 0.8 |  | 66.7 | 58.8 | 16.5 | 2024-02-05 10:56
| B | 1 |  | 2 | NOT STARTED |  | 401 | 71 | 401¦OSWO |  | DEPOT |  |  | 2025-06-12 | 2025-06-19 | [5 empty] | 33 | [7 empty] | 33 | 33
| B | 2 |  | 2 | STARTED |  | 501 | F6 | 501¦HSTAB/VFIN |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-02-25 | 2025-03-05 | [5 empty] | 56.4 | 28.2 | 110.2 | 56.4 | -82 | 0.3 | 0.5 | 50 | 138.4 | 28.2 | 2023-07-26 14:50
| B | 3 |  | 2 | STARTED |  | 501 | F6 | 501¦HSTAB/VFIN |  | DEPOT | WORKABLE | Wires Ready | 2025-01-29 | 2025-02-05 | [5 empty] | 56.4 | 24.7 | 36.4 | 56.4 | -11.7 | 0.7 | 0.4 | 43.8 | 68.1 | 31.7 | 2023-08-08 15:36
| Y | 1 |  | 2 | STARTED |  | 351 | F0 | 351¦PROVISIONS |  | DEPOT |  | Wires Ready | 2025-10-13 | 2025-10-16 | [5 empty] | 86.7 | 46.7 | 140.6 |  | -93.9 | 0.3 |  | 53.8 | 180.6 | 40 | 2023-10-16 15:10
| B | 2 |  | 2 | STARTED |  | 201 | F6 | 201¦WINDOWS |  | DEPOT | HF PARTS |  | 2025-03-10 | 2025-04-28 | [5 empty] | 27.1 | 26.3 | 123 | 15.2 | -96.7 | 0.2 | 1.7 | 97.1 | 123.8 | 0.8 | 2021-06-03 15:41
| B | 1 |  | 2 | NOT STARTED |  | 251 | XH | 251¦OSWO |  | DEPOT |  |  | 2025-08-28 | 2025-09-04 | [5 empty] | 33 | [7 empty] | 33 | 33
| G | 1 |  | 2 | STARTED |  | 201 | F4 | 201¦PROVISIONS |  | DEPOT |  | Wires Ready | 2025-08-13 | 2025-08-13 | [5 empty] | 1 | 0.8 | 37.9 |  | -37.1 |  |  | 76.5 | 38.1 | 0.2 | 2025-02-11 08:51
2 | B | 7 |  | 2 | STARTED |  | 351 | F7 | 351¦PROVISIONS |  | DEPOT | HF PARTS | Wires Ready | 2025-03-05 | 2025-03-26 | [5 empty] | 1091.7 | 742.4 | 510.4 | 1091.7 | 232 | 1.5 | 0.7 | 68 | 859.7 | 349.3 | 2022-04-18 15:47
| B | 1 |  | 2 | STARTED |  | 551 | F7 | 551¦WINGS |  | DEPOT | HF PARTS | Wires Ready | 2025-04-28 | 2025-05-06 | [5 empty] | 147 | 134.2 | 77.1 |  | 57.1 | 1.7 |  | 91.3 | 89.9 | 12.8 | 2022-09-30 09:24
| B | 1 |  | 2 | STARTED |  | 301 | F6 | 551¦OSWO |  | DEPOT |  |  | 2025-04-17 | 2025-04-17 | [5 empty] | 0.9 |  | 1.2 |  | -1.2 |  |  |  | 2.1 | 0.9 | 2025-02-18 06:18
| B | 1 |  | 2 | STARTED |  | VC601 | PZH3 | 601¦TAILCONE |  | DEPOT | HF OTHER BHS | Wires Ready | 2024-02-19 | 2024-02-27 | [5 empty] | 20.8 | 9.2 | 14.8 | 20.8 | -5.6 | 0.6 | 0.4 | 44.4 | 26.3 | 11.5 | 2022-11-25 11:12
| B | 3 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-02-02 | 2024-02-05 | [5 empty] | 1 | 0.8 | 6.9 | 1 | -6.2 | 0.1 | 0.8 | 75 | 7.2 | 0.3 | 2024-02-09 11:55
| B | 1 |  | 2 | NOT STARTED |  | 351 | 1 | 351¦OSWO |  | DEPOT |  |  | 2025-06-12 | 2025-06-19 | [5 empty] | 33 | [7 empty] | 33 | 33
1 | B | 1 |  | 2 | STARTED |  | 451 | F0 | 451¦WHEEL WELL |  | DEPOT | HF PARTS | Wires Ready | 2025-09-25 | 2025-10-08 | [5 empty] | 104.8 | 48.9 | 48.9 |  |  | 1 |  | 46.7 | 104.8 | 55.9 | 2023-01-03 05:22
| B | 1 |  | 2 | STARTED |  | 151 | F6 | 101¦PROVISIONS |  | DEPOT |  | Wires Ready | 2025-10-15 | 2025-10-15 | [5 empty] | 118.4 | 101.5 | 51.2 |  | 50.3 | 2 |  | 85.7 | 68.1 | 16.9 | 2023-10-09 05:20
1 | B | 1 |  | 2 | STARTED |  | 601 | F8 | 601¦TAILCONE |  | DEPOT | HF PARTS | Wires Ready | 2025-06-26 | 2025-07-21 | [5 empty] | 543.1 | 395 | 166.3 |  | 228.7 | 2.4 |  | 72.7 | 314.4 | 148.1 | 2022-05-23 06:10
2 | B | 2 |  | 2 | STARTED |  | 401 | F0 | 401¦OSWO |  | DEPOT |  | Wires Ready | 2025-09-29 | 2025-10-02 | [5 empty] | 310.2 | 256.2 | 205.8 |  | 50.4 | 1.2 |  | 82.6 | 259.7 | 53.9 | 2022-10-20 16:33
| Y | 1 |  | 2 | STARTED |  | 251 | F8 | 251¦FLOOR DRILL |  | DEPOT |  | Wires Ready | 2025-02-06 | 2025-03-04 | [5 empty] | 243.7 | 113.7 | 65.2 | 243.7 | 48.5 | 1.7 | 0.5 | 46.7 | 195.2 | 130 | 2025-02-14 05:11
1 | B | 1 |  | 2 | STARTED |  | 401 | F0 | 401¦STRUCTURES |  | DEPOT |  |  | 2025-06-03 | 2025-06-10 | [5 empty] | 56.4 | 32.9 | 59.1 |  | -26.2 | 0.6 |  | 58.3 | 82.6 | 23.5 | 2025-02-27 13:37
| B | 2 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-03-18 | 2024-03-25 | [5 empty] | 1 | 0.6 | 4 | 1 | -3.4 | 0.2 | 0.6 | 62.5 | 4.4 | 0.4 | 2024-04-04 13:03
| B | 47 |  | 2 | NOT STARTED |  | VC050 | PSP |  |  | DEPOT |  |  | 2025-01-14 | 2025-01-15 | [5 empty] | 8 | 7.7 |  | 8 | 7.7 |  | 1 | 96.4 | 0.3 | 0.3
| B | 1 |  | 2 | STARTED |  | 101 | F6 | 101¦OSWO |  | DEPOT |  | Wires Ready | 2025-09-11 | 2025-09-17 | [5 empty] | 92 | 61.3 | 13 |  | 48.3 | 4.7 |  | 66.7 | 43.7 | 30.7 | 2023-08-09 12:04
| B | 2 |  | 2 | NOT STARTED |  | VC901 | PZD9 |  |  | DEPOT |  | Power On | 2025-01-06 | 2025-01-13 | [5 empty] | 16 |  |  | 16 |  |  |  |  | 16 | 16
| B | 2 |  | 2 | NOT STARTED |  | VC901 | PZD3 |  |  | DEPOT |  | Power On | 2025-01-06 | 2025-01-13 | [5 empty] | 16 |  |  | 16 |  |  |  |  | 16 | 16
2 | B | 2 |  | 2 | STARTED |  | 101 | F8 | 101¦FLOORS |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-09-17 | 2025-09-24 | [5 empty] | 2945 | 2945 | 149.8 |  | 2795.2 | 19.7 |  | 100 | 149.8 |  | 2021-05-05 12:18
| B | 1 |  | 2 | STARTED |  | 201 | F8 | 201¦WINDOWS |  | DEPOT | HF PARTS | Wires Ready | 2025-06-09 | 2025-06-16 | [5 empty] | 33.1 | 19.1 | 263.9 |  | -244.8 | 0.1 |  | 57.7 | 277.9 | 14 | 2022-11-07 14:22
1 | B | 4 |  | 2 | STARTED |  | 351 | F9 | 351¦STRUCTURES |  | DEPOT | WORKABLE | Wires Ready | 2025-08-11 | 2025-08-20 | [5 empty] | 397.1 | 172.7 | 197 |  | -24.3 | 0.9 |  | 43.5 | 421.5 | 224.5 | 2022-09-29 18:22
1 | B | 1 |  | 2 | STARTED |  | 351 | F0 | 351¦STRUCTURES |  | DEPOT | HF OTHER BHS | Power On | 2025-10-07 | 2025-10-15 | [5 empty] | 9.9 | 7.3 | 92.3 |  | -85 | 0.1 |  | 73.3 | 94.9 | 2.6 | 2021-07-09 12:22
1 | Y | 1 |  | 2 | STARTED |  | 601 | 9C | 915 |  | DEPOT |  | Power On | 2025-04-29 | 2025-05-06 | [5 empty] | 16 |  | 31.7 |  | -31.7 |  |  |  | 47.7 | 16 | 2023-09-28 08:06
| B | 1 |  | 2 | STARTED |  | 050 | 2 | 000¦MISC |  | DEPOT |  |  | 2024-02-26 | 2024-03-01 | [5 empty] | 1 | 0.8 | 2 | 1 | -1.3 | 0.4 | 0.8 | 75 | 2.3 | 0.3 | 2024-03-04 12:28
| B | 2 |  | 2 | STARTED |  | 601 | F6 | 601¦TAILCONE |  | DEPOT | HF PARTS | Wires Ready | 2025-02-11 | 2025-03-03 | [5 empty] | 613.5 | 360.9 | 225.2 | 613.5 | 135.7 | 1.6 | 0.6 | 58.8 | 477.8 | 252.6 | 2023-04-20 08:03
| B | 1 |  | 2 | STARTED |  | 601 | F8 | 601¦TAILCONE |  | DEPOT | HF PARTS | Wires Ready | 2025-06-24 | 2025-07-16 | [5 empty] | 2685.2 | 1118.8 | 601.2 |  | 517.6 | 1.9 |  | 41.7 | 2167.5 | 1566.3 | 2022-06-03 05:17
| B | 2 |  | 2 | STARTED |  | 451 | F9 | 451¦WHEEL WELL |  | DEPOT |  | Wires Ready | 2025-07-31 | 2025-08-13 | [5 empty] | 101.2 | 18.6 | 59.6 |  | -41 | 0.3 |  | 18.4 | 142.1 | 82.5 | 2024-02-21 08:37
| B | 1 |  | 2 | NOT STARTED |  | 401 | F7 | 401¦OSWO |  | DEPOT |  |  | 2025-05-02 | 2025-05-09 | [5 empty] | 17.4 | [7 empty] | 17.4 | 17.4
| G | 1 |  | 2 | STARTED |  | 151 | F7 | 251¦PROVISIONS |  | DEPOT |  |  | 2025-08-13 | 2025-08-21 | [5 empty] | 139.6 | 126.9 | 139.7 |  | -12.8 | 0.9 |  | 90.9 | 152.4 | 12.7 | 2024-01-23 14:06
| B | 1 |  | 2 | STARTED |  | 101 | F6 | 101¦VERIFICATION |  | DEPOT |  | Wires Ready | 2025-07-22 | 2025-08-05 | [5 empty] | 1322.3 | 1322.3 | 62.1 |  | 1260.3 | 21.3 |  | 100 | 62.1 |  | 2024-06-18 06:22
| B | 1 |  | 2 | STARTED |  | 101 | F6 | 101¦FLOORS |  | DEPOT | HF PARTS | Wires Ready | 2025-10-06 | 2025-10-09 | [5 empty] | 1667 | 1111.3 | 245 |  | 866.3 | 4.5 |  | 66.7 | 800.7 | 555.7 | 2021-12-17 05:19
1 | B | 7 |  | 2 | STARTED |  | VC351 | PZA1 | 201¦PROVISIONS |  | DEPOT | HF OTHER BHS | Wires Ready | 2024-01-30 | 2024-02-01 | [5 empty] | 44.1 | 23.3 | 284.3 | 44.1 | -261 | 0.1 | 0.5 | 52.9 | 305.1 | 20.8 | 2022-09-26 05:05
2 | B | 1 |  | 2 | STARTED |  | 351 | F8 | 351¦FLOORS |  | DEPOT |  |  | 2025-06-12 | 2025-06-23 | [5 empty] | 78.5 | 32.3 | 23.5 |  | 8.8 | 1.4 |  | 41.2 | 69.7 | 46.2 | 2025-01-16 11:27
| G | 1 |  | 2 | STARTED |  | 601 | F6 | 601¦TAILCONE |  | DEPOT |  | Wires Ready | 2025-05-28 | 2025-06-10 | [5 empty] | 466.9 | 433.6 | 43.4 |  | 390.2 | 10 |  | 92.9 | 76.8 | 33.4 | 2022-07-18 06:27
| B | 1 |  | 2 | NOT STARTED |  | 101 | XQ | 101¦OSWO |  | DEPOT |  |  | 2025-05-22 | 2025-05-29 | [5 empty] | 33 | [7 empty] | 33 | 33
| B | 1 |  | 2 | NOT STARTED |  | 551 | 4D | 551¦OSWO |  | DEPOT |  |  | 2025-06-18 | 2025-06-25 | [5 empty] | 33 | [7 empty] | 33 | 33
| B | 2 |  | 2 | STARTED |  | 401 | F8 | 401¦STRUCTURES |  | DEPOT |  | Wires Ready | 2025-06-04 | 2025-06-25 | [5 empty] | 163.7 | 46.8 | 60.8 |  | -14 | 0.8 |  | 28.6 | 177.7 | 116.9 | 2023-08-09 05:11
1 | B | 1 |  | 2 | STARTED |  | 201 | F7 | 201¦FLOORS |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-03-26 | 2025-04-10 | [5 empty] | 55.1 | 55.1 | 167.4 | 41.3 | -112.3 | 0.3 | 1.3 | 100 | 167.4 |  | 2022-06-17 06:17
| B | 1 |  | 2 | STARTED |  | 101 | 71 | 101¦FLOORS |  | DEPOT |  | Wires Ready | 2025-10-28 | 2025-10-28 | [5 empty] | 55.8 | 34.3 | 21.5 |  | 12.8 | 1.6 |  | 61.5 | 42.9 | 21.4 | 2024-11-21 06:05
1 | B | 2 |  | 2 | STARTED |  | 501 | F8 | 501¦HSTAB/VFIN |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-05-07 | 2025-05-20 | [5 empty] | 56.4 | 33.3 | 92.1 |  | -58.8 | 0.4 |  | 59.1 | 115.2 | 23.1 | 2024-08-19 05:22
2 | B | 2 |  | 2 | STARTED |  | 401 | F9 | 401¦STRUCTURES |  | DEPOT | HF PARTS | Wires Ready | 2025-07-09 | 2025-07-23 | [5 empty] | 635 | 635 | 263.8 |  | 371.1 | 2.4 |  | 100 | 263.8 |  | 2022-09-13 15:35
| G | 1 |  | 2 | STARTED |  | VC301 | PZD4 | 151¦PROVISIONS |  | DEPOT | HF OTHER BHS | Wires Ready | 2024-07-02 | 2024-07-10 | [5 empty] | 559.5 | 559.5 | 374.1 | 559.5 | 185.4 | 1.5 | 1 | 100 | 374.1 |  | 2022-09-27 07:57
1 | B | 12 |  | 2 | STARTED |  | 151 | F6 | 151¦STRUCTURES |  | DEPOT | HF PARTS | Wires Ready | 2025-06-11 | 2025-06-26 | [5 empty] | 615.3 | 615.3 | 171.1 |  | 444.1 | 3.6 |  | 100 | 171.1 |  | 2022-08-11 14:58
2 | B | 2 |  | 2 | NOT STARTED |  | 401 | F9 | 401¦STRUCTURES |  | DEPOT | HF QA | Wires Ready | 2025-07-08 | 2025-07-22 | [5 empty] | 822.1 | 822.1 | 3 |  | 819.1 | 274.1 |  | 100 | 3
| B | 1 |  | 2 | STARTED |  | 151 | F6 | 201¦PROVISIONS |  | DEPOT |  | Wires Ready | 2025-06-18 | 2025-06-19 | [5 empty] | 146.9 | 110.2 | 51.2 |  | 59 | 2.2 |  | 75 | 87.9 | 36.7 | 2022-05-17 10:05
| R | 1 |  | 2 | NOT STARTED |  | 401 | F9 | 401¦FLAME SPRAY |  | DEPOT |  | Wires Ready | 2025-08-28 | 2025-09-09 | [5 empty] | 51.1 | [7 empty] | 51.1 | 51.1
1 | B | 3 |  | 2 | STARTED |  | 401 | F9 | 401¦STRUCTURES |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-07-23 | 2025-08-06 | [5 empty] | 1077.7 | 1077.7 | 4 |  | 1073.7 | 269.4 |  | 100 | 4 |  | 2023-03-27 13:30
| B | 1 |  | 2 | STARTED |  | 401 | F9 | 401¦STRUCTURES |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-07-24 | 2025-08-07 | [5 empty] | 359.4 | 359.4 | 117.7 |  | 241.8 | 3.1 |  | 100 | 117.7 |  | 2022-08-22 08:27
| B | 1 |  | 2 | NOT STARTED |  | 551 | 4D | 551¦OSWO |  | DEPOT |  |  | 2025-07-21 | 2025-07-28 | [5 empty] | 33 | [7 empty] | 33 | 33
1 | B | 1 |  | 2 | STARTED |  | 351 | F9 | 351¦STRUCTURES |  | DEPOT | WORKABLE | Wires Ready | 2025-07-10 | 2025-07-28 | [5 empty] | 1074.3 | 1074.3 | 50.3 |  | 1024 | 21.4 |  | 100 | 50.3 |  | 2022-07-11 06:05
| B | 20 |  | 2 | STARTED |  | 551 | F9 | 551¦WINGS |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-03-25 | 2025-04-10 | [5 empty] | 638.2 | 638.2 | 79.6 | 488 | 558.6 | 8 | 1.3 | 100 | 79.6 |  | 2022-06-13 05:22
| B | 1 |  | 2 | NOT STARTED |  | 551 | 4D | 551¦OSWO |  | DEPOT |  |  | 2025-07-25 | 2025-08-01 | [5 empty] | 33 | [7 empty] | 33 | 33
2 | B | 1 |  | 2 | STARTED |  | 601 | F9 | 601¦TAILCONE |  | DEPOT | HF PARTS | Wires Ready | 2025-07-23 | 2025-09-08 | [5 empty] | 1359.3 | 1359.3 | 107.9 |  | 1251.4 | 12.6 |  | 100 | 107.9 |  | 2022-05-09 12:24
| B | 3 |  | 2 | STARTED |  | 601 | F6 | 601¦TAILCONE |  | DEPOT | HF PARTS | Wires Ready | 2025-05-29 | 2025-06-24 | [5 empty] | 2205.2 | 2205.2 | 168.4 |  | 2036.8 | 13.1 |  | 100 | 168.4 |  | 2022-05-19 11:50
| Y | 1 |  | 2 | SCHEDULED |  | 351 | DH | 915 |  | DEPOT |  | FCF | 2025-08-12 | 2025-08-19 | [5 empty] | 16 | [7 empty] | 16 | 16
1 | B | 1 |  | 2 | STARTED |  | 251 | F8 | 251¦WINDOWS |  | DEPOT |  | Wires Ready | 2025-10-08 | 2025-10-22 | [5 empty] | 371.3 | 371.3 | 81 |  | 290.3 | 4.6 |  | 100 | 81 |  | 2022-11-10 19:17
1 | B | 3 |  | 2 | NOT STARTED |  | 251 | F9 | 251¦OSWO |  | DEPOT |  | Wires Ready | 2025-07-16 | 2025-07-30 | [5 empty] | 551 | 551 |  |  | 551 |  |  | 100
| B | 2 |  | 2 | STARTED |  | 101 | F6 | 101¦STRUCTURES |  | DEPOT |  | Wires Ready | 2025-07-03 | 2025-07-15 | [5 empty] | 1150.3 | 920.3 | 374.9 |  | 545.4 | 2.5 |  | 80 | 605 | 230.1 | 2022-03-07 05:38
| B | 1 |  | 2 | STARTED |  | 151 | F8 | 151¦STRUCTURES |  | DEPOT |  | Wires Ready | 2025-05-08 | 2025-05-19 | [5 empty] | 49 | 31.5 | 69.3 |  | -37.8 | 0.5 |  | 64.3 | 86.8 | 17.5 | 2025-03-23 05:07
| B | 1 |  | 2 | ON-HOLD |  | 901 | 4Z | 915 |  | DEPOT |  |  | 2023-04-12 | 2023-04-12 | [5 empty] | 16 |  |  | 16 |  |  |  |  | 16 | 16
| R | 1 |  | 2 | ON-HOLD |  | VC551 | PD1 | 000¦SERVICE BULLETIN |  | DEPOT |  |  | 2022-12-05 | 2022-12-12 | [5 empty] | 8 |  |  | 8 |  |  |  |  | 8 | 8
| B | 1 |  | 2 | ON-HOLD |  | 601 | F6 | 601¦TAILCONE |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-02-18 | 2025-03-05 | [5 empty] | 213.6 | 115 | 20.3 | 213.6 | 94.7 | 5.7 | 0.5 | 53.8 | 118.9 | 98.6 | 2023-07-26 05:12
| G | 1 |  | 2 | ON-HOLD |  | 401 | F7 | 401¦STRUCTURES |  | DEPOT |  | Wires Ready | 2025-04-28 | 2025-06-04 | [5 empty] | 223.1 | 104.1 | 10.1 |  | 94 | 10.3 |  | 46.7 | 129.1 | 119 | 2023-03-22 05:47
| R | 1 |  | 2 | ON-HOLD |  | VC551 | PD1 | 000¦SERVICE BULLETIN |  | DEPOT |  |  | 2022-11-18 | 2022-11-23 | [5 empty] | 8 |  |  | 8 |  |  |  |  | 8 | 8
| R | 1 |  | 2 | ON-HOLD |  | VC551 | PD1 | 000¦SERVICE BULLETIN |  | DEPOT |  |  | 2022-11-18 | 2022-11-23 | [5 empty] | 8 |  |  | 8 |  |  |  |  | 8 | 8
| R | 1 |  | 2 | ON-HOLD |  | VC551 | PD1 | 000¦SERVICE BULLETIN |  | DEPOT |  |  | 2022-12-05 | 2022-12-12 | [5 empty] | 8 |  |  | 8 |  |  |  |  | 8 | 8
| G | 4 |  | 2 | ON-HOLD |  | 601 | F6 | 601¦TAILCONE |  | DEPOT | HF PARTS | Wires Ready | 2025-04-09 | 2025-04-15 | [5 empty] | 94.4 |  | 27.2 |  | -27.2 |  |  |  | 121.6 | 94.4 | 2024-06-20 12:48
| Y | 1 |  | 2 | ON-HOLD |  | VC551 | PD1 | 000¦SERVICE BULLETIN |  | DEPOT |  |  | 2022-11-26 | 2025-10-08 | [5 empty] | 8 |  | 4.6 | 6.1 | -4.6 |  |  |  | 12.6 | 8 | 2022-10-11 10:38
| Y | 1 |  | 2 | ON-HOLD |  | VC551 | PD1 | 000¦SERVICE BULLETIN |  | DEPOT |  |  | 2022-11-07 | 2022-11-14 | [5 empty] | 8 |  |  | 8 |  |  |  |  | 8 | 8
| B | 1 |  | 2 | ON-HOLD |  | 601 | F8 | 601¦OSWO |  | DEPOT |  | Wires Ready | 2026-01-22 | 2026-01-28 | [5 empty] | 116.8 | 38.9 | 22.2 |  | 16.7 | 1.8 |  | 33.3 | 100 | 77.8 | 2023-12-12 12:29
2 | B | 5 |  | 2 | ON-HOLD |  | 601 | F6 | 601¦TAILCONE |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-02-05 | 2025-02-19 | [5 empty] | 647.5 | 382.6 | 231 | 647.5 | 151.6 | 1.7 | 0.6 | 59.1 | 495.9 | 264.9 | 2022-12-20 19:23
| G | 1 |  | 2 | ON-HOLD |  | 251 | 74 | 251¦FLOOR DRILL |  | DEPOT |  | Wires Ready | 2025-05-27 | 2025-06-17 | [5 empty] | 188.4 | 101.5 | 52.1 |  | 49.4 | 1.9 |  | 53.8 | 139.1 | 87 | 2023-04-04 05:45
| G | 3 |  | 2 | ON-HOLD |  | 101 | DZ | 915 |  | DEPOT |  | FCF | 2025-08-11 | 2025-08-18 | [5 empty] | 16 | [7 empty] | 16 | 16
| G | 2 |  | 2 | ON-HOLD |  | 251 | F0 | 251¦FLOOR DRILL |  | DEPOT |  | Wires Ready | 2025-05-05 | 2025-05-27 | [5 empty] | 245 | 131.9 | 78 |  | 53.9 | 1.7 |  | 53.8 | 191.1 | 113.1 | 2023-04-10 05:47
1 | G | 1 |  | 2 | ON-HOLD |  | 251 | F0 | 251¦FLOOR DRILL |  | DEPOT |  | Wires Ready | 2025-04-09 | 2025-05-13 | [5 empty] | 424.1 | 212.1 | 132.9 |  | 79.2 | 1.6 |  | 50 | 345 | 212.1 | 2023-02-22 08:43
| B | 1 |  | 2 | ON-HOLD |  | 151 | F9 | 351¦STRUCTURES |  | DEPOT |  | Wires Ready | 2025-09-17 | 2025-09-23 | [5 empty] | 24.7 | 18.5 |  |  | 18.5 |  |  | 75 | 6.2 | 6.2
| B | 1 |  | 2 | ON-HOLD |  | 601 | 9F | 601¦TAILCONE |  | DEPOT |  | FCF | 2025-08-05 | 2025-08-12 | [5 empty] | 26.4 | [7 empty] | 26.4 | 26.4
| G | 1 |  | 2 | ON-HOLD |  | 601 | 9F | 601¦TAILCONE |  | DEPOT |  | FCF | 2025-08-07 | 2025-08-14 | [5 empty] | 26.4 | [7 empty] | 26.4 | 26.4
| R | 1 |  | 2 | ON-HOLD |  | 601 | 9C | 915 |  | DEPOT |  | Power On | 2025-04-29 | 2025-05-06 | [5 empty] | 16 | [7 empty] | 16 | 16
| B | 5 |  | 2 | ON-HOLD |  | VC601 | PZH6 | 601¦TAILCONE |  | DEPOT | HF PARTS | Wires Ready | 2024-03-04 | 2024-03-11 | [5 empty] | 671 | 279.6 | 323.7 | 671 | -44.1 | 0.9 | 0.4 | 41.7 | 715.1 | 391.4 | 2022-11-26 08:26
1 | B | 1 |  | 2 | ON-HOLD |  | 501 | F6 | 501¦HSTAB/VFIN |  | DEPOT |  | Wires Ready | 2025-03-06 | 2025-03-25 | [5 empty] | 56.4 | 22.2 | 87 | 56.4 | -64.8 | 0.3 | 0.4 | 39.3 | 121.2 | 34.2 | 2023-08-28 16:20
| B | 2 |  | 2 | ON-HOLD |  | 351 | 4F | 951 ¦ STR-DS |  | DEPOT |  |  | 2020-08-18 | 2020-08-21 | [7 empty] | 6.5 |  | -6.5 |  |  | 50 | 6.5 |  | 2022-05-30 10:45
| B | 2 |  | 2 | ON-HOLD |  | 551 | F7 | 551¦WINGS |  | DEPOT | HF PARTS | Wires Ready | 2025-04-24 | 2025-05-06 | [5 empty] | 268.4 | 244 | 111 |  | 133 | 2.2 |  | 90.9 | 135.4 | 24.4 | 2022-04-06 06:34
3 | B | 1 |  | 2 | ON-HOLD |  | 651 | F6 | 651¦FLIGHT DECK |  | DEPOT |  | Wires Ready | 2025-01-27 | 2025-01-28 | [5 empty] | 26.1 | 15 | 225.8 | 26.1 | -210.8 | 0.1 | 0.6 | 57.6 | 236.9 | 11.1 | 2022-07-07 11:28
| B | 3 |  | 2 | ON-HOLD |  | 351 | F6 | 951 ¦ STR-DS |  | DEPOT |  | Wires Ready | 2025-02-26 | 2025-03-04 | [5 empty] | 313.4 |  |  | 313.4 |  |  |  |  | 313.4 | 313.4
| B | 5 |  | 2 | ON-HOLD |  | 351 | 4F | 951 ¦ STR-DS |  | DEPOT |  |  | 2022-04-15 | 2023-03-21 | [5 empty] | 16 | 16 | 23 | 16 | -7 | 0.7 | 1 | 100 | 23 |  | 2022-04-15 11:31
| B | 1 |  | 2 | ON-HOLD |  | 401 | 4G | 951 ¦ STR-DS |  | DEPOT |  |  | 2022-04-15 | 2022-04-15 | [5 empty] | 8 | 8 | 71.9 | 8 | -63.9 | 0.1 | 1 | 100 | 71.9 |  | 2022-04-16 06:24 | 2022-05-16 13:57
| B | 2 |  | 2 | ON-HOLD |  | 401 | 4G | 951 ¦ STR-DS |  | DEPOT |  |  | 2022-04-16 | 2023-03-23 | [5 empty] | 16 | 16 | 62.7 | 16 | -46.7 | 0.3 | 1 | 100 | 62.7 |  | 2022-04-16 06:19
| B | 3 |  | 2 | ON-HOLD |  | 351 | 4F | 951 ¦ STR-GAC |  | DEPOT |  |  | 2020-08-18 | 2020-08-21 | [7 empty] | 83.2 |  | -83.2 |  |  | 50 | 83.2 |  | 2022-05-31 17:17
| B | 1 |  | 2 | ON-HOLD |  | 351 | 4F | 951 ¦ STR-GAC |  | DEPOT |  |  | 2020-08-18 | 2020-08-21 | [7 empty] | 146.3 |  | -146.3 |  |  | 66.7 | 146.3 |  | 2022-05-27 09:41
| B | 1 |  | 2 | ON-HOLD |  | 201 | 4H | 951 ¦ STR-GAC |  | DEPOT |  |  | 2020-08-18 | 2020-08-21 | [7 empty] | 42.8 |  | -42.8 |  |  | 50 | 42.8 |  | 2022-05-26 20:24
| B | 2 |  | 2 | ON-HOLD |  | 251 | XH | 951 ¦ STR-GAC |  | DEPOT | [11 empty] | 25 |  | -25 |  |  | 50 | 25 |  | 2022-05-26 21:34
| B | 2 |  | 2 | ON-HOLD |  | 201 | 4H | 951 ¦ STR-GAC |  | DEPOT | [11 empty] | 95.1 |  | -95.1 |  |  | 50 | 95.1 |  | 2022-05-24 18:17
| B | 1 |  | 2 | ON-HOLD |  | 251 | XH | 951 ¦ STR-GAC |  | DEPOT |  |  | 2020-04-03 | 2020-04-03 | [7 empty] | 35.6 |  | -35.6 |  |  | 50 | 35.6 |  | 2022-05-27 16:06
| B | 4 |  | 2 | ON-HOLD |  | 201 | 4H | 951 ¦ STR-GAC |  | DEPOT | [11 empty] | 77.5 |  | -77.5 |  |  | 50 | 77.5 |  | 2022-05-25 15:58
| B | 4 |  | 2 | ON-HOLD |  | 401 | XM | 951 ¦ STR-GAC |  | DEPOT | [11 empty] | 147.5 |  | -147.5 |  |  | 50 | 147.5 |  | 2022-05-20 09:12
| B | 1 |  | 2 | ON-HOLD |  | 101 | 4E | 951 ¦ STR-GAC |  | DEPOT | [11 empty] | 15.9 |  | -15.9 |  |  | 50 | 15.9 |  | 2022-05-25 11:24
| G | 1 |  | 2 | ON-HOLD |  | 151 | F9 | 351¦STRUCTURES |  | DEPOT |  | Wires Ready | 2025-07-29 | 2025-07-30 | [5 empty] | 39.8 | 29.8 | 23.1 |  | 6.7 | 1.3 |  | 75 | 33 | 9.9 | 2024-02-26 11:45
| G | 1 |  | 2 | ON-HOLD |  | 801 | 33 | 801¦PROVISIONS |  | DEPOT |  | Power On | 2024-08-09 | 2024-08-16 | [5 empty] | 26.4 |  | 11.3 | 26.4 | -11.3 |  |  |  | 37.7 | 26.4 | 2022-09-09 06:36
1 | Y | 2 |  | 2 | ON-HOLD |  | 251 | F0 | 251¦FLOOR DRILL |  | DEPOT |  | Wires Ready | 2025-05-28 | 2025-06-17 | [5 empty] | 455.5 | 212.6 | 59.1 |  | 153.5 | 3.6 |  | 46.7 | 302 | 242.9 | 2023-04-17 08:07
| B | 2 |  | 2 | ON-HOLD |  | 501 | F6 | 501¦HSTAB/VFIN |  | DEPOT |  | Wires Ready | 2025-02-18 | 2025-03-06 | [5 empty] | 56.4 | 24.2 | 236.7 | 56.4 | -212.5 | 0.1 | 0.4 | 42.9 | 268.9 | 32.2 | 2023-11-28 15:45
| B | 4 |  | 2 | ON-HOLD |  | 651 | F6 | 651¦FLIGHT DECK |  | DEPOT | HF PARTS | Wires Ready | 2025-02-27 | 2025-03-06 | [5 empty] | 74.1 | 74.1 | 120.3 | 74.1 | -46.2 | 0.6 | 1 | 100 | 120.3 |  | 2022-11-08 06:31
| B | 2 |  | 2 | ON-HOLD |  | 651 | F6 | 651¦FLIGHT DECK |  | DEPOT | HF PARTS | Wires Ready | 2025-02-04 | 2025-02-10 | [5 empty] | 80 | 80 | 88.9 | 80 | -8.9 | 0.9 | 1 | 100 | 88.9 |  | 2023-02-10 06:41
| B | 1 |  | 2 | CLOSED |  | 251 | 8 | 401¦SUPER PANEL |  | DEPOT | HF OTHER BHS | GFE Decrib | 2022-02-02 | 2022-02-03 | [5 empty] | 16 | 16 | 432.7 | 16 | -416.7 |  | 1 | 100 | 432.7 |  | 2020-10-29 05:37 | 2021-10-21 10:30
| B | 1 |  | 2 | CLOSED |  | 651 | 4E | 651¦FLIGHT DECK |  | DEPOT | HF PARTS | Wires Ready | 2021-11-08 | 2021-11-09 | [5 empty] | 24 | 24 | 74.8 | 24 | -50.8 | 0.3 | 1 | 100 | 74.8 |  | 2021-08-27 11:49 | 2021-11-24 12:31
| B | 1 |  | 2 | CLOSED |  | VC601 | PZH1 | 601¦GFE LOWER SHELF |  | DEPOT | HF OTHER BHS | Wires Ready | 2020-10-07 | 2020-10-07 | [5 empty] | 24 | 24 | 36.3 | 24 | -12.3 | 0.7 | 1 | 100 | 36.3 |  | 2021-07-15 06:50 | 2021-10-01 13:30
| B | 1 |  | 2 | CLOSED |  | VC401 | PZD4 | 000¦GFE COLLECTOR |  | DEPOT | HF ME |  | 2020-06-11 | 2020-10-07 | [15 empty] | 2021-10-13 10:21 | 2022-10-13 10:21
| B | 1 |  | 2 | CLOSED |  | 601 | 9B | 601¦TAILCONE |  | DEPOT |  | Wires Ready | 2020-08-18 | 2020-08-21 | [5 empty] | 16 | 16 | 29.3 | 16 | -13.3 | 0.5 | 1 | 100 | 29.3 |  | 2021-10-27 09:02 | 2021-11-06 12:30
| B | 2 |  | 2 | CLOSED |  | 601 | XW | 601¦TAILCONE |  | DEPOT | HF OTHER BHS | Wires Ready | 2020-09-10 | 2020-09-11 | [5 empty] | 22 | 22 | 69.3 | 22 | -47.3 | 0.3 | 1 | 100 | 69.3 |  | 2021-10-14 06:25 | 2021-11-30 14:27
| B | 1 |  | 2 | CLOSED |  | 601 | XW | 601¦TAILCONE |  | DEPOT | HF OTHER BHS | Wires Ready | 2021-11-08 | 2021-11-09 | [5 empty] | 11 | 11 | 106.4 | 11 | -95.4 | 0.1 | 1 | 100 | 106.4 |  | 2021-12-06 11:34 | 2022-03-30 21:38
| B | 1 |  | 2 | CLOSED |  | 251 | DZ | 251¦FLOOR DRILL |  | DEPOT |  | Wires Ready | 2023-01-04 | 2023-01-11 | [5 empty] | 40.8 | 40.8 | 49 | 40.8 | -8.2 | 0.8 | 1 | 100 | 49 |  | 2023-04-14 06:51 | 2023-04-27 05:35
| B | 1 |  | 2 | CLOSED |  | 601 | XW | 601¦TAILCONE |  | DEPOT | HF OTHER BHS | Wires Ready | 2020-09-09 | 2020-09-09 | [5 empty] | 10 | 10 | 37.2 | 10 | -27.2 | 0.3 | 1 | 100 | 37.2 |  | 2021-10-27 21:50 | 2021-12-04 10:01
| B | 2 |  | 2 | CLOSED |  | 300 | 1 | 451¦FIRE SUPPRESSION |  | DEPOT |  | FCF | 2020-08-18 | 2020-08-21 | [5 empty] | 16 | 16 | 30.8 | 16 | -14.8 | 0.5 | 1 | 100 | 30.8 |  | 2021-03-24 05:39 | 2021-05-10 19:51
| B | 18 |  | 2 | CLOSED |  | 050 | 28 | 000¦COLLECTOR |  | DEPOT | HF OTHER BHS |  | 2020-01-20 | 2020-10-07 | [12 empty] | 100 |  |  | 2020-01-31 09:00 | 2022-11-15 18:11
| B | 1 |  | 2 | CLOSED |  | 251 | 4J | 251¦INT STRUCTURES |  | DEPOT |  | Wires Ready | 2022-10-17 | 2022-10-21 | [5 empty] | 54.1 | 54.1 | 97.9 | 54.1 | -43.8 | 0.6 | 1 | 100 | 97.9 |  | 2022-09-09 21:24 | 2023-04-10 09:18
| B | 1 |  | 2 | CLOSED |  | 101 | DZ | 101¦STRUCTURES |  | DEPOT |  | Wires Ready | 2023-03-17 | 2023-03-23 | [5 empty] | 26.1 | 26.1 | 228.5 | 26.1 | -202.4 | 0.1 | 1 | 100 | 228.5 |  | 2023-02-15 19:09 | 2023-04-17 22:20
| B | 1 |  | 2 | CLOSED |  | VC201 | PZA1 | 201¦GFE WIRE PROV |  | DEPOT | WORKABLE | Wires Ready | 2023-04-04 | 2023-04-10 | [5 empty] | 31.3 | 31.3 | 443.9 | 31.3 | -412.6 | 0.1 | 1 | 100 | 443.9 |  | 2020-12-14 07:41 | 2023-02-07 13:04
| B | 1 |  | 2 | CLOSED |  | 251 | DH | 251¦FLOORS |  | DEPOT | HF OTHER BHS | Wires Ready | 2021-10-26 | 2021-10-27 | [5 empty] | 16 | 16 | 11 | 16 | 5 | 1.5 | 1 | 100 | 11 |  | 2021-10-16 05:32 | 2021-10-16 12:01
| B | 1 |  | 2 | CLOSED |  | 401 | XM | 401¦BRACKET |  | DEPOT | HF ENG | Wires Ready | 2020-06-06 | 2020-06-08 | [5 empty] | 23.6 | 23.6 | 89.5 | 23.6 | -65.9 | 0.3 | 1 | 100 | 89.5 |  | 2021-02-01 19:43 | 2022-09-15 09:15
| B | 1 |  | 2 | CLOSED |  | 351 | XK | 351¦PROVISIONS |  | DEPOT | WORKABLE | Wires Ready | 2022-11-11 | 2022-11-16 | [5 empty] | 54.1 | 54.1 | 99.9 | 54.1 | -45.8 | 0.5 | 1 | 100 | 99.9 |  | 2021-02-19 16:15 | 2022-12-07 23:18
| B | 1 |  | 2 | CLOSED |  | 351 | XK | 351¦PROVISIONS |  | DEPOT | WORKABLE | Wires Ready | 2022-11-22 | 2022-11-29 | [5 empty] | 47.6 | 47.6 | 82.7 | 47.6 | -35.1 | 0.6 | 1 | 100 | 82.7 |  | 2021-03-17 23:00 | 2023-03-15 18:39
| B | 1 |  | 2 | CLOSED |  | 100 | 7 | 551¦ENGINE MODS |  | DEPOT |  | FCF | 2024-02-16 | 2024-02-21 | [5 empty] | 16 | 16 | 16.4 | 16 | -0.4 | 1 | 1 | 100 | 16.4 |  | 2024-02-27 06:15 | 2024-03-25 14:54
| B | 1 |  | 2 | CLOSED |  | 200 | 4 | 101¦PROVISIONS |  | DEPOT | WORKABLE | Power On | 2020-06-10 | 2020-06-10 | [5 empty] | 12 | 12 | 97.2 | 12 | -85.2 | 0.1 | 1 | 100 | 97.2 |  | 2020-12-21 12:14 | 2021-03-17 10:43
| B | 2 |  | 2 | CLOSED |  | 120 | 1 | 351¦BREATHER GAPS |  | DEPOT | HF ENG | Decrib | 2020-04-29 | 2020-04-29 | [5 empty] | 8 | 8 | 111.7 | 8 | -103.7 | 0.1 | 1 | 100 | 111.7 |  | 2020-08-21 15:22 | 2021-01-26 23:55
| B | 1 |  | 2 | CLOSED |  | 351 | 4F | 351¦FWD BG |  | DEPOT | HF OTHER BHS | GFE Decrib | 2020-09-14 | 2020-09-14 | [5 empty] | 16 | 16 | 130.5 | 16 | -114.5 | 0.1 | 1 | 100 | 130.5 |  | 2021-06-03 05:50 | 2021-08-27 15:02
| B | 1 |  | 2 | CLOSED |  | 200 | 2 | 401¦FWD BG |  | DEPOT | IN WORK | Power On | 2021-05-20 | 2021-05-21 | [5 empty] | 64 | 64 | 369.9 | 64 | -305.9 | 0.2 | 1 | 100 | 369.9 |  | 2021-01-25 15:50 | 2021-05-11 22:50
| B | 1 |  | 2 | CLOSED |  | 801 | XP | 801¦PROVISIONS |  | DEPOT | HF PARTS | Wires Ready | 2021-12-20 | 2021-12-22 | [5 empty] | 32 | 32 | 82.1 | 32 | -50.1 | 0.4 | 1 | 100 | 82.1 |  | 2021-12-10 07:06 | 2021-12-20 15:28
| B | 1 |  | 2 | CLOSED |  | 351 | AA | 351¦FWD BG |  | DEPOT | HF OTHER BHS | GFE Decrib | 2021-04-08 | 2021-04-09 | [5 empty] | 16 | 16 | 204.5 | 16 | -188.5 | 0.1 | 1 | 100 | 204.5 |  | 2021-03-29 20:59 | 2021-07-21 09:29
| B | 1 |  | 2 | CLOSED |  | VC351 | PZA1 | 201¦PROVISIONS |  | DEPOT | WORKABLE | Wires Ready | 2022-06-22 | 2022-06-24 | [5 empty] | 16 | 16 | 86.5 | 16 | -70.5 | 0.2 | 1 | 100 | 86.5 |  | 2021-12-08 14:36 | 2022-05-28 10:40
2 | B | 1 |  | 2 | CLOSED |  | 651 | 16 | 651¦FLIGHT DECK |  | DEPOT |  | Wires Ready | 2022-04-25 | 2022-04-28 | [5 empty] | 17.6 | 17.6 | 127.6 | 17.6 | -110 | 0.1 | 1 | 100 | 127.6 |  | 2022-08-22 11:38 | 2022-09-28 07:49
| B | 4 |  | 2 | CLOSED |  | 601 | XW | 601¦TAILCONE |  | DEPOT | HF PARTS | Wires Ready | 2020-09-14 | 2020-09-14 | [5 empty] | 22 | 22 | 155.9 | 22 | -133.9 | 0.1 | 1 | 100 | 155.9 |  | 2021-06-04 12:45 | 2021-12-01 01:01
| B | 1 |  | 2 | CLOSED |  | 351 | AA | 551¦WINGS |  | DEPOT |  | Wires Ready | 2021-01-07 | 2021-01-08 | [5 empty] | 20 | 20 | 2.4 | 20 | 17.6 | 8.3 | 1 | 100 | 2.4 |  | 2021-01-06 11:37 | 2022-01-29 12:55
| B | 1 |  | 2 | CLOSED |  | 200 | 4 | 301¦FLOORS |  | DEPOT | HF PARTS | GFE Decrib | 2021-03-12 | 2021-03-15 | [5 empty] | 32 | 32 | 138.7 | 32 | -106.7 | 0.2 | 1 | 100 | 138.7 |  | 2021-03-15 10:26 | 2021-03-27 12:52
| B | 1 |  | 2 | CLOSED |  | 101 | DZ | 101¦FLOORS |  | DEPOT |  | Wires Ready | 2023-03-07 | 2023-03-08 | [5 empty] | 26.9 | 26.9 | 98.2 | 26.9 | -71.3 | 0.3 | 1 | 100 | 98.2 |  | 2022-12-06 20:49 | 2023-04-04 20:02
| B | 2 |  | 2 | CLOSED |  | 200 | 1 | 351¦FWD BG |  | DEPOT | HF ENG | GFE Decrib | 2021-05-12 | 2021-05-13 | [5 empty] | 16 | 16 | 131.2 | 16 | -115.2 | 0.1 | 1 | 100 | 131.2 |  | 2021-01-05 18:39 | 2021-06-02 11:49
| B | 4 |  | 2 | CLOSED |  | 200 | 7 | 601¦TAILCONE |  | DEPOT | HF PARTS | Tailcone | 2020-08-14 | 2020-08-17 | [5 empty] | 16 | 16 |  | 16 | 16 |  | 1 | 100 |  |  | 2021-04-19 14:53 | 2021-06-02 14:53
| B | 1 |  | 2 | CLOSED |  | VC351 | PZA1 | 351¦FWD BG |  | DEPOT | WORKABLE | GFE Decrib | 2021-04-30 | 2021-04-30 | [5 empty] | 16 | 16 | 458.6 | 16 | -442.6 |  | 1 | 100 | 458.6 |  | 2020-08-28 05:40 | 2021-06-29 06:58
1 | B | 1 |  | 2 | CLOSED |  | 401 | XM | 401¦STRUCTURES |  | DEPOT | HF ENG | Wires Ready | 2021-05-10 | 2021-05-12 | [5 empty] | 10 | 10 | 131.6 | 10 | -121.6 | 0.1 | 1 | 100 | 131.6 |  | 2021-01-21 16:22 | 2022-05-20 12:18
| B | 1 |  | 2 | CLOSED |  | VC551 | PD1 |  |  | DEPOT |  |  | 2022-06-17 | 2022-06-17 | [5 empty] | 8 | 8 | 10 | 8 | -2 | 0.8 | 1 | 100 | 10 |  | 2022-07-15 06:41 | 2022-07-26 09:59
| B | 1 |  | 2 | CLOSED |  | 651 | JF | 651¦FLIGHT DECK |  | DEPOT |  | Wires Ready | 2022-11-11 | 2022-11-16 | [5 empty] | 39.3 | 39.3 | 80.9 | 39.3 | -41.6 | 0.5 | 1 | 100 | 80.9 |  | 2022-05-12 07:46 | 2023-03-30 09:02
| B | 1 |  | 2 | CLOSED |  | 801 | 4F | 801¦PROVISIONS |  | DEPOT |  | Wires Ready | [7 empty] | 40 | 40 | 15 |  | 25 | 2.7 |  | 100 | 15 |  | 2021-10-15 15:33 | 2022-01-26 10:54
| B | 1 |  | 2 | CLOSED |  | 401 | AB | 401¦FWD BG |  | DEPOT | HF PARTS | GFE Decrib | 2021-04-16 | 2021-04-19 | [5 empty] | 56 | 56 | 148.9 | 56 | -92.9 | 0.4 | 1 | 100 | 148.9 |  | 2021-05-14 19:44 | 2021-08-04 15:09
| B | 1 |  | 2 | CLOSED |  | 050 | 3 | 000¦ARRIVAL |  | DEPOT | IN WORK |  | 2019-06-03 | 2019-06-04 | [5 empty] | 16 | 16 | 22.1 | 16 | -6.1 | 0.7 | 1 | 100 | 22.1 |  | 2019-05-30 05:19 | 2019-06-24 12:58
| B | 1 |  | 2 | CLOSED |  | 120 | 8 | 401¦SUPER PANEL |  | DEPOT | HF OTHER BHS | Wires Ready | 2020-06-01 | 2020-06-01 | [5 empty] | 16 | 16 | 0.2 | 16 | 15.8 | 80 | 1 | 100 | 0.2 |  | 2020-05-26 06:00 | 2020-06-10 12:02
| B | 1 |  | 2 | CLOSED |  | 120 | 8 | 401¦SUPER PANEL |  | DEPOT | HF ENG | Decrib | 2020-05-15 | 2020-05-18 | [5 empty] | 16 | 16 | 138.4 | 16 | -122.4 | 0.1 | 1 | 100 | 138.4 |  | 2020-10-28 13:01 | 2021-01-25 05:39
| B | 1 |  | 2 | CLOSED |  | 050 | 8 | 000¦050 REMOVALS |  | DEPOT |  |  | 2020-02-19 | 2020-02-19 | [5 empty] | 8 | 8 | 5.8 | 8 | 2.2 | 1.4 | 1 | 100 | 5.8 |  | 2020-02-18 06:55 | 2020-02-18 12:55
| B | 1 |  | 2 | CLOSED |  | 200 | 7 | 851¦TAILCONE |  | DEPOT | IN WORK | Tailcone | 2020-06-16 | 2020-06-17 | [5 empty] | 48 | 48 | 77.4 | 48 | -29.4 | 0.6 | 1 | 100 | 77.4 |  | 2020-10-02 05:33 | 2021-03-17 23:57
| B | 2 |  | 2 | CLOSED |  | 100 | 3 | 351¦FIRE SUPPRESSION |  | DEPOT | HF ENG | Power On | 2020-04-07 | 2020-04-07 | [5 empty] | 16 | 16 | 10.6 | 16 | 5.4 | 1.5 | 1 | 100 | 10.6 |  | 2020-04-07 05:22 | 2020-04-30 08:25
| B | 1 |  | 2 | CLOSED |  | VC601 | PZH2 |  |  | DEPOT | HF OTHER BHS | Tailcone | 2020-07-23 | 2020-07-24 | [5 empty] | 16 | 16 | 13 | 16 | 3 | 1.2 | 1 | 100 | 13 |  | 2021-03-19 06:40 | 2021-04-09 11:50
| B | 1 |  | 2 | CLOSED |  | 100 | 8 | 401¦SUPER PANEL |  | DEPOT |  | Wires Ready | 2020-03-12 | 2020-03-12 | [5 empty] | 6 | 6 | 24 | 6 | -18 | 0.3 | 1 | 100 | 24 |  | 2020-03-10 05:17 | 2020-03-23 07:48
| B | 1 |  | 2 | CLOSED |  | 200 | 1 | 351¦STAIRS |  | DEPOT | HF OTHER BHS | Wires Ready | 2020-06-19 | 2020-06-21 | [5 empty] | 32 | 32 | 8.4 | 32 | 23.6 | 3.8 | 1 | 100 | 8.4 |  | 2020-10-31 05:09 | 2020-11-02 12:29
| B | 1 |  | 2 | CLOSED |  | 200 | 51 | 351¦BREATHER GAPS |  | DEPOT | HF OTHER BHS | Wires Ready | 2020-06-01 | 2020-06-01 | [5 empty] | 16 | 16 | 35.9 | 16 | -19.9 | 0.4 | 1 | 100 | 35.9 |  | 2020-10-23 15:48 | 2020-11-06 23:37
| B | 1 |  | 2 | CLOSED |  | 200 | 2 | 401¦BREATHER GAPS |  | DEPOT | WORKABLE | Decrib | 2020-09-22 | 2020-09-22 | [5 empty] | 12 | 12 | 127.9 | 12 | -115.9 | 0.1 | 1 | 100 | 127.9 |  | 2021-02-03 06:35 | 2021-02-13 12:05
| B | 1 |  | 2 | CLOSED |  | 200 | 1 | 351¦STAIRS |  | DEPOT | WORKABLE | Decrib | 2020-06-09 | 2020-06-10 | [5 empty] | 12 | 12 | 82.2 | 12 | -70.2 | 0.1 | 1 | 100 | 82.2 |  | 2020-10-09 05:28 | 2020-10-19 13:38
| B | 1 |  | 2 | CLOSED |  | 120 | 9 | 501¦TAILCONE |  | DEPOT | WORKABLE | Tailcone | 2020-05-13 | 2020-05-13 | [5 empty] | 16 | 16 | 80.1 | 16 | -64.1 | 0.2 | 1 | 100 | 80.1 |  | 2020-07-25 04:56 | 2020-08-12 08:12
| B | 1 |  | 2 | CLOSED |  | 151 | XC | 151¦STRUCTURES |  | DEPOT | WORKABLE | Wires Ready | 2020-03-30 | 2020-03-31 | [5 empty] | 16 | 16 | 113.9 | 16 | -97.9 | 0.1 | 1 | 100 | 113.9 |  | 2020-07-06 10:07 | 2022-05-27 13:19
| B | 1 |  | 2 | CLOSED |  | 151 | XC | 301¦FLOORS |  | DEPOT |  | Wires Ready | 2023-01-10 | 2023-01-17 | [5 empty] | 34.4 | 34.4 | 77.8 | 34.4 | -43.4 | 0.4 | 1 | 100 | 77.8 |  | 2022-07-19 05:56 | 2023-03-21 12:52
| B | 1 |  | 2 | CLOSED |  | 601 | XW | 601¦TAILCONE |  | DEPOT |  | Wires Ready | 2023-02-01 | 2023-02-03 | [5 empty] | 36.7 | 36.7 | 57.9 | 36.7 | -21.2 | 0.6 | 1 | 100 | 57.9 |  | 2021-07-28 12:16 | 2023-03-08 22:03
| B | 1 |  | 2 | CLOSED |  | 251 | XI | 251¦FLOOR MOD |  | DEPOT | HF PARTS | Wires Ready | 2023-02-02 | 2023-02-09 | [5 empty] | 36.7 | 36.7 | 144 | 36.7 | -107.3 | 0.3 | 1 | 100 | 144 |  | 2021-04-28 18:56 | 2022-12-16 13:35
| B | 2 |  | 2 | CLOSED |  | 200 | 2 | 401¦FWD BG |  | DEPOT | IN WORK | GFE Decrib | 2021-05-18 | 2021-05-20 | [5 empty] | 16 | 16 | 200.7 | 16 | -184.7 | 0.1 | 1 | 100 | 200.7 |  | 2021-01-04 15:53 | 2021-05-19 00:54
| B | 1 |  | 2 | CLOSED |  | 351 | XK | 351¦BRACKETS |  | DEPOT | HF PARTS | Wires Ready | 2023-01-03 | 2023-01-06 | [5 empty] | 10.6 | 10.6 | 181.3 | 10.6 | -170.7 | 0.1 | 1 | 100 | 181.3 |  | 2022-01-31 06:12 | 2022-11-07 13:37
| B | 2 |  | 2 | CLOSED |  | 601 | XW | 601¦TAILCONE |  | DEPOT | HF OTHER BHS | Wires Ready | 2022-09-30 | 2022-10-04 | [5 empty] | 17.6 | 17.6 | 68.1 | 17.6 | -50.5 | 0.3 | 1 | 100 | 68.1 |  | 2022-07-21 10:18 | 2022-10-06 14:55
| B | 1 |  | 2 | CLOSED |  | 351 | XK | 351¦STRUCTURES |  | DEPOT | WORKABLE | Wires Ready | 2020-04-03 | 2020-04-06 | [5 empty] | 22 | 22 | 146.1 | 22 | -124.1 | 0.2 | 1 | 100 | 146.1 |  | 2020-07-17 10:15 | 2022-08-05 09:38
| B | 1 |  | 2 | CLOSED |  | 351 | XK | 351¦PROVISIONS |  | DEPOT | IN WORK | Wires Ready | 2021-07-28 | 2021-07-29 | [5 empty] | 26.4 | 26.4 | 111.9 | 26.4 | -85.5 | 0.2 | 1 | 100 | 111.9 |  | 2021-01-20 10:09 | 2022-08-12 13:19
| B | 1 |  | 2 | CLOSED |  | 101 | 4S | 101¦PROVISIONS |  | DEPOT |  | Wires Ready | 2020-04-03 | 2020-04-03 | [5 empty] | 24 | 24 | 117.4 | 24 | -93.4 | 0.2 | 1 | 100 | 117.4 |  | 2021-12-21 05:28 | 2022-05-25 12:42
| B | 1 |  | 2 | CLOSED |  | 351 | XK | 351¦PROVISIONS |  | DEPOT |  | Wires Ready | 2021-10-04 | 2021-10-04 | [5 empty] | 26.4 | 26.4 | 61.4 | 26.4 | -35 | 0.4 | 1 | 100 | 61.4 |  | 2021-10-12 12:09 | 2022-08-03 13:46
| B | 1 |  | 2 | CLOSED |  | 351 | AA | 351¦PROVISIONS |  | DEPOT |  | Power On | 2023-02-06 | 2023-02-10 | [5 empty] | 26.4 | 26.4 | 21.7 | 26.4 | 4.7 | 1.2 | 1 | 100 | 21.7 |  | 2023-01-04 14:05 | 2023-04-10 22:08
| B | 1 |  | 2 | CLOSED |  | 401 | XM | 401¦PROVISIONS |  | DEPOT | HF OTHER BHS | Wires Ready | 2020-10-20 | 2020-10-20 | [5 empty] | 8 | 8 | 17 | 8 | -9 | 0.5 | 1 | 100 | 17 |  | 2022-05-18 06:22 | 2022-05-20 09:42
| B | 23 |  | 2 | CLOSED |  | 050 | 8 | 801¦PROVISIONS |  | DEPOT | HF DESIGN |  | 2019-04-24 | 2020-06-12 | [12 empty] | 100 |  |  |  | 2022-03-08 17:36
| B | 1 |  | 2 | CLOSED |  | 201 | XF | 201¦PROVISIONS |  | DIS |  |  | 2022-03-04 | 2022-03-04 |  |  |  |  | Item 1)Blend out noted scratches along indicated surface at a minimum 20:1 width to depth ratio. Depth of blend not to exceed .003. Blend in accordance with BAC5300-1 Section 8.4 REWORK and BAC5748 Type II Class 5. Maintain minimum 1.0R at the base of the blend. Break sharp edges per BAC5300. Maintain 125RHR or better surface finish per BACD2097. Penetrant inspect reworked area per BAC5423.Do not apply Alodine or primer at this time.QA to measure amount of blend and RESUBMIT to Engineering with depth of blend for further review.E-UM review not required. |  |  | 5.8 |  | -5.8 |  |  | 100 | 5.8 |  | 2022-03-08 09:10 | 2022-03-11 13:51
| B | 1 |  | 2 | CLOSED |  | 251 | 4J | 251¦PROVISIONS |  | DEPOT |  | Wires Ready | 2021-11-29 | 2021-11-29 | [5 empty] | 24 | 24 | 94.4 | 24 | -70.4 | 0.3 | 1 | 100 | 94.4 |  | 2022-03-01 08:27 | 2022-03-17 11:50
| B | 2 |  | 2 | CLOSED |  | 401 | XM | 401¦STRUCTURES |  | DEPOT | HF OTHER BHS | Wires Ready | 2021-03-15 | 2021-03-16 | [5 empty] | 22 | 22 | 141.9 | 22 | -119.9 | 0.2 | 1 | 100 | 141.9 |  | 2021-03-25 05:36 | 2022-06-04 09:25
| B | 1 |  | 2 | CLOSED |  | 351 | XK | 351¦FLOORS |  | DEPOT |  | Wires Ready | 2021-04-23 | 2021-04-26 | [5 empty] | 22 | 22 | 37.5 | 22 | -15.5 | 0.6 | 1 | 100 | 37.5 |  | 2021-12-20 08:56 | 2022-04-12 13:30
| B | 1 |  | 2 | CLOSED |  | 451 | 45 | 451¦WHEEL WELL |  | DEPOT |  | Wires Ready | 2023-04-04 | 2023-04-07 | [5 empty] | 17.6 | 17.6 | 19.8 | 17.6 | -2.2 | 0.9 | 1 | 100 | 19.8 |  | 2022-08-30 06:03 | 2022-10-22 12:50
| B | 1 |  | 2 | CLOSED |  | 401 | 4G | 401¦FWD BG |  | DEPOT | WORKABLE | Power On | 2021-05-17 | 2021-05-18 | [5 empty] | 16 | 16 | 123.8 | 16 | -107.8 | 0.1 | 1 | 100 | 123.8 |  | 2021-03-11 19:19 | 2021-09-27 18:23
| B | 1 |  | 2 | CLOSED |  | 401 | AB | 401¦FWD BG |  | DEPOT | HF PARTS | GFE Decrib | 2021-03-25 | 2021-03-26 | [5 empty] | 48 | 48 | 216.9 | 48 | -168.9 | 0.2 | 1 | 100 | 216.9 |  | 2021-02-19 16:02 | 2021-07-03 09:56
| B | 2 |  | 2 | CLOSED |  | 351 | XK | 351¦PROVISIONS |  | DEPOT | WORKABLE | Wires Ready | 2021-07-23 | 2021-07-26 | [5 empty] | 26.4 | 26.4 | 181.6 | 26.4 | -155.2 | 0.1 | 1 | 100 | 181.6 |  | 2021-03-18 16:09 | 2022-08-09 14:37
| B | 1 |  | 2 | CLOSED |  | 151 | XC | 151¦REMOVALS |  | DEPOT |  | Wires Ready | 2021-12-03 | 2021-12-07 | [5 empty] | 16 | 16 | 17.7 | 16 | -1.7 | 0.9 | 1 | 100 | 17.7 |  | 2022-03-24 06:46 | 2022-06-13 13:03
| B | 1 |  | 2 | CLOSED |  | 101 | 4E | 101¦STRUCTURES |  | DEPOT |  | Wires Ready | 2020-04-03 | 2022-03-17 | [5 empty] | 9.9 | 9.9 | 80 | 9.9 | -70.1 | 0.1 | 1 | 100 | 80 |  | 2022-05-31 06:39 | 2022-07-12 09:53
| B | 1 |  | 2 | CLOSED |  | 601 | XW | 601¦TAILCONE |  | DEPOT | HF OTHER BHS | Wires Ready | 2021-11-13 | 2021-11-15 | [5 empty] | 11 | 11 | 78 | 11 | -67 | 0.1 | 1 | 100 | 78 |  | 2022-04-28 07:46 | 2022-06-13 10:05
| B | 1 |  | 2 | CLOSED |  | 601 | XW | 601¦TAILCONE |  | DEPOT | HF PARTS | Wires Ready | 2021-11-08 | 2021-11-09 | [5 empty] | 22 | 22 | 164 | 22 | -142 | 0.1 | 1 | 100 | 164 |  | 2021-04-03 10:37 | 2022-01-10 14:18
| B | 1 |  | 2 | CLOSED |  | VC601 | PZH4 | 601¦GFE TAILCONE |  | DEPOT | HF PARTS | Wires Ready | 2020-09-03 | 2020-09-03 | [5 empty] | 16 | 16 | 156.4 | 16 | -140.4 | 0.1 | 1 | 100 | 156.4 |  | 2021-12-06 05:47 | 2021-12-22 05:57
| B | 1 |  | 2 | CLOSED |  | 100 | 3 | 351¦ECS |  | DEPOT |  | Wires Ready | 2020-03-27 | 2020-03-30 | [5 empty] | 22 | 22 | 54.7 | 22 | -32.7 | 0.4 | 1 | 100 | 54.7 |  | 2020-04-01 08:51 | 2022-09-23 08:14
| B | 1 |  | 2 | CLOSED |  | 601 | 9A | 601¦TAILCONE |  | DEPOT | HF PARTS | Wires Ready | [7 empty] | 10 | 10 | 64.3 |  | -54.3 | 0.2 |  | 100 | 64.3 |  | 2021-10-20 13:01 | 2021-10-28 12:00
| B | 1 |  | 2 | CLOSED |  | VC201 | PZB2 | 201¦GFE WIRE PROV |  | DEPOT | HF AHS | Wires Ready | 2022-03-25 | 2022-03-30 | [5 empty] | 22 | 22 | 144.1 | 22 | -122.1 | 0.2 | 1 | 100 | 144.1 |  | 2021-10-22 05:40 | 2022-08-05 08:55
| B | 1 |  | 2 | CLOSED |  | 151 | XD | 151¦STRUCTURES |  | DEPOT | HF PARTS | Wires Ready | 2021-04-06 | 2021-04-07 | [5 empty] | 22 | 22 | 118.5 | 22 | -96.5 | 0.2 | 1 | 100 | 118.5 |  | 2021-06-14 16:06 | 2022-08-03 12:40
| B | 2 |  | 2 | CLOSED |  | 201 | DZ | 201¦FLOORS |  | DEPOT |  | Wires Ready | 2022-11-18 | 2022-11-22 | [5 empty] | 40.8 | 40.8 | 214.3 | 40.8 | -173.5 | 0.2 | 1 | 100 | 214.3 |  | 2022-08-18 19:03 | 2023-06-06 13:35
| B | 1 |  | 2 | CLOSED |  | 251 | 4J | 251¦PROVISIONS |  | DEPOT |  | Wires Ready | 2023-01-18 | 2023-01-25 | [5 empty] | 44.1 | 44.1 | 121.6 | 44.1 | -77.5 | 0.4 | 1 | 100 | 121.6 |  | 2022-10-25 21:45 | 2023-06-07 14:20
| B | 2 |  | 2 | CLOSED |  | 050 | 5 | 000¦050 REMOVALS |  | DEPOT | WORKABLE |  | 2019-07-31 | 2019-08-01 | [5 empty] | 54 | 54 | 32.1 | 54 | 21.9 | 1.7 | 1 | 100 | 32.1 |  | 2019-08-07 06:38 | 2019-08-14 13:46
| B | 1 |  | 2 | CLOSED |  | 351 | PSP | 351¦PROVISIONS |  | DEPOT | [9 empty] | 12 | 12 | 42.2 |  | -30.2 | 0.3 |  | 100 | 42.2 |  | 2024-01-09 12:00 | 2024-01-12 12:52
| B | 1 |  | 2 | CLOSED |  | 601 | XW | 601¦TAILCONE |  | DEPOT | HF OTHER BHS | Wires Ready | 2023-01-26 | 2023-01-30 | [5 empty] | 29.3 | 29.3 | 116 | 29.3 | -86.7 | 0.3 | 1 | 100 | 116 |  | 2022-05-02 05:23 | 2023-06-15 12:31
| B | 2 |  | 2 | CLOSED |  | 351 | XK | 351¦PROVISIONS |  | DEPOT | WORKABLE | Wires Ready | 2022-10-17 | 2022-10-20 | [5 empty] | 54.1 | 54.1 | 236.9 | 54.1 | -182.8 | 0.2 | 1 | 100 | 236.9 |  | 2020-12-14 21:18 | 2023-03-03 14:17
| B | 1 |  | 2 | CLOSED |  | 601 | XW | 601¦TAILCONE |  | DEPOT | HF OTHER BHS | Wires Ready | 2021-12-10 | 2021-12-11 | [5 empty] | 22 | 22 | 130.5 | 22 | -108.5 | 0.2 | 1 | 100 | 130.5 |  | 2022-06-04 05:19 | 2022-06-25 10:44
| B | 1 |  | 2 | CLOSED |  | 251 | W4 | 251¦WINDOWS |  | DEPOT | HF PARTS | Wires Ready | 2023-04-03 | 2023-04-04 | [5 empty] | 21.1 | 21.1 | 48.2 | 21.1 | -27.1 | 0.4 | 1 | 100 | 48.2 |  | 2022-12-06 21:57 | 2023-01-21 19:40
| B | 1 |  | 2 | CLOSED |  | 351 | 4F | 351¦BRACKETS |  | DEPOT | HF OTHER BHS | Power On | 2023-01-12 | 2023-01-17 | [5 empty] | 9 | 9 | 26.5 | 9 | -17.5 | 0.3 | 1 | 100 | 26.5 |  | 2022-05-06 20:41 | 2022-10-31 23:18
| B | 1 |  | 2 | CLOSED |  | 351 | XK | 351¦PROVISIONS |  | DEPOT | WORKABLE | Wires Ready | 2022-11-11 | 2022-11-16 | [5 empty] | 11.9 | 11.9 | 192.1 | 11.9 | -180.2 | 0.1 | 1 | 100 | 192.1 |  | 2021-02-19 16:12 | 2022-11-05 09:59
| B | 1 |  | 2 | CLOSED |  | 251 | XI | 251¦FLOOR MOD |  | DEPOT | HF PARTS | Wires Ready | 2023-03-14 | 2023-03-21 | [5 empty] | 36.7 | 36.7 | 79.8 | 36.7 | -43.1 | 0.5 | 1 | 100 | 79.8 |  | 2022-10-18 08:30 | 2023-02-25 13:01
| B | 1 |  | 2 | CLOSED |  | 351 | 4F | 351¦PROVISIONS |  | DEPOT |  | Wires Ready | 2022-12-22 | 2022-12-22 | [5 empty] | 26.4 | 26.4 | 91.7 | 26.4 | -65.3 | 0.3 | 1 | 100 | 91.7 |  | 2023-01-04 16:10 | 2023-01-31 15:01
| B | 1 |  | 2 | CLOSED |  | 351 | 4T | 351¦BRACKETS |  | DEPOT |  | Wires Ready | 2022-12-07 | 2022-12-12 | [5 empty] | 10.6 | 10.6 | 24.1 | 10.6 | -13.5 | 0.4 | 1 | 100 | 24.1 |  | 2022-08-30 17:17 | 2022-10-17 22:58
| B | 1 |  | 2 | CLOSED |  | VC351 | PZA5 | 351¦STRUCTURES |  | DEPOT | HF OTHER BHS | Wires Ready | 2022-11-15 | 2022-11-18 | [5 empty] | 45 | 45 | 40 | 45 | 5 | 1.1 | 1 | 100 | 40 |  | 2023-01-13 06:34 | 2023-02-22 22:37
| B | 1 |  | 2 | CLOSED |  | 401 | F2 | 401¦STRUCTURES |  | DEPOT | HF PARTS | Wires Ready | 2024-05-16 | 2024-05-29 | [5 empty] | 45 | 45 | 63.1 | 45 | -18.1 | 0.7 | 1 | 100 | 63.1 |  | 2020-09-19 05:32 | 2024-06-04 10:14
1 | B | 1 |  | 2 | CLOSED |  | VC801 | PZA2 | 801¦OSWO |  | DEPOT |  | Wires Ready | 2024-06-13 | 2024-06-25 | [5 empty] | 489.8 | 489.8 |  | 489.8 | 489.8 |  | 1 | 100 |  |  |  | 2024-10-22 10:17
| B | 1 |  | 2 | CLOSED |  | VC601 | PZH6 | 601¦TAILCONE |  | DEPOT | HF PARTS | Wires Ready | 2023-05-09 | 2023-05-10 | [5 empty] | 26.1 | 26.1 | 77.8 | 26.1 | -51.8 | 0.3 | 1 | 100 | 77.8 |  | 2022-11-26 11:07 | 2024-01-23 12:24
| B | 4 |  | 2 | CLOSED |  | VC601 | PZH4 | 601¦TAILCONE |  | DEPOT | HF OTHER BHS | Wires Ready | 2024-09-25 | 2024-10-01 | [5 empty] | 47.5 | 47.5 | 16.5 | 47.5 | 31 | 2.9 | 1 | 100 | 16.5 |  | 2024-09-09 05:44 | 2024-09-12 09:17
2 | B | 1 |  | 2 | CLOSED |  | 201 | 46 | 201¦OSWO |  | DEPOT |  | Wires Ready | 2023-08-04 | 2023-08-04 | [5 empty] | 5.3 | 5.3 | 10.9 | 5.3 | -5.6 | 0.5 | 1 | 100 | 10.9 |  | 2023-06-12 09:48 | 2023-09-20 06:36
| B | 1 |  | 2 | CLOSED |  | 351 | F1 | 351¦PROVISIONS |  | DEPOT | HF PARTS | Wires Ready | 2024-02-22 | 2024-02-26 | [5 empty] | 47.6 | 47.6 | 36.3 | 47.6 | 11.3 | 1.3 | 1 | 100 | 36.3 |  | 2023-03-07 21:40 | 2024-04-22 11:33
| B | 1 |  | 2 | CLOSED |  | 351 | 33 | 351¦BRACKETS |  | DEPOT |  | Wires Ready | 2024-01-24 | 2024-01-25 | [5 empty] | 26.1 | 26.1 | 82.9 | 26.1 | -56.8 | 0.3 | 1 | 100 | 82.9 |  | 2023-11-13 11:49 | 2024-04-24 09:57
| B | 1 |  | 2 | CLOSED |  | 351 | 1 | 351¦STAIRS |  | DEPOT | HF PARTS | GFE Decrib | 2021-03-16 | 2021-03-17 | [5 empty] | 12 | 12 | 288.5 | 12 | -276.5 |  | 1 | 100 | 288.5 |  | 2021-02-01 12:51 | 2024-04-29 15:27
| B | 1 |  | 2 | CLOSED |  | VC601 | PZH2 | 601¦GFE REMOVE TC |  | DEPOT |  | Wires Ready | 2023-06-30 | 2023-07-05 | [5 empty] | 29.3 | 29.3 | 115 | 29.3 | -85.7 | 0.3 | 1 | 100 | 115 |  | 2022-05-02 13:24 | 2023-12-08 10:09
| B | 2 |  | 2 | CLOSED |  | 251 | XH | 251¦PROVISIONS |  | DEPOT | HF PARTS | Wires Ready | 2023-06-06 | 2023-06-09 | [5 empty] | 31.3 | 31.3 | 166.5 | 31.3 | -135.2 | 0.2 | 1 | 100 | 166.5 |  | 2022-07-28 20:42 | 2023-12-20 13:54
| B | 2 |  | 2 | CLOSED |  | 901 | WH | 901¦BENCH WORK |  | DEPOT |  | Wires Ready | 2023-08-02 | 2023-08-02 | [5 empty] | 5.3 | 5.3 |  | 5.3 | 5.3 |  | 1 | 100 |  |  | 2023-08-31 06:25 | 2023-10-20 06:02
| B | 1 |  | 2 | CLOSED |  | 201 | F1 | 201¦PROVISIONS |  | DEPOT | HF PARTS | Wires Ready | 2024-03-19 | 2024-03-26 | [5 empty] | 24 | 24 | 39.5 | 24 | -15.5 | 0.6 | 1 | 100 | 39.5 |  | 2021-08-07 11:13 | 2021-09-02 08:52
| B | 1 |  | 2 | CLOSED |  | 451 | F4 | 451¦WHEEL WELL |  | DEPOT |  | Wires Ready | 2024-09-24 | 2024-09-26 | [5 empty] | 29.3 | 29.3 | 66 | 29.3 | -36.7 | 0.4 | 1 | 100 | 66 |  | 2022-09-12 06:18 | 2024-05-29 12:16
| B | 1 |  | 2 | CLOSED |  | 101 | F2 | 101¦WINDOWS |  | DEPOT |  | Wires Ready | 2024-04-11 | 2024-04-17 | [5 empty] | 90.9 | 90.9 | 71.4 | 90.9 | 19.5 | 1.3 | 1 | 100 | 71.4 |  | 2022-01-25 12:13 | 2024-08-15 14:29
| B | 4 |  | 2 | CLOSED |  | VC601 | PZH4 | 601¦TAILCONE |  | DEPOT | HF OTHER BHS | Wires Ready | 2024-07-23 | 2024-07-29 | [5 empty] | 47.5 | 47.5 | 10 | 47.5 | 37.5 | 4.8 | 1 | 100 | 10 |  | 2024-09-09 05:45 | 2024-09-18 12:28
| B | 1 |  | 2 | CLOSED |  | VC401 | PZC3 | 401¦STRUCTURES |  | DEPOT |  | Wires Ready | 2024-08-13 | 2024-08-15 | [5 empty] | 52.1 | 52.1 | 41.8 | 52.1 | 10.3 | 1.2 | 1 | 100 | 41.8 |  | 2022-09-19 06:25 | 2024-05-31 11:59
| B | 1 |  | 2 | CLOSED |  | 351 | AA | 351¦AFT BG |  | DEPOT | IN WORK | GFE Decrib | 2021-04-23 | 2021-04-26 | [5 empty] | 8 | 8 | 172.5 | 8 | -164.5 |  | 1 | 100 | 172.5 |  | 2020-12-16 20:00 | 2021-07-01 14:22
| B | 1 |  | 2 | CLOSED |  | 451 | 3A | 451¦WHEEL WELL |  | DEPOT |  | Wires Ready | 2023-01-03 | 2023-01-09 | [5 empty] | 29.3 | 29.3 | 111.8 | 29.3 | -82.5 | 0.3 | 1 | 100 | 111.8 |  | 2022-11-30 09:24 | 2023-02-07 13:27
| B | 1 |  | 2 | CLOSED |  | 351 | AA | 351¦AFT BG |  | DEPOT | HF PARTS | GFE Decrib | 2021-04-26 | 2021-04-27 | [5 empty] | 16 | 16 | 236.4 | 16 | -220.4 | 0.1 | 1 | 100 | 236.4 |  | 2021-01-28 00:10 | 2021-09-14 21:45
| B | 1 |  | 2 | CLOSED |  | 200 | 7 | 851¦TAILCONE |  | DEPOT | HF OTHER BHS | Tailcone | 2020-08-21 | 2020-08-24 | [5 empty] | 16 | 16 | 38.5 | 16 | -22.5 | 0.4 | 1 | 100 | 38.5 |  | 2021-04-30 13:07 | 2021-05-11 14:32
| B | 1 |  | 2 | CLOSED |  | 601 | 9A | 601¦TAILCONE |  | DEPOT | HF PARTS | Wires Ready | 2020-09-11 | 2020-09-11 | [5 empty] | 22 | 22 | 89 | 22 | -67 | 0.2 | 1 | 100 | 89 |  | 2021-06-04 13:00 | 2021-11-02 19:10
| B | 2 |  | 2 | CLOSED |  | 601 | 9A | 601¦TAILCONE |  | DEPOT | HF PARTS | Wires Ready | 2020-09-11 | 2020-09-14 | [5 empty] | 22 | 22 | 70.7 | 22 | -48.7 | 0.3 | 1 | 100 | 70.7 |  | 2021-09-21 05:31 | 2021-11-04 15:05
| B | 1 |  | 2 | CLOSED |  | 601 | 9 | 601¦TAILCONE |  | DEPOT | HF PARTS | Wires Ready | 2022-03-02 | 2022-03-03 | [5 empty] | 22 | 22 | 86.9 | 22 | -64.9 | 0.3 | 1 | 100 | 86.9 |  | 2022-05-02 09:13 | 2022-07-09 09:20
| B | 1 |  | 2 | CLOSED |  | 151 | F2 | 151¦STRUCTURES |  | DEPOT | WORKABLE | Wires Ready | 2024-04-08 | 2024-04-16 | [5 empty] | 39.6 | 39.6 | 258.8 | 39.6 | -219.2 | 0.2 | 1 | 100 | 258.8 |  | 2020-07-02 12:49 | 2024-03-14 19:40
| B | 1 |  | 2 | CLOSED |  | 050 | 2 | 000¦MAINT |  | DEPOT |  |  | 2025-01-16 | 2025-01-16 | [5 empty] | 1 | 1 | 2.5 | 1 | -1.5 | 0.4 | 1 | 100 | 2.5 |  | 2025-01-15 09:44 | 2025-01-15 14:40
| B | 1 |  | 2 | CLOSED |  | 451 | F2 | 451¦WHEEL WELL |  | DEPOT |  | Wires Ready | 2024-06-03 | 2024-06-05 | [5 empty] | 29.3 | 29.3 | 78.1 | 29.3 | -48.8 | 0.4 | 1 | 100 | 78.1 |  | 2022-10-03 13:51 | 2024-08-22 08:29
| B | 1 |  | 2 | CLOSED |  | 251 | F1 | 251¦PROVISIONS |  | DEPOT |  | Wires Ready | 2024-02-02 | 2024-02-05 | [5 empty] | 31.3 | 31.3 | 211.1 | 31.3 | -179.8 | 0.1 | 1 | 100 | 211.1 |  | 2022-06-28 06:27 | 2024-07-24 19:59
| B | 1 |  | 2 | CLOSED |  | 351 | F3 | 351¦BRACKETS |  | DEPOT |  | Wires Ready | 2024-06-24 | 2024-06-26 | [5 empty] | 42.4 | 42.4 | 74 | 42.4 | -31.6 | 0.6 | 1 | 100 | 74 |  | 2022-09-28 05:02 | 2024-09-04 09:17
| B | 1 |  | 2 | CLOSED |  | 201 | F1 | 201¦FLOORS |  | DEPOT |  | Wires Ready | 2024-03-07 | 2024-03-14 | [5 empty] | 46.4 | 46.4 | 229.8 | 46.4 | -183.4 | 0.2 | 1 | 100 | 229.8 |  | 2022-07-07 06:10 | 2024-09-04 05:55
| B | 1 |  | 2 | CLOSED |  | 401 | F3 | 401¦STRUCTURES |  | DEPOT | HF OTHER BHS | Wires Ready | 2024-07-22 | 2024-07-24 | [5 empty] | 1531.6 | 1531.6 | 789.3 | 1531.6 | 742.3 | 1.9 | 1 | 100 | 789.3 |  | 2021-05-10 09:45 | 2024-12-02 13:19
| B | 1 |  | 2 | CLOSED |  | VC801 | PZA2 | 801¦OSWO |  | DEPOT |  | Wires Ready | 2024-06-17 | 2024-06-27 | [5 empty] | 4.4 | 4.4 | 4 | 4.4 | 0.4 | 1.1 | 1 | 100 | 4 |  | 2024-06-11 17:52 | 2024-06-11 20:59
| B | 1 |  | 2 | CLOSED |  | 801 | F5 | 801¦PROVISIONS |  | DEPOT |  |  | 2025-02-12 | 2025-02-18 | [5 empty] | 43.5 | 43.5 | 28.1 | 43.5 | 15.3 | 1.5 | 1 | 100 | 28.1 |  | 2024-11-18 09:44 | 2024-12-17 13:25
| B | 2 |  | 2 | CLOSED |  | VC601 | PZH5 | 601¦TAILCONE |  | DEPOT | HF PARTS | Wires Ready | 2024-01-25 | 2024-02-01 | [5 empty] | 26.1 | 26.1 | 50.8 | 26.1 | -24.8 | 0.5 | 1 | 100 | 50.8 |  | 2022-11-25 07:11 | 2024-05-21 09:04
| B | 3 |  | 2 | CLOSED |  | VC601 | PZH5 | 601¦TAILCONE |  | DEPOT | HF PARTS | Wires Ready | 2024-01-25 | 2024-02-01 | [5 empty] | 26.1 | 26.1 | 70.8 | 26.1 | -44.8 | 0.4 | 1 | 100 | 70.8 |  | 2022-11-25 07:03 | 2024-07-08 13:19
| B | 2 |  | 2 | CLOSED |  | 351 | F1 | 351¦STRUCTURES |  | DEPOT | HF OTHER BHS | Wires Ready | 2024-02-06 | 2024-02-07 | [5 empty] | 36.7 | 36.7 | 180.3 | 36.7 | -143.6 | 0.2 | 1 | 100 | 180.3 |  | 2023-07-07 06:25 | 2024-08-06 09:29
| B | 1 |  | 2 | CLOSED |  | 351 | F1 | 351¦STRUCTURES |  | DEPOT | HF OTHER BHS | Wires Ready | 2024-02-20 | 2024-02-21 | [5 empty] | 36.7 | 36.7 | 127.4 | 36.7 | -90.7 | 0.3 | 1 | 100 | 127.4 |  | 2023-08-30 05:24 | 2024-08-07 07:14
| B | 1 |  | 2 | CLOSED |  | 351 | F3 | 351¦STRUCTURES |  | DEPOT |  | Wires Ready | 2024-06-17 | 2024-06-20 | [5 empty] | 36.7 | 36.7 | 61.8 | 36.7 | -25.1 | 0.6 | 1 | 100 | 61.8 |  | 2024-02-26 11:16 | 2024-08-06 14:54
| B | 1 |  | 2 | CLOSED |  | 601 | F3 | 601¦TAILCONE |  | DEPOT | HF OTHER BHS | Wires Ready | 2024-07-23 | 2024-07-30 | [5 empty] | 72.3 | 72.3 | 307.5 | 72.3 | -235.2 | 0.2 | 1 | 100 | 307.5 |  | 2022-04-26 17:54 | 2024-05-06 12:27
| B | 2 |  | 2 | CLOSED |  | 101 | F2 | 101¦FLOORS |  | DEPOT | HF OTHER BHS | Wires Ready | 2024-04-30 | 2024-05-07 | [5 empty] | 32 | 32 | 109.7 | 32 | -77.7 | 0.3 | 1 | 100 | 109.7 |  | 2021-12-07 09:00 | 2021-12-16 12:55
1 | B | 1 |  | 2 | CLOSED |  | 351 | F1 | 351¦BRACKETS |  | DEPOT | HF PARTS | Wires Ready | 2024-02-01 | 2024-02-05 | [5 empty] | 42.4 | 42.4 | 232.3 | 42.4 | -189.9 | 0.2 | 1 | 100 | 232.3 |  | 2022-04-05 20:31 | 2024-08-19 18:29
| B | 1 |  | 2 | CLOSED |  | 251 | F3 | 251¦INT STRUCTURES |  | DEPOT |  | Wires Ready | 2024-07-19 | 2024-07-23 | [5 empty] | 22 | 22 | 325.5 | 22 | -303.5 | 0.1 | 1 | 100 | 325.5 |  | 2024-05-29 08:30 | 2024-07-24 12:29
1 | B | 2 |  | 2 | CLOSED |  | 501 | F4 | 501¦HSTAB/VFIN |  | DEPOT | HF OTHER BHS | Wires Ready | 2024-09-05 | 2024-09-12 | [5 empty] | 36.7 | 36.7 | 294.7 | 36.7 | -258 | 0.1 | 1 | 100 | 294.7 |  | 2022-04-20 07:08 | 2024-08-19 12:42
| B | 1 |  | 2 | CLOSED |  | 451 | F5 | 451¦WHEEL WELL |  | DEPOT |  | Wires Ready | 2024-10-01 | 2024-10-09 | [5 empty] | 26.1 | 26.1 | 260.1 | 26.1 | -234.1 | 0.1 | 1 | 100 | 260.1 |  | 2023-09-25 13:13 | 2024-10-10 14:32
| B | 1 |  | 2 | CLOSED |  | 300 | 1 | 351¦STRUCTURES |  | DIS |  |  | 2024-10-08 | 2024-10-08 |  |  |  |  | Create new NCR forcurrent condition, ensure to reference NCR1031024N. Revise/Clarifyattachment to reflect discrepant holes ONLY.For Holes 1-8:Include FWD and AFTedge margins. Include qty (3) decimal places.For hole 35:Provide FWD and AFT edge margins andpitch to adjacent fasteners. Include qty (3) decimal places.For holes 102-116&amp; 52:Provideedge margins in all directions. Include qty (3) decimal places.No further rework isrequired on this NCR.E-UM review is notrequired. |  |  | 55.2 |  | -55.2 |  |  | 100 | 55.2 |  | 2024-10-07 08:05 | 2024-10-15 15:47
| B | 1 |  | 2 | CLOSED |  | VC601 | PZH4 | 601¦TAILCONE |  | DEPOT | HF PARTS | Wires Ready | 2024-11-25 | 2024-12-03 | [5 empty] | 68.5 | 68.5 | 32.1 | 68.5 | 36.5 | 2.1 | 1 | 100 | 32.1 |  | 2023-04-14 04:50 | 2025-04-06 08:52
1 | B | 1 |  | 2 | CLOSED |  | 351 | F9 | 351¦PROVISIONS |  | DEPOT | HF PARTS | Wires Ready | 2025-07-16 | 2025-07-30 | [5 empty] | 586.6 | 586.6 | 14.8 |  | 571.9 | 39.6 |  | 100 | 14.8 |  | 2022-08-16 23:44 | 2025-04-04 08:43
| B | 2 |  | 2 | CLOSED |  | 551 | F5 | 551¦WINGS |  | DEPOT |  |  | 2024-10-25 | 2024-10-31 | [5 empty] | 21.9 | 21.9 | 146.7 | 21.9 | -124.8 | 0.1 | 1 | 100 | 146.7 |  | 2024-09-16 07:10 | 2024-10-03 12:47
| B | 1 |  | 2 | CLOSED |  | 401 | F3 | 401¦PROVISIONS |  | DEPOT |  | Wires Ready | 2024-06-10 | 2024-06-17 | [5 empty] | 1118.8 | 1118.8 | 246.2 | 1118.8 | 872.6 | 4.5 | 1 | 100 | 246.2 |  | 2022-08-01 07:14 | 2024-12-12 09:55
| B | 1 |  | 2 | CLOSED |  | VC351 | PZA5 | 351¦STRUCTURES |  | DEPOT |  | Wires Ready | 2024-02-19 | 2024-02-20 | [5 empty] | 104.5 | 104.5 | 49.2 | 104.5 | 55.3 | 2.1 | 1 | 100 | 49.2 |  | 2023-03-09 08:25 | 2024-11-20 13:16
| B | 3 |  | 2 | CLOSED |  | 351 | F1 | 351¦STRUCTURES |  | DEPOT |  | Wires Ready | 2024-03-04 | 2024-03-05 | [5 empty] | 62 | 62 | 21.9 | 62 | 40 | 2.8 | 1 | 100 | 21.9 |  | 2023-11-16 12:46 | 2024-12-12 14:55
| B | 5 |  | 2 | CLOSED |  | 120 | 1 | H LL |  | DEPOT | WORKABLE | Wires Ready | 2020-04-28 | 2020-04-28 | [5 empty] | 8 | 8 | 50.2 | 8 | -42.2 | 0.2 | 1 | 100 | 50.2 |  | 2020-08-26 06:44 | 2024-12-11 08:55
| B | 1 |  | 2 | CLOSED |  | 601 | 6 | 601¦TAILCONE |  | DEPOT | HF OTHER BHS | Wires Ready | 2024-04-08 | 2024-04-15 | [5 empty] | 67.2 | 67.2 | 54.5 | 67.2 | 12.7 | 1.2 | 1 | 100 | 54.5 |  | 2024-02-13 06:00 | 2025-01-23 09:55
2 | B | 1 |  | 2 | CLOSED |  | 351 | F0 | 351¦STRUCTURES |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-09-22 | 2025-09-29 | [5 empty] | 484 | 484 | 349.3 |  | 134.7 | 1.4 |  | 100 | 349.3 |  | 2022-09-22 05:26 | 2025-02-19 10:55
| B | 2 |  | 2 | CLOSED |  | 351 | 4F | 351¦STRUCTURES |  | DEPOT | HF PARTS | Wires Ready | 2024-01-25 | 2024-01-29 | [5 empty] | 580.3 | 580.3 | 362.1 | 580.3 | 218.2 | 1.6 | 1 | 100 | 362.1 |  | 2022-08-09 13:24 | 2024-12-16 20:40
| B | 1 |  | 2 | CLOSED |  | 501 | F3 | 501¦HSTAB/VFIN |  | DEPOT |  | Wires Ready | 2024-07-08 | 2024-07-15 | [5 empty] | 34.3 | 34.3 | 5.9 | 34.3 | 28.3 | 5.8 | 1 | 100 | 5.9 |  | 2024-12-19 18:25 | 2024-12-20 00:10
| B | 4 |  | 2 | CLOSED |  | 601 | F5 | 601¦TAILCONE |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-01-22 | 2025-01-29 | [5 empty] | 36.7 | 36.7 | 94.5 | 36.7 | -57.8 | 0.4 | 1 | 100 | 94.5 |  | 2023-01-30 18:35 | 2024-04-19 09:42
| B | 1 |  | 2 | CLOSED |  | 601 | F6 | 601¦TAILCONE |  | DEPOT | HF PARTS | Wires Ready | 2026-01-26 | 2026-01-29 | [5 empty] | 251.2 | 251.2 | 177.9 |  | 73.3 | 1.4 |  | 100 | 177.9 |  | 2022-08-30 16:19 | 2025-03-03 23:18
| B | 1 |  | 2 | CLOSED |  | 101 | XA | 101¦OSWO |  | DEPOT |  |  | 2025-05-12 | 2025-05-19 | [5 empty] | 33 | 33 | 11.5 |  | 21.5 | 2.9 |  | 100 | 11.5 |  | 2025-03-22 08:14 | 2025-03-27 06:52
| B | 1 |  | 2 | CLOSED |  | 401 | F6 | 401¦STRUCTURES |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-02-05 | 2025-03-10 | [5 empty] | 1323.8 | 1323.8 | 295.2 | 1323.8 | 1028.5 | 4.5 | 1 | 100 | 295.2 |  | 2024-04-09 04:59 | 2025-03-04 12:56
| B | 1 |  | 2 | CLOSED |  | 451 | F8 | 451¦WHEEL WELL |  | DEPOT | HF PARTS | Wires Ready | 2025-09-25 | 2025-10-08 | [5 empty] | 135.6 | 135.6 | 284.8 |  | -149.2 | 0.5 |  | 100 | 284.8 |  | 2022-05-18 13:55 | 2025-03-25 10:22
| B | 1 |  | 2 | CLOSED |  | 251 | F6 | 251¦OSWO |  | DEPOT |  |  | 2025-02-27 | 2025-03-10 | [5 empty] | 14.7 | 14.7 | 19.6 | 14.7 | -5 | 0.7 | 1 | 100 | 19.6 |  | 2024-12-27 05:53 | 2025-02-25 10:10
| B | 1 |  | 2 | CLOSED |  | 351 | F7 | 251¦REMOVALS |  | DEPOT |  |  | 2025-05-15 | 2025-05-22 | [5 empty] | 16 | 16 | 26.6 |  | -10.6 | 0.6 |  | 100 | 26.6 |  | 2025-03-12 07:17 | 2025-03-14 09:37
| B | 1 |  | 2 | CLOSED |  | 851 | EH | 951 ¦ STR-GAC |  | DEPOT |  |  | 2024-09-11 | 2024-09-12 | [5 empty] | 7 | 7 | 34.4 | 7 | -27.4 | 0.2 | 1 | 100 | 34.4 |  | 2024-08-06 08:48 | 2025-04-04 20:52
| B | 18 |  | 2 | CLOSED |  | 851 | EH | 951 ¦ STR-GAC |  | DEPOT |  |  | 2024-09-27 | 2024-09-30 | [5 empty] | 7 | 7 | 50.8 | 7 | -43.8 | 0.1 | 1 | 100 | 50.8 |  | 2024-07-23 11:34 | 2025-03-28 12:22
| B | 1 |  | 2 | CLOSED |  | 201 | F9 | 201¦OSWO |  | DEPOT |  | Wires Ready | 2025-08-06 | 2025-08-07 | [5 empty] | 33.4 | 33.4 | 27.4 |  | 6 | 1.2 |  | 100 | 27.4 |  | 2024-08-14 08:57 | 2025-02-13 16:00
| B | 1 |  | 2 | CLOSED |  | 851 | EH | 951 ¦ STR-GAC |  | DEPOT | [16 empty] | 100 |  |  | 2022-08-25 09:32 | 2025-03-19 12:22
| B | 1 |  | 2 | CLOSED |  | 101 | XA | 951 ¦ STR-GAC |  | DEPOT | [11 empty] | 10.7 |  | -10.7 |  |  | 100 | 10.7 |  | 2022-08-25 15:51 | 2025-03-19 12:22
| B | 10 |  | 2 | CLOSED |  | 851 | EH | 951 ¦ STR-GAC |  | DEPOT | [11 empty] | 40.4 |  | -40.4 |  |  | 100 | 40.4 |  | 2022-08-23 05:38 | 2025-03-19 12:22
1 | B | 1 |  | 2 | CLOSED |  | 351 | F7 | 351¦BRACKETS |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-07-09 | 2025-07-23 | [5 empty] | 276.9 | 276.9 | 79.8 |  | 197.2 | 3.5 |  | 100 | 79.8 |  | 2023-02-14 09:06 | 2025-02-21 16:10
| B | 1 |  | 2 | CLOSED |  | 201 | F6 | 201¦PROVISIONS |  | DEPOT | HF ENG | Wires Ready | 2025-02-12 | 2025-02-26 | [5 empty] | 32.1 | 32.1 | 76.7 | 32.1 | -44.6 | 0.4 | 1 | 100 | 76.7 |  | 2020-12-08 04:48 | 2025-02-04 15:40
| B | 1 |  | 2 | CLOSED |  | 151 | F6 | 151¦PROVISIONS |  | DEPOT | WORKABLE | Wires Ready | 2025-05-29 | 2025-06-12 | [5 empty] | 294.6 | 294.6 | 172.2 |  | 122.3 | 1.7 |  | 100 | 172.2 |  | 2020-10-06 06:28 | 2025-03-06 10:16
| B | 2 |  | 2 | CLOSED |  | 351 | F8 | 351¦STRUCTURES |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-06-12 | 2025-06-26 | [5 empty] | 1948 | 1948 | 86.4 |  | 1861.5 | 22.5 |  | 100 | 86.4 |  | 2021-09-22 08:37 | 2025-02-19 17:10
| B | 1 |  | 2 | CLOSED |  | 201 | F6 | 201¦FLOORS |  | DEPOT | HF OTHER BHS | Wires Ready | 2025-02-18 | 2025-03-05 | [5 empty] | 54.1 | 54.1 | 267.1 | 54.1 | -213 | 0.2 | 1 | 100 | 267.1 |  | 2021-11-19 18:07 | 2025-02-25 09:40
| B | 1 |  | 2 | CLOSED |  | 401 | XM | 401¦STRUCTURES |  | DEPOT | HF OTHER BHS | Power On | 2024-12-04 | 2024-12-11 | [5 empty] | 45 | 45 | 137 | 45 | -92 | 0.3 | 1 | 100 | 137 |  | 2021-04-06 16:08 | 2025-04-01 13:28
| B | 1 |  | 2 | CLOSED |  | 601 | XW | 601¦TAILCONE |  | DEPOT |  | Wires Ready | 2021-11-08 | 2021-11-09 | [5 empty] | 11 | 11 | 77 | 11 | -66 | 0.1 | 1 | 100 | 77 |  | 2022-05-25 08:34 | 2022-06-08 12:33
| B | 1 |  | 2 | CLOSED |  | 151 | F6 | 101¦PROVISIONS |  | DEPOT |  |  | 2025-09-04 | 2025-09-16 | [5 empty] | 43.5 | 43.5 | 59 |  | -15.6 | 0.7 |  | 100 | 59 |  | 2025-03-18 09:20 | 2025-03-29 12:48
| B | 10 |  | 2 | CLOSED |  | 851 | EH | 951 ¦ STR-GAC |  | DEPOT | [11 empty] | 87 |  | -87 |  |  | 100 | 87 |  | 2022-05-20 05:05 | 2025-03-19 12:07
| B | 5 |  | 2 | CLOSED |  | 851 | EH | 951 ¦ STR-GAC |  | DEPOT | [11 empty] | 49.6 |  | -49.6 |  |  | 100 | 49.6 |  | 2022-05-20 08:31 | 2025-03-19 12:07
| B | 3 |  | 2 | CLOSED |  | 851 | EH | 951 ¦ STR-GAC |  | DEPOT | [11 empty] | 65 |  | -65 |  |  | 100 | 65 |  | 2022-05-23 17:33 | 2025-03-19 12:22
| B | 2 |  | 2 | CLOSED |  | 851 | EH | 951 ¦ STR-GAC |  | DEPOT | [11 empty] | 123.2 |  | -123.2 |  |  | 100 | 123.2 |  | 2022-05-21 13:21 | 2025-03-19 12:22
| B | 1 |  | 2 | CLOSED |  | 301 | 4H | 951 ¦ STR-GAC |  | DEPOT | [11 empty] | 17.2 |  | -17.2 |  |  | 100 | 17.2 |  | 2022-08-19 07:19 | 2025-03-19 12:22
| B | 6 |  | 2 | CLOSED |  | 251 | XH | 951 ¦ STR-GAC |  | DEPOT | [11 empty] | 21.8 |  | -21.8 |  |  | 100 | 21.8 |  | 2022-08-19 06:32 | 2025-03-19 12:22
| B | 3 |  | 2 | CLOSED |  | 851 | EH | 951 ¦ STR-GAC |  | DEPOT | [11 empty] | 14.4 |  | -14.4 |  |  | 100 | 14.4 |  | 2022-08-23 06:10 | 2025-03-19 12:22
| B | 1 |  | 2 | CLOSED |  | 301 | XJ | 951 ¦ STR-GAC |  | DEPOT |  |  | 2020-08-18 | 2020-08-21 | [7 empty] | 105.3 |  | -105.3 |  |  | 100 | 105.3 |  | 2022-05-24 15:11 | 2025-03-19 12:07
| B | 1 |  | 2 | CLOSED |  | 301 | XJ | 951 ¦ STR-GAC |  | DEPOT |  |  | 2020-08-18 | 2020-08-21 | [7 empty] | 47.9 |  | -47.9 |  |  | 100 | 47.9 |  | 2022-05-27 16:17 | 2025-03-19 12:07
| B | 3 |  | 2 | CLOSED |  | 301 | XJ | 951 ¦ STR-GAC |  | DEPOT |  |  | 2020-08-18 | 2020-08-21 | [7 empty] | 51.8 |  | -51.8 |  |  | 100 | 51.8 |  | 2022-05-23 11:23 | 2025-03-19 12:07
| B | 1 |  | 2 | CLOSED |  | 301 | XJ | 951 ¦ STR-GAC |  | DEPOT |  |  | 2020-08-18 | 2020-08-21 | [7 empty] | 75.1 |  | -75.1 |  |  | 100 | 75.1 |  | 2022-05-23 12:19 | 2025-03-19 12:07
| B | 1 |  | 2 | CLOSED |  | 301 | XJ | 951 ¦ STR-GAC |  | DEPOT |  |  | 2020-08-18 | 2020-08-21 | [7 empty] | 87.6 |  | -87.6 |  |  | 100 | 87.6 |  | 2022-05-23 11:21 | 2025-03-19 12:07
| B | 1 |  | 2 | CLOSED |  | 301 | XJ | 951 ¦ STR-GAC |  | DEPOT |  |  | 2020-08-18 | 2020-08-21 | [7 empty] | 67.3 |  | -67.3 |  |  | 100 | 67.3 |  | 2022-05-23 17:36 | 2025-03-19 12:07
| B | 2 |  | 2 | CLOSED |  | 301 | XJ | 951 ¦ STR-GAC |  | DEPOT |  |  | 2020-08-18 | 2020-08-21 | [7 empty] | 76.7 |  | -76.7 |  |  | 100 | 76.7 |  | 2022-05-23 07:01 | 2025-03-19 12:07
| B | 1 |  | 2 | CLOSED |  | 401 | XM | 951 ¦ STR-GAC |  | DEPOT | [11 empty] | 177.1 |  | -177.1 |  |  | 100 | 177.1 |  | 2022-05-23 06:33 | 2025-03-19 12:07
| B | 5 |  | 2 | CLOSED |  | 101 | 4E | 951 ¦ STR-GAC |  | DEPOT |  |  | 2020-04-03 | 2020-04-03 | [7 empty] | 63.7 |  | -63.7 |  |  | 100 | 63.7 |  | 2022-05-23 07:38 | 2025-03-19 12:07
| B | 1 |  | 2 | CLOSED |  | VC351 | PZA1 | 201¦PROVISIONS |  | DEPOT |  | Wires Ready | 2024-02-12 | 2024-02-15 | [5 empty] | 43.1 | 43.1 | 300.3 | 43.1 | -257.2 | 0.1 | 1 | 100 | 300.3 |  | 2022-11-15 09:08 | 2025-03-17 08:40
| B | 1 |  | 2 | CLOSED |  | 251 | F9 | 251¦PROVISIONS |  | DEPOT |  | Wires Ready | 2025-07-22 | 2025-08-06 | [5 empty] | 247.1 | 247.1 | 207.6 |  | 39.5 | 1.2 |  | 100 | 207.6 |  | 2023-03-09 05:44 | 2025-03-24 09:07
| B | 1 |  | 2 | CLOSED |  | 201 | F9 | 201¦PROVISIONS |  | DEPOT |  |  | 2025-05-08 | 2025-05-15 | [5 empty] | 33 | 33 | 6.7 |  | 26.3 | 4.9 |  | 100 | 6.7 |  | 2025-03-20 06:47 | 2025-04-02 12:37
| B | 4 |  | 2 | CLOSED |  | 551 | F7 | 551¦WINGS |  | DEPOT |  |  | 2025-03-25 | 2025-04-01 | [5 empty] | 43.8 | 43.8 | 40.5 | 43.8 | 3.3 | 1.1 | 1 | 100 | 40.5 |  | 2025-01-31 04:57 | 2025-02-11 11:55
| B | 1 |  | 2 | CLOSED |  | 351 | F6 | 351¦OSWO |  | DEPOT |  | Wires Ready | 2025-02-25 | 2025-03-11 | [5 empty] | 4995.3 | 4995.3 | 92.1 | 4995.3 | 4903.2 | 54.2 | 1 | 100 | 92.1 |  | 2022-07-07 05:39 | 2025-02-10 08:10
| B | 2 |  | 2 | CLOSED |  | 101 | 4E | 951 ¦ STR-GAC |  | DEPOT |  |  | 2020-04-03 | 2020-04-03 | [7 empty] | 49.4 |  | -49.4 |  |  | 100 | 49.4 |  | 2022-05-23 08:41 | 2025-03-19 11:37
| B | 2 |  | 2 | CLOSED |  | 451 | F7 | 451¦WHEEL WELL |  | DEPOT | HF PARTS | Wires Ready | 2025-10-08 | 2025-10-20 | [5 empty] | 160.8 | 160.8 | 337.2 |  | -176.4 | 0.5 |  | 100 | 337.2 |  | 2022-05-16 06:17 | 2025-03-17 05:52
| B | 1 |  | 2 | CLOSED |  | 251 | 71 | 351¦PROVISIONS |  | DEPOT |  | Wires Ready | 2025-07-28 | 2025-08-11 | [5 empty] | 2726.3 | 2726.3 | 78.5 |  | 2647.8 | 34.7 |  | 100 | 78.5 |  | 2022-09-30 12:43 | 2025-04-02 09:47
| B | 1 |  | 2 | CLOSED |  | VC601 | PZH4 | 601¦TAILCONE |  | DEPOT | HF PARTS | Wires Ready | 2024-11-25 | 2024-12-03 | [5 empty] | 119.2 | 119.2 | 34.2 | 119.2 | 85 | 3.5 | 1 | 100 | 34.2 |  | 2025-04-05 04:31 | 2025-04-06 08:52