## Corporate Compliance Team (hidden)
Corporate Compliance Team | links
Compliance - Corporate Compliance (new obligation register - sharepoint) |  | Excel
Compliance System #1 - iComply data |  | SkyTrust
Compliance System #1 - Fasttrack (Labs) |  | Barometer IT
Compliance System #2 - Excel (Water Quality) |  | PowerBi
Compliance System #3 - Compliance Manual Significant Aspects Register (Environment) | Link to details here Environmental Compliance Manual | OIR | Angela Dewdney
Compliance System #4 SAAM Audit Obligations | Incomplete list, with no viable data for transfer. We need to switch off this module/functionality in SAAM and discard the data. SAI360 : SAAM | FastTrack
Compliance System #5 |  | Workplace Safety Australia
Compliance System #6 |  | SAAM
Compliance System #7 |  | Maximo
Compliance System #8
Compliance System #9

## TASK SCHEDULE
[10 empty] | PROJECT START DATE: |  |  | 2025-03-03
[10 empty] | 2025-03-10 | [33 empty] | 2024
[10 empty] | 2025-03-10 |  |  |  | 2025-04-07 |  |  |  | 2025-05-05 |  |  |  |  | 2025-06-09 |  |  |  | 2025-07-07 |  |  |  | 2025-08-04 |  |  |  |  | 2025-09-08 |  |  |  | 2025-10-06 |  |  |  | 2025-11-03 |  |  |  |  | 2025-12-08 |  |  |  | 2026-01-05 |  |  |  | 2026-02-02 |  |  |  |  | 2026-03-09 |  |  |  | 2026-04-06 |  |  |  | 2026-05-04 |  |  |  |  | 2026-06-08
[9 empty] | Wk Starting | [68 empty] | DASHBOARD CALCULATIONS - BY PHASE |  |  | DASHBOARD CALCULATIONS - OVERALL | time axis 2025-03-03 to 2026-06-15
| TASK | ASSIGNED TO | KEY CONTACT | START | END | DAYS | STATUS | KANBAN | % COMPLETE | [68 empty] | PHASE | TASK COMPLETION % | TASKS PENDING % |  | TASK COMPLETION % | TASKS PENDING %
AS IS/TO BE & USE CASES | As Is / To Be - Risk | Rebecca Boucher, Linda Taylor |  | 2025-01-13 | 2025-03-14 | 45 | LATE | On Hold | 70% | [68 empty] | DEFINE | 29.05% | 70.95% | PROJECT STATUS | 8.265% | 91.73%
| As Is / To Be - Assurance | Rebecca Boucher, Linda Taylor |  | 2025-01-13 | 2025-03-14 | 45 | LATE | Up Next | 5% | [68 empty] | MEASURE | 8% | 92%
| As Is / To Be - Obligation Management | Rebecca Boucher, Linda Taylor |  | 2025-01-13 |  |  |  | Up Next | 0% | [68 empty] | ANALYSE | 0% | 100%
| As Is / To Be - Action Management | Rebecca Boucher, Linda Taylor |  | 2025-01-13 |  |  |  | On Hold | 80% | [68 empty] | IMPROVE | 0% | 100%
| As Is / To Be - Reporting/Data | Rebecca Boucher, Linda Taylor, Daisy Shan |  | 2025-01-13 |  |  |  | Backlog | 0% | [68 empty] | CONTROL | 0% | 100%
| As Is / To Be - Business Continuity & Resilience | Rebecca Boucher, Linda Taylor |  | 2025-01-13 |  |  |  | Up Next | 0%
| As Is / To Be - Management of Change | Rebecca Boucher, Linda Taylor, Darren Macdonald |  | 2025-01-13 |  |  |  | Up Next | 0%
| Use Cases - Risk | Rebecca Boucher, Linda Taylor |  | 2025-01-13 | 2025-03-14 | 45 | LATE | On Hold | 70%
| Use Cases - Assurance | Rebecca Boucher, Linda Taylor |  | 2025-01-13 | 2025-03-14 | 45 | LATE | Up Next | 60%
| Use Cases - Obligation Management | Rebecca Boucher, Linda Taylor |  | 2025-01-13 |  |  |  | Up Next | 60%
| Use Cases - Action Management | Rebecca Boucher, Linda Taylor |  | 2025-01-13 |  |  |  | Up Next | 80%
| Use Cases - Reporting/Data | Rebecca Boucher, Linda Taylor, Daisy Shan |  | 2025-01-13 |  |  |  | Up Next | 0%
| Use Cases - Business Continuity & Resilience | Rebecca Boucher, Linda Taylor |  | 2025-01-13 |  |  |  | Up Next | 0%
| Use Cases - Management of Change | Rebecca Boucher, Linda Taylor, Darren Macdonald |  | 2025-01-13 |  |  |  | Up Next | 0%
| Use Cases - Administration | Rebecca Boucher, Linda Taylor |  | 2025-01-13 |  |  |  | Backlog | 0%
| Use Cases - Non-functional | Rebecca Boucher |  | 2025-01-13 |  |  |  | Backlog | 0%
| GRC Interrelationship Mapping | Rebecca Boucher, Linda Taylor, Darren Macdonald |  | 2025-01-13 | 2025-03-14 | 45 | LATE | In Progress | 95%
| As-Is Process Maps (draft) | Rebecca Boucher, Linda Taylor |  | 2025-03-05 | 2025-03-14 | 8 | LATE | In Progress | 80%
| To-Be Process Maps (draft) | Rebecca Boucher, Linda Taylor |  | 2025-03-11 | 2025-03-14 | 4 | LATE | In Progress | 10%
| Add MOC to our source of harm diagram | Rebecca Boucher, Linda Taylor |  | 2025-03-11 | 2025-03-14 | 4 | LATE | Up Next | 0%
0%
DATA DISCOVERY | SAAM Risk Module | Daisy Shan | [5 empty] | Completed | 100%
| SAAM Hazard Module - Environment Impact & Aspect Register | Daisy Shan |  | 2025-03-18 | 2025-03-20 | 3 | ON TIME | Up Next | 0%
| SAAM Hazard Module - Water Quality Risks | Daisy Shan |  | 2025-03-20 | 2025-03-24 | 3 | ON TIME | Up Next | 0%
| Supply chain risk | Daisy Shan | [5 empty] | Backlog | 0%
| Technology risk | Daisy Shan | [5 empty] | Backlog | 0%
| SAAM Assurance Module | Daisy Shan | [5 empty] | Backlog | 0%
| Assurance - CGRR | Daisy Shan | [5 empty] | Backlog | 0%
| Compliance - Corporate Compliance (new obligation register - sharepoint) | Daisy Shan | Libby |  |  |  |  | Backlog | 0%
| Compliance System #1 - iComply data | Daisy Shan | Libby |  |  |  |  | Backlog | 0%
| Compliance System #1 - Fasttrack (Labs) | Daisy Shan | Caroline Hobby |  |  |  |  | Backlog | 0%
| Compliance System #2 - Excel (Water Quality) | Daisy Shan | Stacey Kovac |  |  |  |  | Backlog | 0%
| Compliance System #3 - Compliance Manual Significant Aspects Register (Environment) | Daisy Shan | Angela Dewdney |  |  |  |  | Backlog | 0%
| Compliance System #4 SAAM Audit Obligations | Daisy Shan | Linda Taylor |  |  |  |  | Closed Out | 100%
| Compliance System #5 | Daisy Shan | [5 empty] | Backlog | 0%
| Compliance System #6 | Daisy Shan | [5 empty] | Backlog | 0%
| Compliance System #7 | Daisy Shan | [5 empty] | Backlog | 0%
| Compliance System #8 | Daisy Shan | [5 empty] | Backlog | 0%
| Compliance System #9 | Daisy Shan | [5 empty] | Backlog | 0%
0%
0%
| (Draft) data configuration - enterprise risk | Daisy Shan, Linda Taylor | [5 empty] | Backlog | 0%
0%
0%
0%
0%
DATA TIDY UP & CLEANSE | SAAM - Level 1 Risks | Linda Taylor, Tania Del Torre | [5 empty] | Up Next | 0%
| SAAM - Level 2 Risks | Linda Taylor, Tania Del Torre | [5 empty] | Backlog | 0%
| SAAM - Level 3 Risks | Linda Taylor, Tania Del Torre | [5 empty] | Backlog | 0%
| SAAM - Control Library | Linda Taylor, Tania Del Torre | [5 empty] | Backlog | 0%
| SAAM - Environment Aspect & Impact Register | Tania Del Torre | [5 empty] | Backlog | 0%
| SAAM - Water Quality Risks | Tania Del Torre | [5 empty] | Backlog | 0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
PROCUREMENT & SELECTION | Request for Information - development of documents | [6 empty] | Up Next | 0%
| Request for Information - submissions open | [6 empty] | Up Next | 0%
| Request for Information - assessment of responses and shortlisting | [6 empty] | Up Next | 0%
| Request for Tender - development of documents | [6 empty] | Up Next | 0%
| Request for Tender - submissions open | [6 empty] | Up Next | 0%
| Request for Tender - assessment of responses and shortlisting | [6 empty] | Up Next | 0%
| Request for Tender - vendor demonstrations | [6 empty] | Up Next | 0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
OTHER TASKS | Communication #1 - general comms to business about GRC technology project | Linda Taylor, Melody Caffin | [5 empty] | Up Next | 0%
| Communication #2 - Sweet Spot | Linda Taylor | [5 empty] | Backlog | 0%
| Communication #3 - Risk Community of Practice | Linda Taylor | [5 empty] | Backlog | 0%
| Communication #4 - Compliance Working Group | Linda Taylor | [5 empty] | Backlog | 0%
| Communication #5 - Together article | Linda Taylor | [5 empty] | Backlog | 0%
0%
0%
0%
0%
0%
Formulas:
DAYS = IF([END]="","",NETWORKDAYS([START],[END]))
STATUS = IF(OR(L7="",[END]=""),"",IF(L7=100%,"COMPLETE",IF(TODAY()>[END],"LATE",IF(TODAY()<[END]," ON TIME","DUE"))))
Note on P1: Martin, Leigh: INPUT PROJECT START DATE HERE
Note on I6: Martin, Leigh: STATUS COLUMN WILL AUTOPOPULATE BASED ON THE DATA ENTERED INTO COLUMNS F / G.
Note on J6: Martin, Leigh: STATUS COLUMN WILL AUTOPOPULATE BASED ON THE DATA ENTERED INTO COLUMNS F / G / H
Note on L6: Martin, Leigh: ENTER % COMPLETE INTO THIS COLUMN AND THE BAR CHART VISUAL WILL AUTO POPULATE
Note on D39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Link to details here Environmental Compliance Manual
Note on D40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Incomplete list, with no viable data for transfer. We need to switch off this module/functionality in SAAM and discard the data. SAI360 : SAAM