## Table 1
| Week Start | Weekly Performance to Date
| 2025-04-21 | ALL Aircraft (AC) |  |  |  | Shop Complete (AC) |  |  |  | Shop Complete (MM) |  |  | Major Milestone (MM) |  |  |  | Mon 4/21 | Tue 4/22 | Wed 4/23 | Thu 4/24 | Fri 4/25 | Sat 4/26 | Sun 4/27
|  | Actuals (BL) | Chk / Maint / Bltn | NCOs Closed | NCOs Created | Conformity | Non-Conformity | HF NCO | BARGE | Conformity | Non-Conformity | HF NCO | Balance to Go | Actuals | NCOs Closed | NCOs Created | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals
| Total | 190 | 47 | 127 | 117 | 1 | 63 | 66 |  |  | 51 | 55 | 9222 | 144 | 122 | 103 | 22 | 32 | 32 | 37 | 21
|  | ALL Aircraft 1 | [7 empty] | AC1 - Structures Complete
Aircraft | Aircraft 1 | 93 | 28 | 56 | 50 |  | 32 | 38 | Total |  | 24 | 32 | 3941 | 48 | 55 | 45 | 7 | 12 | 11 | 10 | 8
Aircraft 1 | BARGE1 | 7 |  | 11 | 6 |  | 8 | 7 | BARGE1 |  | 8 | 7 | 759 | 7 | 11 | 4 | 1 | 1 | 1 | 2 | 2
Aircraft 1 | BARGE2 | 8 |  | 7 | 5 |  | 3 | 3 | BARGE2 |  | 2 | 2 | 761 | 8 | 7 | 5 | Mon 4/21: 2; Tue 4/22: 1; Wed 4/23: 1; Thu 4/24: 4
Aircraft 1 | BARGE3 | 15 |  | 7 | 11 |  | 11 | 11 | BARGE3 |  | 11 | 10 | 1326 | 15 | 7 | 11 | 3 | 2 | 5 | 2 | 3
Aircraft 1 | BARGE4 | 3 |  | 2 | 2 |  | 1 | 1 | BARGE4 |  | 1 | 1 | 156 | 3 | 2 | 1 | bar: Tue 4/22 to Fri 4/25
Aircraft 1 | BARGE5 | 53 |  | 13 | 9 |  | 6 | 12 | BARGE5 |  |  | 8 | 497 | 8 | 12 | 7 | Mon 4/21: 1; Tue 4/22: 4; Thu 4/24: 1; Fri 4/25: 2
Aircraft 1 | BARGE6 | 7 |  | 16 | 17 |  | 3 | 4 | BARGE6 |  | 2 | 4 | 440 | 7 | 16 | 17 | Tue 4/22: 3; Wed 4/23: 4
Aircraft 1 | MISC | [7 empty] | MISC |  |  |  | 2 | bar: Tue 4/22 to Fri 4/25
|  | ALL Aircraft 2 | [7 empty] | AC2 - Structures Complete
| Aircraft 2 | 97 | 19 | 71 | 67 | 1 | 31 | 28 | Total |  | 27 | 23 | 5281 | 96 | 67 | 58 | 15 | 20 | 21 | 27 | 13
Aircraft 2 | BARGE1 | 23 |  | 9 | 14 |  | 10 | 5 | BARGE1 |  | 10 | 5 | 1035 | 22 | 8 | 11 | 2 | 2 | 4 | 11 | 3
Aircraft 2 | BARGE2 | 11 |  | 9 | 5 | 1 |  | 4 | BARGE2 |  |  | 2 | 840 | 11 | 9 | 2 | 2 | 2 | 3 | 2 | 2
Aircraft 2 | BARGE3 | 35 |  | 20 | 20 |  | 14 | 4 | BARGE3 |  | 14 | 4 | 1824 | 35 | 20 | 19 | 7 | 11 | 7 | 7 | 3
Aircraft 2 | BARGE4 | 13 |  | 6 | 7 |  |  | 2 | BARGE4 |  |  | 2 | 348 | 13 | 6 | 6 | 1 | 2 | 2 | 3 | 5
Aircraft 2 | BARGE5 | 5 |  | 18 | 14 |  | 6 | 10 | BARGE5 |  | 2 | 7 | 776 | 5 | 15 | 13 | Mon 4/21: 2; Wed 4/23: 2; Thu 4/24: 1
Aircraft 2 | BARGE6 | 10 |  | 9 | 7 |  | 1 | 3 | BARGE6 |  | 1 | 3 | 457 | 10 | 9 | 7 | Mon 4/21: 1; Tue 4/22: 3; Wed 4/23: 3; Thu 4/24: 3
Aircraft 2 | MISC | [7 empty] | MISC |  |  |  | 1 | bar: Tue 4/22 to Fri 4/25

## Table 1 (2)
| Week Start | Weekly Performance to Date
| 2025-04-21 | ALL Aircraft (AC) |  |  |  | Shop Complete (AC) |  |  |  | Shop Complete (MM) |  |  | Major Milestone (MM) |  |  |  | Mon 4/21 | Tue 4/22 | Wed 4/23 | Thu 4/24 | Fri 4/25 | Sat 4/26 | Sun 4/27
|  | Actuals (BL) | Chk / Maint / Bltn | NCOs Closed | NCOs Created | Conformity | Non-Conformity | HF NCO | BARGE | Conformity | Non-Conformity | HF NCO | Balance to Go | Actuals | NCOs Closed | NCOs Created | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals
| Total | 190 | 47 | 127 | 117 | 1 | 63 | 66 |  |  | 51 | 55 | 9222 | 144 | 122 | 103 | 22 | 32 | 32 | 37 | 21
|  | ALL Aircraft 1 | [7 empty] | AC1 - Structures Complete
Aircraft 1 | Aircraft 1 | 93 | 28 | 56 | 50 |  | 32 | 38 | Total |  | 24 | 32 | 3941 | 48 | 55 | 45 | 7 | 12 | 11 | 10 | 8
Aircraft 1 | BARGE1 | 7 |  | 11 | 6 |  | 8 | 7 | BARGE1 |  | 8 | 7 | 759 | 7 | 11 | 4 | 1 | 1 | 1 | 2 | 2
Aircraft 1 | BARGE2 | 8 |  | 7 | 5 |  | 3 | 3 | BARGE2 |  | 2 | 2 | 761 | 8 | 7 | 5 | Mon 4/21: 2; Tue 4/22: 1; Wed 4/23: 1; Thu 4/24: 4
Aircraft 1 | BARGE3 | 15 |  | 7 | 11 |  | 11 | 11 | BARGE3 |  | 11 | 10 | 1326 | 15 | 7 | 11 | 3 | 2 | 5 | 2 | 3
Aircraft 1 | BARGE4 | 3 |  | 2 | 2 |  | 1 | 1 | BARGE4 |  | 1 | 1 | 156 | 3 | 2 | 1 | bar: Tue 4/22 to Fri 4/25
Aircraft 1 | BARGE5 | 53 |  | 13 | 9 |  | 6 | 12 | BARGE5 |  |  | 8 | 497 | 8 | 12 | 7 | Mon 4/21: 1; Tue 4/22: 4; Thu 4/24: 1; Fri 4/25: 2
Aircraft 1 | BARGE6 | 7 |  | 16 | 17 |  | 3 | 4 | BARGE6 |  | 2 | 4 | 440 | 7 | 16 | 17 | Tue 4/22: 3; Wed 4/23: 4
Aircraft 1 | MISC | [7 empty] | MISC |  |  |  | 2 | bar: Tue 4/22 to Fri 4/25
|  | ALL Aircraft 2 | [7 empty] | AC2 - Structures Complete
Aircraft 2 | Aircraft 2 | 97 | 19 | 71 | 67 | 1 | 31 | 28 | Total |  | 27 | 23 | 5281 | 96 | 67 | 58 | 15 | 20 | 21 | 27 | 13
Aircraft 2 | BARGE1 | 23 |  | 9 | 14 |  | 10 | 5 | BARGE1 |  | 10 | 5 | 1035 | 22 | 8 | 11 | 2 | 2 | 4 | 11 | 3
Aircraft 2 | BARGE2 | 11 |  | 9 | 5 | 1 |  | 4 | BARGE2 |  |  | 2 | 840 | 11 | 9 | 2 | 2 | 2 | 3 | 2 | 2
Aircraft 2 | BARGE3 | 35 |  | 20 | 20 |  | 14 | 4 | BARGE3 |  | 14 | 4 | 1824 | 35 | 20 | 19 | 7 | 11 | 7 | 7 | 3
Aircraft 2 | BARGE4 | 13 |  | 6 | 7 |  |  | 2 | BARGE4 |  |  | 2 | 348 | 13 | 6 | 6 | 1 | 2 | 2 | 3 | 5
Aircraft 2 | BARGE5 | 5 |  | 18 | 14 |  | 6 | 10 | BARGE5 |  | 2 | 7 | 776 | 5 | 15 | 13 | Mon 4/21: 2; Wed 4/23: 2; Thu 4/24: 1
Aircraft 2 | BARGE6 | 10 |  | 9 | 7 |  | 1 | 3 | BARGE6 |  | 1 | 3 | 457 | 10 | 9 | 7 | Mon 4/21: 1; Tue 4/22: 3; Wed 4/23: 3; Thu 4/24: 3
Aircraft 2 | MISC | [7 empty] | MISC |  |  |  | 1 | bar: Tue 4/22 to Fri 4/25