## Table 1
| Week Start | Weekly Performance to Date
| 45740 | ALL Aircraft (AC) |  |  |  | Shop Complete (AC) |  |  |  | Shop Complete (MM) |  |  | Major Milestone (MM) |  |  |  | Mon 3/24 | Tue 3/25 | Wed 3/26 | Thu 3/27 | Fri 3/28 | Sat 3/29 | Sun 3/30
|  | Actuals (BL) | Chk / Maint / Bltn | NCOs Closed | NCOs Created | Conformity | Non-Conformity | HF NCO | BARGE | Conformity | Non-Conformity | HF NCO | Balance to Go | Actuals | NCOs Closed | NCOs Created | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals
| Total | 171 | 29 | 173 | 195 |  | 45 | 83 |  |  | 38 | 66 | 9806 | 146 | 170 | 183 | 26 | 36 | 34 | 30 | 20
|  | ALL Aircraft 1 | [7 empty] | AC1 - Structures Complete
| Aircraft 1 | 78 | 16 | 90 | 104 |  | 19 | 44 | Total |  | 17 | 36 | 4134 | 55 | 88 | 95 | 11 | 15 | 13 | 12 | 4
Aircraft 1 | BARGE1 | 12 |  | 13 | 11 |  | 3 | 7 | BARGE1 |  | 3 | 5 | 785 | 11 | 13 | 11 | Mon 3/24: 1; Tue 3/25: 2; Wed 3/26: 5; Thu 3/27: 3
Aircraft 1 | BARGE2 | 7 |  | 18 | 29 |  | 2 | 8 | BARGE2 |  | 2 | 7 | 795 | 7 | 18 | 29 | Mon 3/24: 2; Tue 3/25: 3; Wed 3/26: 1; Fri 3/28: 1
Aircraft 1 | BARGE3 | 22 |  | 12 | 9 |  | 6 | 13 | BARGE3 |  | 6 | 12 | 1416 | 22 | 12 | 9 | 6 | 4 | 5 | 5 | 2
Aircraft 1 | BARGE4 | 3 |  | 6 | 15 |  | 1 | 1 | BARGE4 |  | 1 | 1 | 133 | 3 | 4 | 7 | Tue 3/25: 2; Thu 3/27: 1
Aircraft 1 | BARGE5 | 8 |  | 23 | 30 |  | 3 | 8 | BARGE5 |  | 3 | 7 | 517 | 8 | 23 | 29 | Mon 3/24: 1; Tue 3/25: 2; Wed 3/26: 2; Thu 3/27: 3
Aircraft 1 | BARGE6 | 4 |  | 18 | 10 |  | 2 | 4 | BARGE6 |  | 2 | 4 | 468 | 4 | 18 | 10 | Mon 3/24: 1; Tue 3/25: 2; Fri 3/28: 1
Aircraft 1 | MISC | 22 |  |  |  |  | 2 | 3 | MISC |  |  |  | 20
|  | ALL Aircraft 2 | [7 empty] | AC2 - Structures Complete
| Aircraft 2 | 93 | 13 | 83 | 91 |  | 26 | 39 | Total |  | 21 | 30 | 5672 | 91 | 82 | 88 | 15 | 21 | 21 | 18 | 16
Aircraft 2 | BARGE1 | 23 |  | 21 | 22 |  | 3 | 7 | BARGE1 |  | 3 | 5 | 1129 | 23 | 21 | 22 | 4 | 8 | 5 | 4 | 2
Aircraft 2 | BARGE2 | 10 |  | 12 | 18 |  | 3 | 8 | BARGE2 |  | 1 | 6 | 886 | 10 | 11 | 18 | Mon 3/24: 2; Tue 3/25: 4; Wed 3/26: 1; Fri 3/28: 3
Aircraft 2 | BARGE3 | 25 |  | 9 | 6 |  | 5 | 4 | BARGE3 |  | 5 | 4 | 1929 | 25 | 9 | 6 | 4 | 3 | 6 | 7 | 5
Aircraft 2 | BARGE4 | 16 |  | 6 | 7 |  | 2 | 3 | BARGE4 |  | 2 | 3 | 401 | 16 | 6 | 7 | 3 | 2 | 3 | 3 | 5
Aircraft 2 | BARGE5 | 11 |  | 15 | 23 |  | 4 | 14 | BARGE5 |  | 4 | 10 | 800 | 10 | 15 | 20 | Tue 3/25: 2; Wed 3/26: 5; Thu 3/27: 3
Aircraft 2 | BARGE6 | 7 |  | 20 | 15 |  | 6 | 2 | BARGE6 |  | 6 | 2 | 502 | 7 | 20 | 15 | 2 | 2 | 1 | 1 | 1
Aircraft 2 | MISC | 1 |  |  |  |  | 3 | 1 | MISC |  |  |  | 25