## Table 1
| Week Start | Weekly Performance to Date
| 45754 | ALL Aircraft (AC) |  |  |  | Shop Complete (AC) |  |  |  | Shop Complete (MM) |  |  | Major Milestone (MM) |  |  |  | Mon 4/7 | Tue 4/8 | Wed 4/9 | Thu 4/10 | Fri 4/11 | Sat 4/12 | Sun 4/13
|  | Actuals (BL) | Chk / Maint / Bltn | NCOs Closed | NCOs Created | Conformity | Non-Conformity | HF NCO | BARGE | Conformity | Non-Conformity | HF NCO | Balance to Go | Actuals | NCOs Closed | NCOs Created | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals
| Total | 203 | 51 | 154 | 152 | 1 | 72 | 72 |  |  | 58 | 58 | 9514 | 155 | 147 | 148 | 34 | 41 | 24 | 23 | 12 | 17 | 4
|  | ALL Aircraft 1 | [7 empty] | AC1 - Structures Complete
| Aircraft 1 | 99 | 28 | 68 | 59 |  | 35 | 42 | Total |  | 25 | 35 | 4042 | 52 | 65 | 56 | 17 | 11 | 8 | 8 | 3 | 3 | 2
Aircraft 1 | Barge1 | 8 |  | 17 | 13 |  | 7 | 10 | Barge1 |  | 7 | 9 | 776 | 7 | 16 | 13 | 3 | 1 | 1 | 1 | 1
Aircraft 1 | Barge2 | 10 |  | 14 | 10 |  | 2 | 4 | Barge2 |  | 2 | 3 | 779 | 10 | 12 | 8 | 1 | 2 | 2 | 3 |  | 2
Aircraft 1 | Barge3 | 20 |  | 5 | 9 |  | 10 | 12 | Barge3 |  | 10 | 11 | 1388 | 19 | 5 | 9 | Mon 4/7: 11; Tue 4/8: 4; Wed 4/9: 3; Fri 4/11: 1
Aircraft 1 | Barge4 | 2 |  | 3 | 3 |  | 2 | 1 | Barge4 |  | 2 | 1 | 128 | 2 | 3 | 3 | bar: Mon 4/7; Thu 4/10
Aircraft 1 | Barge5 | 52 |  | 8 | 10 |  | 12 | 11 | Barge5 |  | 2 | 7 | 515 | 7 | 8 | 9 |  | 2 | 1 | 2 | 1 |  | 1
Aircraft 1 | Barge6 | 7 |  | 21 | 14 |  | 2 | 4 | Barge6 |  | 2 | 4 | 454 | 7 | 21 | 14 | 1 | 2 | 1 | 1 |  | 1 | 1
Aircraft 1 | MISC | [7 empty] | MISC |  |  |  | 2
|  | ALL Aircraft 2 | [7 empty] | AC2 - Structures Complete
| Aircraft 2 | 104 | 23 | 86 | 93 | 1 | 37 | 30 | Total |  | 33 | 23 | 5472 | 103 | 82 | 92 | 17 | 30 | 16 | 15 | 9 | 14 | 2
Aircraft 2 | Barge1 | 27 |  | 8 | 21 |  | 14 | 6 | Barge1 |  | 14 | 5 | 1083 | 27 | 7 | 21 | 3 | 10 | 3 | 3 | 2 | 4 | 2
Aircraft 2 | Barge2 | 10 |  | 23 | 20 | 1 | 2 | 6 | Barge2 |  | 1 | 3 | 863 | 10 | 21 | 19 | 1 | 3 |  | 4 | 1 | 1
Aircraft 2 | Barge3 | 28 |  | 11 | 14 |  | 13 | 3 | Barge3 |  | 13 | 3 | 1883 | 28 | 11 | 14 | 7 | 8 | 5 | 3 | 2 | 3
Aircraft 2 | Barge4 | 14 |  | 6 | 6 |  | 1 | 2 | Barge4 |  | 1 | 2 | 373 | 14 | 6 | 6 | 4 | 3 | 2 | 1 | 2 | 2
Aircraft 2 | Barge5 | 16 |  | 18 | 20 |  | 6 | 10 | Barge5 |  | 3 | 7 | 789 | 15 | 17 | 20 | 1 | 2 | 3 | 3 | 2 | 4
Aircraft 2 | Barge6 | 9 |  | 20 | 12 |  | 1 | 3 | Barge6 |  | 1 | 3 | 480 | 9 | 20 | 12 | Mon 4/7: 1; Tue 4/8: 4; Wed 4/9: 3; Thu 4/10: 1
Aircraft 2 | MISC | [7 empty] | MISC |  |  |  | 1