## Table 1
| Week Start | Weekly Performance to Date
| 45775 | ALL Aircraft (AC) |  |  |  | Shop Complete (AC) |  |  |  | Shop Complete (MM) |  |  | Major Milestone (MM) |  |  |  | Mon 4/28 | Tue 4/29 | Wed 4/30 | Thu 5/1 | Fri 5/2 | Sat 5/3 | Sun 5/4
|  | Actuals (BL) | Chk / Maint / Bltn | NCOs Closed | NCOs Created | Conformity | Non-Conformity | HF NCO | BARGE | Conformity | Non-Conformity | HF NCO | Balance to Go | Actuals | NCOs Closed | NCOs Created | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals
| Total | 214 | 37 | 139 | 134 | 1 | 61 | 63 |  |  | 54 | 52 | 9050 | 160 | 136 | 128 | 36 | 41 | 33 | 30 | 20
|  | ALL Aircraft 1 | [7 empty] | AC1 - Structures Complete
| Aircraft 1 | 115 | 16 | 69 | 60 |  | 29 | 36 | Total |  | 25 | 30 | 3875 | 61 | 67 | 56 | 14 | 15 | 14 | 10 | 8
Aircraft 1 | BARGE1 | 8 |  | 6 | 6 |  | 8 | 6 | BARGE1 |  | 8 | 6 | 748 | 8 | 6 | 6 | Mon 4/28: 2; Tue 4/29: 2; Wed 4/30: 1; Thu 5/1: 3
Aircraft 1 | BARGE2 | 7 |  | 12 | 14 |  | 4 | 3 | BARGE2 |  | 3 | 2 | 744 | 7 | 10 | 13 | Mon 4/28: 3; Tue 4/29: 2; Wed 4/30: 2
Aircraft 1 | BARGE3 | 22 |  | 5 | 7 |  | 10 | 11 | BARGE3 |  | 10 | 10 | 1298 | 21 | 5 | 7 | 6 | 4 | 4 | 2 | 5
Aircraft 1 | BARGE4 | 9 |  | 16 | 18 |  |  | 2 | BARGE4 |  |  | 2 | 164 | 9 | 16 | 17 | 1 | 2 | 3 | 2 | 1
Aircraft 1 | BARGE5 | 59 |  | 8 | 5 |  | 4 | 11 | BARGE5 |  | 1 | 7 | 491 | 6 | 8 | 3 | Tue 4/29: 2; Wed 4/30: 2; Thu 5/1: 1; Fri 5/2: 1
Aircraft 1 | BARGE6 | 10 |  | 22 | 10 |  | 3 | 3 | BARGE6 |  | 3 | 3 | 428 | 10 | 22 | 10 | 2 | 3 | 2 | 2 | 1
Aircraft 1 | MISC | [7 empty] | MISC |  |  |  | 2
|  | ALL Aircraft 2 | [7 empty] | AC2 - Structures Complete
| Aircraft 2 | 99 | 21 | 70 | 74 | 1 | 32 | 27 | Total |  | 29 | 22 | 5175 | 99 | 69 | 72 | 22 | 26 | 19 | 20 | 12
Aircraft 2 | BARGE1 | 18 |  | 16 | 16 |  | 11 | 4 | BARGE1 |  | 11 | 4 | 1019 | 18 | 16 | 16 | 5 | 1 | 4 | 6 | 2
Aircraft 2 | BARGE2 | 13 |  | 9 | 9 | 1 | 1 | 4 | BARGE2 |  | 1 | 2 | 827 | 13 | 8 | 9 | 2 | 4 | 3 | 3 | 1
Aircraft 2 | BARGE3 | 32 |  | 12 | 12 |  | 14 | 3 | BARGE3 |  | 14 | 3 | 1783 | 32 | 12 | 12 | 10 | 10 | 7 | 4 | 1
Aircraft 2 | BARGE4 | 9 |  | 3 | 9 |  |  | 2 | BARGE4 |  |  | 2 | 339 | 9 | 3 | 7 | Tue 4/29: 3; Wed 4/30: 1; Fri 5/2: 5
Aircraft 2 | BARGE5 | 12 |  | 20 | 25 |  | 5 | 10 | BARGE5 |  | 2 | 7 | 763 | 12 | 20 | 25 | 2 | 4 | 2 | 2 | 2
Aircraft 2 | BARGE6 | 15 |  | 10 | 3 |  | 1 | 4 | BARGE6 |  | 1 | 4 | 443 | 15 | 10 | 3 | 3 | 4 | 2 | 5 | 1
Aircraft 2 | MISC | [7 empty] | MISC |  |  |  | 1