## Table 1
| Week Start | Weekly Performance to Date
| 45782 | ALL Aircraft (AC) |  |  |  | Shop Complete (AC) |  |  |  | Shop Complete (MM) |  |  | Major Milestone (MM) |  |  |  | Mon 5/5 | Tue 5/6 | Wed 5/7 | Thu 5/8 | Fri 5/9 | Sat 5/10 | Sun 5/11
|  | Actuals (BL) | Chk / Maint / Bltn | NCOs Closed | NCOs Created | Conformity | Non-Conformity | HF NCO | BARGE | Conformity | Non-Conformity | HF NCO | Balance to Go | Actuals | NCOs Closed | NCOs Created | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals
| Total | 220 | 28 | 134 | 115 | 1 | 69 | 65 |  |  | 59 | 54 | 8876 | 163 | 129 | 112 | 30 | 30 | 32 | 44 | 27
|  | ALL Aircraft 1 | [7 empty] | AC1 - Structures Complete
| Aircraft 1 | 83 | 14 | 54 | 52 |  | 28 | 35 | Total |  | 23 | 29 | 3821 | 50 | 49 | 49 | 13 | 13 | 9 | 8 | 7
Aircraft 1 | BARGE1 | 13 |  | 7 | 4 |  | 7 | 6 | BARGE1 |  | 7 | 6 | 733 | 13 | 7 | 4 | 2 | 3 | 3 | 3 | 2
Aircraft 1 | BARGE2 | 12 |  | 14 | 12 |  | 3 | 3 | BARGE2 |  | 2 | 2 | 731 | 12 | 14 | 11 | 4 | 2 | 2 | 3 | 1
Aircraft 1 | BARGE3 | 9 |  | 10 | 8 |  | 12 | 11 | BARGE3 |  | 12 | 10 | 1259 | 9 | 10 | 8 | Mon 5/5: 5; Tue 5/6: 4
Aircraft 1 | BARGE4 | 2 |  | 6 | 9 |  |  | 1 | BARGE4 |  |  | 1 | 192 | 2 | 6 | 9 | bar: Tue 5/6 to Wed 5/7
Aircraft 1 | BARGE5 | 40 |  | 9 | 9 |  | 4 | 11 | BARGE5 |  |  | 7 | 482 | 7 | 5 | 8 | Mon 5/5: 1; Tue 5/6: 2; Wed 5/7: 2; Fri 5/9: 2
Aircraft 1 | BARGE6 | 7 |  | 8 | 10 |  | 2 | 3 | BARGE6 |  | 2 | 3 | 422 | 7 | 7 | 9 | 1 | 1 | 1 | 2 | 2
Aircraft 1 | MISC | [7 empty] | MISC |  |  |  | 2
|  | ALL Aircraft 2 | [7 empty] | AC2 - Structures Complete
| Aircraft 2 | 137 | 14 | 80 | 63 | 1 | 41 | 30 | Total |  | 36 | 25 | 5055 | 113 | 80 | 63 | 17 | 17 | 23 | 36 | 20
Aircraft 2 | BARGE1 | 18 |  | 13 | 8 |  | 13 | 4 | BARGE1 |  | 13 | 4 | 995 | 18 | 13 | 8 | 4 | 4 | 5 | 4 | 1
Aircraft 2 | BARGE2 | 12 |  | 10 | 9 | 1 | 1 | 4 | BARGE2 |  | 1 | 2 | 812 | 12 | 10 | 9 | 2 | 4 | 2 | 3 | 1
Aircraft 2 | BARGE3 | 40 |  | 21 | 19 |  | 12 | 6 | BARGE3 |  | 12 | 6 | 1743 | 39 | 21 | 19 | 7 | 5 | 10 | 12 | 5
Aircraft 2 | BARGE4 | 20 |  | 6 | 3 |  |  | 2 | BARGE4 |  |  | 2 | 319 | 20 | 6 | 3 | Mon 5/5: 1; Thu 5/8: 11; Fri 5/9: 8
Aircraft 2 | BARGE5 | 35 |  | 20 | 16 |  | 9 | 11 | BARGE5 |  | 4 | 8 | 753 | 12 | 20 | 16 | 1 | 2 | 1 | 4 | 4
Aircraft 2 | BARGE6 | 12 |  | 10 | 8 |  | 6 | 3 | BARGE6 |  | 6 | 3 | 432 | 12 | 10 | 8 | 2 | 2 | 5 | 2 | 1
Aircraft 2 | MISC | [7 empty] | MISC |  |  |  | 1